## Cover
SURAKKHA Action - DG ECHO 2026/00158/RQ/01/03
FIVDB - Detailed MEAL Plan & Indicator Performance Tracking Table (IPTT)
Local implementing partner under the technical support of Plan International Bangladesh (PIB)
Action title | Strengthening Integrated EiE, Child Protection, Health & GBV Services for Rohingya Refugees and Host Communities in Cox's Bazar, and Scaling up Multi-Hazard Anticipatory Action (SURAKKHA)
Request number | 2026/00158/RQ/01/03
Action period | 1 June 2026 – 31 May 2028 (24 months / 8 quarters)
Consortium lead | Save the Children International (SC)
Technical supervision of FIVDB | Plan International Bangladesh (PIB)
FIVDB scope | Result 1 – Education in Emergencies (Activities 1-7); Result 2 – Child Protection (Activities 1, 3, 4, 5)
Target camps | Camp 1W, Camp 6, Camp 21, Camp 24 (Cox's Bazar)
FIVDB budget | EUR 592,371.41
Contents
• 1. MEAL Framework, RACI, DCP & Reporting (combined: Framework, RACI Matrix, Data Collection Plan, Reporting Schedule)
• 4. M&E Calendar
• 6. CFM Log Template
• 6b. Collective Feedback
• 6c. Target Breakdown (facility & beneficiary targets by sex/disability)
• 7. IPTT (Indicator Performance Tracking Table)
• 8. Activity Tracker (implementation progress by activity)
• 10. Activity Data Log (per-event data entry, Host/FDMN, sex & age, target/discrepancy)
• 11. Distribution Log (per-item distribution data entry, Host/FDMN, sex & age, ODM/PDM, target/discrepancy)
• 12. Dropout Tracker (learners, staff & volunteers by designation, month-wise trend)
• 12b. Attendance Tracker (learner attendance rate by camp, month-wise under quarter)
• 13. Budget Tracker - Monthly / 13b. Quarterly / 13c. Yearly & Total Project Period (activity-wise smart budget tracking)
• 14. Activity List (simplified, for sharing with the team)
Note: FIVDB-specific baselines, targets and budget figures throughout this workbook are derived from the consortium Logframe (Annex I), Beneficiary Table (Annex 2, EiE_PIB / CP_PIB_V2 tabs) and Locations & Integration Mapping (Annex 3). They are indicative and should be validated with PIB at inception.
Common Points of Confusion (FAQ) - read this before using the workbook
Q: How is 'segregation' done, and why these 4 categories?
A: Every person-level field in this workbook (Activity Data Log, Distribution Log, Dropout Tracker, Attendance Tracker) uses the SAME four categories: Girls <18, Boys <18, Women 18+, Men 18+ - always in that order. Each is further split Host (community) vs FDMN (Forcibly Displaced Myanmar Nationals - the official Government of Bangladesh term for Rohingya refugees), giving 8 raw entry columns that roll up into the 4 categories shown in summaries and the Dashboard. This one convention is used everywhere so figures from different sheets can be added together safely.
Q: Why do some indicators show a blue 'auto' cell and others a yellow manual cell?
A: IPTT (Sheet 7): 'Number'-unit indicators are AUTOMATIC (light-blue) - cumulative sums pulled from the Activity Data Log and Distribution Log via each entry's own Linked Indicator(s) match, no typing required. '%'-unit indicators are MANUAL (yellow) - a percentage cannot be derived by summing headcounts, so FIVDB enters it directly from survey/assessment data. Activity Tracker (Sheet 8): PLANNED is always manual (FIVDB's own quarterly target); ACTUAL is always automatic (summed from Sheets 10-11).
Q: Why are there three different-looking activity codes (R1A1, R1A1.1, R1-I1)?
A: R1A1 / R1A2... = FIVDB's real Detailed Budget Reference codes (Activity Tracker parent codes). R1A1.1 / R1A1.2... = the SUB-ACTIVITY level under each budget code (Activity Tracker rows, Data Log/Distribution Log entries). R1-I1 / R2-I1... = INDICATOR codes (IPTT rows only) - a completely separate numbering system, cross-referenced to sub-activity codes via the 'Linked Activity/ies' and 'Linked Indicator(s)' columns. None of these three are typos of each other.
Q: Why does the 'How to Articulate in Narrative Report' text mention numbers I haven't entered?
A: For 'Number'-unit IPTT indicators this narrative is a live formula, not static text - it recalculates the moment new data is logged in Sheets 10-11, including a full sex/age breakdown (Girls <18 / Boys <18 / Women 18+ / Men 18+) and the indicator's own Definition and Source and Method of Data Collection. Before any data is logged it will show 0s, not blanks - that is expected.
Q: Why do several % targets look almost identical (75-95% range)?
A: These are the officially approved consortium targets from the Logframe (Annex I) and Narrative Proposal, not FIVDB-set or copy-pasted figures. They cluster in a similar range because they derive from comparable prior-phase (ECHO HIP 2023) performance baselines across CP/PSS/GBV service lines. Each indicator's Comments column (Sheet 7) cites its own distinct source paragraph.
Q: What does 'Cumulative' vs the quarterly columns mean?
A: TARGET and ACTUAL are both shown by individual quarter (Q1...Q8) AND as a running Cumulative Actual to Date (which is simply the latest quarter with a non-blank value). % of LOP Target Achieved always compares the CUMULATIVE actual against the full life-of-project target, not any single quarter's figure.
Q: Why do some FIVDB figures differ from the wider consortium total?
A: FIVDB delivers only part of Result 1 (alongside SC) and part of Result 2 (Activities 1, 3, 4, 5; Activity 2 is SC-led). Every indicator's Comments/Definition explicitly states both FIVDB's own target AND, where relevant, the full consortium target - FIVDB is only accountable for its own figure, never the consortium total.
Q: What is RAG Status based on?
A: Activity Tracker (Sheet 8): RAG compares cumulative ACTUAL (auto, from Sheets 10-11) against cumulative PLANNED (FIVDB's own manual quarterly targets) - On Track >=90%, Slightly Behind 70-89%, Behind <70%. It has nothing to do with the IPTT's indicator-level status.

## 1. MEAL-RACI-DCP-Reporting
1. MEAL Framework, RACI Matrix, Data Collection Plan & Reporting Schedule
FIVDB delivers Result 1 (Education) and Result 2 Activities 1, 3, 4, 5 (Child Protection) under PIB's technical supervision, within SC's consortium-wide MEAL system. This sheet combines four previously separate sections (Framework, RACI, Data Collection Plan, Reporting Schedule) for a single, continuous read.
1.1 MEAL Objectives
Objective | Reference
Track FIVDB's contribution to Result 1 and Result 2 indicators against agreed targets, disaggregated by sex, age and disability. | Logframe (Annex I), Result 1 & 2 indicators
Ensure quality, safety and protection-sensitivity of education and case-management/PSS services delivered by FIVDB. | CP Minimum Standards in Humanitarian Settings; Plan Safeguarding Framework
Provide accurate, timely, verifiable data to PIB for consolidation into SC's ECHO interim/final reporting. | Narrative Proposal, reporting obligations section
Maintain a functioning, safe, child-friendly complaints and feedback mechanism (CFM) across all FIVDB camps. | Plan/FIVDB CFM SOP
Generate learning that informs adaptive management of FIVDB's activities across the 24-month action. | MEAL Plan, Section 10 (Learning & Adaptive Management)
1.2 Guiding Principles
Principle | Reference
Do no harm / child safeguarding is non-negotiable in all data collection involving children. | Plan Safeguarding Framework (Updated Risk Assessment Process, 2024)
Participation: communities (adolescents, parents, CESGs, CBCPCs) are consulted on monitoring design, not only as data sources. | CHS Commitment 4 (participation and feedback)
Triangulation: indicators are, where possible, verified through more than one data source. | IPTT & MEAL Workbook, Sheet 7, Verification/QA Step column
Proportionality: MEAL effort is proportionate to FIVDB's budget share and risk profile within the consortium. | FIVDB Detailed Budget (EUR 592,371.41 total)
Data protection: beneficiary data (esp. CP case data) is stored/shared under SC/PIB's data protection protocol. | SC/PIB Data Protection Protocol
1.3 MEAL Governance Structure
Level | Responsibility | Reference
FIVDB | Field-level data collection, first-line quality checks, case management, CFM Tier 1, monthly indicator tracker updates. | IPTT & MEAL Workbook, Sheets 7-8
PIB (technical supervision) | Technical quality assurance, monthly data-quality spot checks, consolidation of FIVDB data into EiE_PIB / CP_PIB_V2 tabs, CFM Tier 2 (sensitive/safeguarding) escalation point. | Narrative Proposal, technical supervision arrangements
SC (consortium lead) | Consortium-wide MEAL standards, indicator consolidation across all partners, ECHO interim/final reporting, leads mid-term/final evaluation. | Logframe (Annex I), consortium reporting structure
1.4 RACI Matrix - FIVDB / PIB / SC
R = Responsible A = Accountable C = Consulted I = Informed
Function | FIVDB | PIB | SC (Lead) | Frequency | Reference
Field data collection (attendance, case files, distributions) | R | C | I | Ongoing/daily | IPTT & MEAL Workbook, Sheets 10-11
Data entry & indicator tracker update | R | A | I | Weekly | IPTT & MEAL Workbook, Sheet 7
Data quality spot-checks / verification visits | C | R | A | Monthly | Field Reporting Templates, Template 7
Indicator consolidation (FIVDB/PIB share) | Input | R | A | Monthly | IPTT & MEAL Workbook, Sheet 7
Consortium indicator consolidation (all partners) | I | Input | R | Quarterly | Logframe (Annex I)
Complaints & feedback handling - Tier 1 (non-sensitive) | R | C | I | Ongoing | MEAL Plan, Section 9 (AAP/CFM)
Complaints & feedback handling - Tier 2 (safeguarding/sensitive) | Escalate | R | A | Within 24-48h | Field Reporting Templates, Template 16
Post-distribution monitoring (PDM) | R | C (QC) | I | Per distribution | IPTT & MEAL Workbook, Sheet 11 (ODM/PDM columns)
Case-management supervision | R (case workers) | R (technical) | A (standards) | Weekly/bi-weekly | CP Minimum Standards, 7-step process
Training delivery & pre/post assessment | R | C | I | Per training | Field Reporting Templates, Template 2
Baseline / KAP survey | Input | R | A | Month 1-2 | MEAL Plan, Section 8 (M&E Calendar)
Mid-term review | Input | C | R | Month 12 | MEAL Plan, Section 8 (M&E Calendar)
Final evaluation | Input | C | R | Month 22-24 | MEAL Plan, Section 8 (M&E Calendar)
Interim / final ECHO report data package | Input | R | A | Month 12 / 24 | Logframe cover page (reporting schedule)
Safeguarding incident management | R (first response) | A (escalation) | I | Within 24-48h | Field Reporting Templates, Template 16
1.5 Data Collection Plan - Tools & Methods
Tool | Purpose | Linked indicator(s) | Responsible | Frequency | Reference
Enrolment/attendance registers (CBLF) | Track learner enrolment, attendance, drop-out | R1-I1, R1-I2, R1-I4, SO-I2 | Facilitators | Daily/weekly | IPTT & MEAL Workbook, Sheet 7
Case management database (CPIMS+ or equivalent) | Track CP case ID, planning, services, closure | R2-I1, R2-I2 | Case workers | Per case, continuous | CP Minimum Standards, 7-step process
Training registers + pre/post-tests | Measure knowledge/skills gained | R1-I5, R1-I7, R2-I3 | MEAL Officer / trainers | Per training | FIVDB Detailed Budget, R1A4/R2A5
Distribution/dispatch records & waybills | Verify materials/kits reached beneficiaries | R1-I3, R1-I4 | Logistics / MEAL Officer | Per distribution | IPTT & MEAL Workbook, Sheet 11
Referral tracker (EiE <-> CP <-> Health) | Track cross-sector referrals & follow-up | R1-I8, R2-I1 | Case workers / facilitators | Ongoing, reviewed weekly | Field Reporting Templates, Template 8
Post-distribution monitoring (PDM) survey | Verify quality, appropriateness, safety of distributions | SO-I1 | MEAL Officer | Within 2-4 weeks of distribution | IPTT & MEAL Workbook, Sheet 11 (PDM columns)
PSS pre/post assessment (IASC domains) | Measure wellbeing/coping change | R2-I4 | Case workers / PSS facilitators | At PSS group entry & exit | IASC Common M&E Framework
Community perception / KAP survey | Measure safety, accountability, satisfaction | SO-I1 | MEAL Officer / PIB | Baseline, midline, endline | MEAL Plan, Section 8 (M&E Calendar)
Facility monitoring checklist | Verify safe-learning standards, environmental activities | R1-I2, R1-I9 | Education Officer | Quarterly | Field Reporting Templates, Template 5
Complaints & Feedback Mechanism (CFM) log | Record, triage, resolve complaints | SO-I1 | MEAL Officer / Safeguarding FP | Ongoing | MEAL Plan, Section 9 (AAP/CFM)
1.6 Reporting Schedule
Report | Due | Prepared by | Submitted to | Reference
Weekly activity/attendance summary | Weekly | FIVDB field teams | FIVDB Project Manager / PIB | Field Reporting Templates, Template 1
Monthly progress & indicator update | Monthly | FIVDB MEAL Officer | PIB | IPTT & MEAL Workbook, Sheet 7
Quarterly narrative + indicator report | Quarterly | FIVDB Project Manager | PIB -> SC | IPTT & MEAL Workbook, Sheets 7-8
Interim narrative & financial report inputs | Month 12 | FIVDB | PIB -> SC -> DG ECHO | Logframe cover page (action timeline)
Final narrative & financial report inputs | Month 24 | FIVDB | PIB -> SC -> DG ECHO | Logframe cover page (action timeline)
Incident / safeguarding report | Within 24-48h of incident | FIVDB Safeguarding Focal Point | PIB Safeguarding Focal Point | Field Reporting Templates, Template 16

## 4. M&E Calendar
4. Monitoring & Evaluation Calendar (by month, grouped under quarter)
X = planned activity in that month. Q1 = Jun-Aug 2026 ... Q8 = Mar-May 2028; months are grouped under their quarter. 'Tool Used' cites the actual template/sheet; 'Tool Status' flags where no ready-made instrument exists yet and needs developing. 'Full Process' gives the step-by-step method, Step 1 to last.
Activity | Tool Used | Tool Status | Indicator Reference | Activity Reference | Full Process (Step 1 to last) | Q1 |  |  | Q2 |  |  | Q3 |  |  | Q4 |  |  | Q5 |  |  | Q6 |  |  | Q7 |  |  | Q8 |  |  | Notes
[6 empty] | 06/2026 | 07/2026 | 08/2026 | 09/2026 | 10/2026 | 11/2026 | 12/2026 | 01/2027 | 02/2027 | 03/2027 | 04/2027 | 05/2027 | 06/2027 | 07/2027 | 08/2027 | 09/2027 | 10/2027 | 11/2027 | 12/2027 | 01/2028 | 02/2028 | 03/2028 | 04/2028 | 05/2028
Baseline / KAP survey | Baseline/KAP Survey Questionnaire | Needs development - no ready-made instrument yet in the Field Reporting Templates pack | SO-I1 | INC-6 | Step 1: Design/adapt questionnaire with PIB MEAL. Step 2: Train enumerators. Step 3: Sample households per camp (stratified by sex/age/disability). Step 4: Administer face-to-face (paper or KoBo/ODK). Step 5: Clean and analyse data. Step 6: Share baseline report with PIB. | X | X | X | X | X | X | [18 empty] | Month 1-2 start-up
Monthly indicator tracking | IPTT Data Reporting Form | Needs development - removed from the Field Reporting Templates pack pending redesign (see pack's closing note) | All Sheet 7 indicators | N/A (cross-cutting) | Step 1: Field staff record activity data in source registers. Step 2: MEAL Officer extracts monthly cumulative figures. Step 3: Enter into IPTT Sheet 7 ACTUAL columns. Step 4: Cross-check against Activity Tracker Sheet 8. Step 5: Flag off-track indicators to Project Manager. | X | X | X | X | X | X | X | X | X | X | X | X | X | X | X | X | X | X | X | X | X | X | X | X | Continuous
Quarterly data review (FIVDB-PIB-SC) | IPTT (Sheet 7) + Activity Tracker (Sheet 8) | Exists - this workbook | All indicators | All activities | Step 1: MEAL Officer prepares quarterly extract. Step 2: Joint meeting scheduled with PIB/SC. Step 3: Walk through IPTT % Achieved and Activity Tracker RAG status together. Step 4: Agree corrective actions for off-track items. Step 5: Minute and circulate action points. | X | X | X | X | X | X | X | X | X | X | X | X | X | X | X | X | X | X | X | X | X | X | X | X | Every quarter
Data quality spot-check (PIB) | Data Quality Check / Spot-Check Report | Exists - Field Reporting Templates, Template 7 | All indicators | N/A (cross-cutting) | Step 1: PIB MEAL randomly samples >=10% of source records. Step 2: Verify reported value against source document. Step 3: Record match/discrepancy and root cause. Step 4: Calculate % accuracy. Step 5: Agree corrective action with FIVDB; set follow-up date. | X | X | X | X | X | X | X | X | X | X | X | X | X | X | X | X | X | X | X | X | X | X | X | X | Monthly, reviewed quarterly
Post-distribution monitoring (PDM) | PDM Questionnaire | Needs development - ODM/PDM tracking columns exist (Sheet 11) but no standalone PDM survey instrument yet | SO-I1 | R1A2, R1A3, R2A3 | Step 1: Select random sample of recipients (2-4 weeks post-distribution). Step 2: Contact by phone or in-person. Step 3: Administer PDM questionnaire (quality, appropriateness, safety, satisfaction). Step 4: Record findings in Distribution Log Sheet 11 (PDM Findings). Step 5: Flag issues for follow-up. | X | X | X | X | X | X | X | X | X | X | X | X | X | X | X | X | X | X | X | X | X | X | X | X | Per distribution cycle
Case management supervision & review | CPMS Supervision Checklist | Needs development - referenced against CP Minimum Standards but not yet built as a standalone checklist | R2-I1, R2-I5 | R2A1 | Step 1: PIB technical supervisor reviews case files. Step 2: Individual/group supervision session with case workers. Step 3: Score against CPMS supervision checklist. Step 4: Identify coaching needs. Step 5: Record in supervision log; follow up at next session. | X | X | X | X | X | X | X | X | X | X | X | X | X | X | X | X | X | X | X | X | X | X | X | X | Weekly/bi-weekly
Facility monitoring checklist | Monitoring Visit Checklist | Exists - Field Reporting Templates, Template 5 | R1-I2, R1-I9, R2-I4 | R1A2, R2A3 | Step 1: Joint FIVDB-PIB site visit scheduled. Step 2: Complete the relevant Template 5 section (by visit type). Step 3: Record observations and photographic evidence. Step 4: Complete Monitoring Visit Report (Template 4). Step 5: Share findings and agree action points. |  |  |  | X | X | X |  |  |  | X | X | X |  |  |  | X | X | X |  |  |  | X | X | X | Quarterly
Mid-term review contribution | IPTT extract + case examples | Exists - this workbook + Field Reporting Templates, Template 10 | All indicators | All activities | Step 1: Compile camp-level data from IPTT/Activity Tracker. Step 2: Self-assess progress against targets. Step 3: Compile illustrative case examples (Template 10). Step 4: Submit to PIB/SC ahead of the review. Step 5: Participate in KIIs/FGDs. | [9 empty] | X | X | X | [12 empty] | Month 12
Interim ECHO report data package | IPTT extract | Exists - this workbook | All indicators | All activities | Step 1: MEAL Officer compiles IPTT extract. Step 2: Draft narrative highlights. Step 3: Compile supporting evidence. Step 4: PIB validates. Step 5: Submit to SC. | [9 empty] | X | X | X | [12 empty] | Month 12
Community perception / KAP midline | Community Perception Survey | Needs development - no standalone instrument yet, to mirror the baseline tool once built | SO-I1 | INC-6 | Step 1: Repeat baseline sampling approach. Step 2: Administer same/comparable questionnaire. Step 3: Analyse and compare to baseline. Step 4: Share midline report with PIB. | [9 empty] | X | X | X | [12 empty] | Month 12
Final evaluation contribution | IPTT extract + KII/FGD participation | Exists - this workbook | All indicators | All activities | Step 1: Support SC/PIB-led evaluators with data access. Step 2: Participate in KIIs/FGDs. Step 3: Verify final indicator values. Step 4: Review draft evaluation findings. | [21 empty] | X | X | X | Month 22-24
Endline KAP survey | Baseline/KAP Survey Questionnaire (repeat) | Needs development - same instrument as baseline, once built | SO-I1 | INC-6 | Step 1: Repeat baseline/midline methodology. Step 2: Administer at project close. Step 3: Compare results against baseline and midline. Step 4: Share endline report. | [21 empty] | X | X | X | Month 22-23
Final ECHO report data package | IPTT extract | Exists - this workbook | All indicators | All activities | Step 1: Compile final IPTT extract for the full 24-month period. Step 2: Draft narrative. Step 3: Compile evidence. Step 4: PIB validates. Step 5: Submit to SC. | [21 empty] | X | X | X | Month 24
Sustainability / handover review | Workshop discussion (no fixed instrument) | Not applicable - facilitated discussion, no data-collection tool needed | SO-I1 | CLOSE | Step 1: Joint FIVDB-PIB-SC workshop scheduled. Step 2: Document lessons learned. Step 3: Agree handover/sustainability arrangements for CESGs, CBCPCs, MPCACs, adolescent clubs. Step 4: Circulate handover plan. | [21 empty] | X | X | X | Month 22-24

## 5b. Dashboard
Dashboard - Program, MEAL, Management & Finance Summary
Live summary pulled automatically from the IPTT (Sheet 7), Activity Tracker (Sheet 8), Budget Tracker (Sheet 13), Activity Data Log (Sheet 10) and Distribution Log (Sheet 11). Nothing on this sheet is entered manually - update the current reporting quarter on the IPTT sheet and everything below recalculates.
Current Reporting Quarter |  | Overall Budget Utilised |  | Avg. Physical Progress (all activities) |  | Total Data Log Entries (Sheets 10+11)
1 |  | 0% |  |  |  | 0
ACTION NEEDED - What requires attention right now
Consolidated from every section below, so decision-makers see what needs attention without reading the whole sheet.
Area |  |  | Alert |  |  |  | Count
Activities |  |  | Sub-activities marked 'Behind' (Sheet 8) |  |  |  | 0
Indicators |  |  | Indicators 'At Risk' (<70% of expected pace, Sheet 7) |  |  |  | 8
Budget |  |  | Lines at Overspend Risk (>110% utilised, Sheet 13c) |  |  |  | 0
CFM |  |  | Category 5/6 safeguarding/PSEA/fraud/security concerns logged |  |  |  | 0
Data Quality |  |  | Activity Data Log rows missing Event Date (breaks the auto-link) |  |  |  | 0
For Management - Implementation Status
RAG status distribution across all 75 sub-activities (Activity Tracker, Sheet 8), based on cumulative % Physical Progress vs plan.
On Track |  | Slightly Behind |  | Behind |  | No data yet
0 |  | 0 |  | 0 |  | 75
'Behind' activities need management attention - filter the Activity Tracker's RAG Status column (Sheet 8) directly to see which ones.
For MEAL - Indicator Achievement
% of LOP Target Achieved, averaged by Result (IPTT, Sheet 7). Indicator count classified: On Track (>=90% of expected pace), Watch (70-89%), At Risk (<70%).
Result |  | Avg % of LOP Target Achieved |  | Indicators On Track |  | Indicators Watch |  | Indicators At Risk
Result 1 (Education) |  | 0% |  | 0 |  | 0 |  | 8
Result 2 (Protection) |  |  |  | 0 |  | 0 |  | 0
Specific Objective |  |  |  | 0 |  | 0 |  | 0
Data collection volume (Sheets 10-11) and retention (Sheet 12) are tracked on their own sheets - see Activity Data Log, Distribution Log, and Dropout Tracker directly for full detail.
For Program Staff - This Quarter's Delivery
Focused on what's due this quarter and what needs catching up - planned vs actually logged, current reporting quarter only.
Metric |  |  |  |  | Value
Sub-activities with a target planned this quarter |  |  |  |  | 0
Sub-activities marked 'Behind' (need catch-up) |  |  |  |  | 0
Events/sessions logged this quarter (Sheet 10) |  |  |  |  | 0
Distributions logged this quarter (Sheet 11) |  |  |  |  | 0
Participants reached this quarter (Sheet 10, Total Participants) |  |  |  |  | 0
Recipients reached this quarter (Sheet 11, Total Recipients) |  |  |  |  | 0
For Finance - Budget Utilisation
From the Budget Tracker (Sheet 13). Utilisation = cumulative spend to date / approved budget, per line.
Metric |  |  | Value
Total Approved Budget (EUR) |  |  | 592371.4097
Total Spent to Date (EUR) |  |  | 0
Overall Utilisation % |  |  | 0%
Budget Lines - Underspend Risk |  |  | 13
Budget Lines - On Track |  |  | 0
Budget Lines - Overspend Risk |  |  | 0
Activity & Distribution - Male / Female Breakdown
Sums Host + FDMN across all logged rows (Activity Data Log, Sheet 10; Distribution Log, Sheet 11). Male = Boys <18 + Male 18+; Female = Girls <18 + Female 18+, per each sheet's own sex/age columns.
Source |  |  | Male |  | Female |  | Total
Activity Data Log (Sheet 10) |  |  | 0 |  | 0 |  | 0
Distribution Log (Sheet 11) |  |  | 0 |  | 0 |  | 0
TOTAL (Activity + Distribution) |  |  | 0 |  | 0 |  | 0
Indicator-by-Indicator Detail (all 17 indicators)
Every indicator individually, not just Result-level averages - pulled live from IPTT (Sheet 7). Status: On Track >=90% of expected pace, Watch 70-89%, At Risk <70%, No data yet if blank.
Code |  | Indicator |  |  |  | Unit | Cumulative Actual | LOP Target | % Achieved / Status
R1-I1 |  | Number of targeted girls and boys enrolled in non-formal education services |  |  |  | Number | 0 | 1224 | 0% - At Risk
R1-I2 |  | Number of learning spaces established or restored to minimum standards for safe learning |  |  |  | Number | 0 | 51 | 0% - At Risk
R1-I3 |  | Number of teachers provided with teaching aids/materials |  |  |  | Number | 0 | 68 | 0% - At Risk
R1-I4 |  | Number of girls and boys provided with learning materials |  |  |  | Number | 0 | 1224 | 0% - At Risk
R1-I5 |  | Number of teachers/education personnel showing increased knowledge and teaching skills to address children's learning needs |  |  |  | Number | 0 | 68 | 0% - At Risk
R1-I6 |  | Number of students, teachers and other education personnel provided with psycho-social support services |  |  |  | Number | 0 | 2516 | 0% - At Risk
R1-I7 |  | Number of teachers and other education personnel showing increased knowledge and skills to address the protection needs of girls and boys |  |  |  | Number | 0 | 68 | 0% - At Risk
R1-I8 |  | Number of girls and boys referred to specialised services (e.g. child protection, health, MHPSS) |  |  |  | Number | 0 | 122 | 0% - At Risk
R1-I9 |  | % educational facilities that are carrying out environmental and climate friendly activities day-to-day |  |  |  | % |  | 65% | No data yet
R2-I1 |  | (MANDATORY) % of children and caregivers whose urgent child protection needs/risks have been addressed through the case management process |  |  |  | % |  | 95% | No data yet
R2-I2 |  | % of children separated from or allegedly associated with armed groups and armed forces who benefit from appropriate care and services |  |  |  | % |  | 80% | No data yet
R2-I3 |  | Average % knowledge increase amongst participants on the protection subject in focus |  |  |  | % |  | 80% | No data yet
R2-I4 |  | (MANDATORY) % of persons who receive appropriate PSS reporting improved mental health and psychosocial well-being OR capacities to cope |  |  |  | % |  | 80% | No data yet
R2-I5 |  | % of caseworkers whose knowledge assessment score is at least 70% |  |  |  | % |  | 75% | No data yet
R2-Ref1 |  | (MANDATORY) Number of minimum standards for care for survivors achieved |  |  |  | Number | 0 | N/A | N/A - On Track
R2-Ref2 |  | Number of individuals benefiting from GBV response services (SC-led, R2-A2) |  |  |  | % | N/A | N/A | N/A - On Track
R2-Ref3 |  | % of GBV high-risk cases supervised (SC-led, R2-A2) |  |  |  | % | N/A | N/A | N/A - On Track
SO-I1 |  | % of beneficiaries reporting that humanitarian assistance is delivered in a safe, accessible, accountable and participatory manner |  |  |  | % |  | 85% | No data yet
SO-I2 |  | % targeted girls and boys who are retained in education at the end of the action |  |  |  | % |  | 90% | No data yet
Budget Line-by-Line Detail (all 14 lines)
Every budget line individually, pulled live from the Budget Tracker (Sheet 13c, Yearly & Total). Status: On Track 70-110% utilisation for time elapsed, Underspend Risk <70%, Overspend Risk >110%.
Budget Line |  |  | Approved (EUR) |  | Spent to Date (EUR) |  | % Utilised | Status
Identification, assessment and appropriate placement of out-of-school and dropout children, incl. disability screening (min. 3% target) |  |  | 0 |  | 0 |  | 0% | Underspend Risk
Education Service Delivery Support: learning materials, teaching-volunteer incentives, CBLF minimum package, solar/fire safety, maintenance, assistive devices |  |  | 0 |  | 0 |  | 0% | Underspend Risk
Gender-Appropriate Dignity Kits and MHM Support for adolescent girls |  |  | 0 |  | 0 |  | 0% | Underspend Risk
Strengthening Technical/Operational Capacities of Staff, Teaching Volunteers and Consortium Partners |  |  | 0 |  | 0 |  | 0% | Underspend Risk
Community Engagement (CESG), Caregiver Support and SEL Storybooks |  |  | 0 |  | 0 |  | 0% | Underspend Risk
Child protection case management services (identification, assessment, planning, referral, closure) |  |  | 0 |  | 0 |  | 0% | Underspend Risk
Establish and/or refurbish Multipurpose Centres + deliver MHPSS (shown as 0 in source - costs captured under R2A3 below) |  |  | 0 |  | 0 |  |  | Overspend Risk
PSS and protection-focused group interventions via MPCACs (incl. establishment, ISMF, Men & Boys Engagement, dignity/MHM kits) |  |  | 0 |  | 0 |  | 0% | Underspend Risk
Strengthening community-based protection mechanisms (CBCPC, PALS, risk mapping, IPT/puppet, DRR training) |  |  | 0 |  | 0 |  | 0% | Underspend Risk
Capacity-building for frontline staff/volunteers on CP-GBV integration |  |  | 0 |  | 0 |  | 0% | Underspend Risk
Human Resources (all local staff salaries - Project Coordinator, Technical Coordinator, officers, M&E, admin, etc.) |  |  | 0 |  | 0 |  | 0% | Underspend Risk
Running Costs (staff/support travel, office rent & utilities, communications) |  |  | 0 |  | 0 |  | 0% | Underspend Risk
Equipment (laptops, furniture and fixtures) |  |  | 0 |  | 0 |  | 0% | Underspend Risk
Indirect Costs (Local Partner ICR, max 2% of direct costs) |  |  | 0 |  | 0 |  | 0% | Underspend Risk
Camp-wise Summary
Total participants/recipients reached to date, by camp - summed live from the Activity Data Log (Sheet 10) and Distribution Log (Sheet 11) Camp columns.
Camp |  |  | Activity Data Log Participants |  |  | Distribution Log Recipients |  |  | Total
Camp 1W |  |  | 0 |  |  | 0 |  |  | 0
Camp 6 |  |  | 0 |  |  | 0 |  |  | 0
Camp 21 |  |  | 0 |  |  | 0 |  |  | 0
Camp 24 |  |  | 0 |  |  | 0 |  |  | 0
Complaints & Feedback (CFM) Summary
Pulled live from the CFM Log (Sheet 6). Category 5/6 = safeguarding/PSEA/fraud/security concerns - these need immediate management attention regardless of overall volume.
Metric |  |  |  |  | Value
Total feedback/complaints logged |  |  |  |  | 0
Unresolved (open) |  |  |  |  | 0
Category 5/6 (safeguarding/PSEA/fraud/security) - needs immediate attention |  |  |  |  | 0
Attendance Summary (age-segregated)
Pulled live from the Attendance Tracker's Compile section (Sheet 12b) - latest month with data, per camp and age segment.
Camp |  |  | Segment |  | Latest Attendance %
Camp 1W |  |  | Girls <18 |  | No data yet
Camp 1W |  |  | Boys <18 |  | No data yet
Camp 6 |  |  | Girls <18 |  | No data yet
Camp 6 |  |  | Boys <18 |  | No data yet
Camp 21 |  |  | Girls <18 |  | No data yet
Camp 21 |  |  | Boys <18 |  | No data yet
Camp 24 |  |  | Girls <18 |  | No data yet
Camp 24 |  |  | Boys <18 |  | No data yet
Dropout Summary (age-segregated)
Pulled live from the Dropout Tracker's Automatic Summary (Sheet 12, Section E) - cumulative dropout %, by category and age/sex segment.
Category |  |  | Segment |  | Dropout %
A. Learner Dropout |  |  | Girls <18
A. Learner Dropout |  |  | Boys <18
B. Staff Dropout / Turnover - by Designation |  |  | Female 18+
B. Staff Dropout / Turnover - by Designation |  |  | Male 18+
C. Volunteer Dropout / Turnover - by Designation & Rohingya/Host |  |  | Female 18+
C. Volunteer Dropout / Turnover - by Designation & Rohingya/Host |  |  | Male 18+
Chart - Activity RAG Status Distribution
On Track | Slightly Behind | Behind | No data yet
0 | 0 | 0 | 75
Chart - Dropout % by Category & Segment
A. Learner Dropout - Girls <18
A. Learner Dropout - Boys <18
B. Staff Dropout / Turnover - by Designation - Female 18+
B. Staff Dropout / Turnover - by Designation - Male 18+
C. Volunteer Dropout / Turnover - by Designation & Rohingya/Host - Female 18+
C. Volunteer Dropout / Turnover - by Designation & Rohingya/Host - Male 18+

## 6. CFM Log Template
6. Complaints & Feedback Mechanism (CFM) - Individual Feedback Database
Adapted from Save the Children's MPCA Feedback Database Template for FIVDB/SURAKKHA. Records individual pieces of feedback and concerns (hotline, feedback box, one-to-one conversations, face-to-face). For group/collective feedback (community meetings, FGDs, informal debriefs), use Sheet 6b (Collective Feedback) instead. Do NOT record names or descriptive detail for Category 5/6 sensitive concerns (safeguarding, PSEA, fraud, security) - record only the reference number of the formal report filed with the PIB/FIVDB Safeguarding Focal Point. Category 5/6 concerns must be escalated within 24-48 hours per the Safeguarding Framework.
Information about when and by whom the feedback/concern was received or documented | [5 empty] | Information about the person who shared feedback/concern and the feedback/concern itself (OPTIONAL - the person may decline to give this information) | [17 empty] | Information about referring, actioning and closing the feedback loop
Unique Number | Date Received (dd/mm/yy) | Name of Staff Who Received/Documented | Position of Staff Member | Contact Details of Staff Member | Channel | Name of Person Sharing Feedback (if known) | Type of Person | Age (if known) | Age Group (auto) | Gender | Vulnerability | Phone Number (if provided) | Camp | Block (if known) | Address (if applicable) | Theme/Sector | Activity/Project (Activity Code if known) | Description of Feedback (NOT for Category 5/6 - cite report ref# instead) | Category | Sub-Category (Category 5/6 only) | Date of Referral (dd/mm/yy) | Name of Staff Referred To | Position of Staff Referred To | Contact of Staff Referred To | Actions Undertaken to Resolve (NOT for Category 5/6) | Status | Date Resolved (dd/mm/yy) | Days Taken to Resolve (auto) | Feedback Loop Closed? (communicated back to person) | Additional Comments
1
2
3
4
5
6
7
8
9
10
11
12
13
14
15
16
17
18
19
20
21
22
23
24
25
26
27
28
29
30
31
32
33
34
35
36
37
38
39
40

## 6b. Collective Feedback
6b. Complaints & Feedback Mechanism (CFM) - Collective Feedback
Records feedback gathered from a GROUP of adults or children (e.g. community meetings, FGDs) or informal feedback shared by front-line staff (e.g. during a de-brief session) - as distinct from Sheet 6's individual feedback log. This allows FIVDB/PIB to analyse both formal/individual and informal/collective feedback together.
Unique Number | Date (dd/mm/yy) | Name of Staff Who Documented | Position | Method (community meeting/FGD/debrief) | Camp | Group Composition (e.g. CESG, CBCPC, parents) | No. of Participants (M/F/Total) | Theme/Sector | Summary of Feedback/Concerns Raised | Category | Actions Undertaken | Status | Date Resolved (dd/mm/yy) | Feedback Loop Closed? (communicated back to group) | Additional Comments
1
2
3
4
5
6
7
8
9
10
11
12
13
14
15
16
17
18
19
20
21
22
23
24
25
26
27
28
29
30
31
32
33
34
35
36
37
38
39
40

## 6c. Target Breakdown
6c. Target Breakdown - FIVDB Facility & Beneficiary Targets
Figures cross-validated against the Narrative Proposal (18-Mar-26), the FIVDB Detailed Budget, and Annex 3 (Locations & Integration Mapping). Updated from earlier Annex-2-derived estimates where the Narrative/Budget give more precise, confirmed numbers - see the Comments column and the note at the end of each section. Education and Protection beneficiary totals are counted as unique within each sector separately; the same person may appear in both sectors, so the combined FIVDB total at the bottom is not a de-duplicated headcount across sectors.
A. Education (Result 1) Targets
A.1 Facility / structure targets
Structure | Camp 1W | Camp 6 | Camp 21 | Camp 24 | Total | Reference
Community-Based Learning Facilities (CBLFs) - girls' | 10 | 10 | 7 | 7 | 34 | Narrative Proposal; camp split computed proportionally (2:1 girls:boys ratio applied to Annex 3 camp totals)
Community-Based Learning Facilities (CBLFs) - boys' | 6 | 5 | 3 | 3 | 17 | Narrative Proposal; camp split computed proportionally (2:1 girls:boys ratio applied to Annex 3 camp totals)
CBLFs total (by camp, per Annex 3) | 16 | 15 | 10 | 10 | 51 | Annex 3, PLAN sheet, rows 3-6
Community Education Support Groups (CESGs, ~1 per 2 CBLFs) | 8 | 8 | 5 | 5 | ~26 groups | FIVDB Detailed Budget, R1A5; camp split = CBLFs per camp / 2, rounded
CORRECTED: FIVDB's 51 facilities are all CBLFs (34 girls' + 17 boys'), per the Narrative Proposal. GoLFs (Girls-Only Learning Facilities, secondary level) belong to SC, not FIVDB - the earlier 'GoLF included within the 51' assumption was incorrect and has been removed. Camp-wise girls'/boys' split is NOT independently specified in the Narrative Proposal or Annex 3 - it is computed by applying the confirmed overall 2:1 girls:boys ratio (34:17) to each camp's known total facility count (16/15/10/10), rounded to whole facilities; validate the actual per-camp split with PIB once site allocation is finalised.
A.2 Beneficiary targets - camp-wise (life of project)
Category | Target (Total) | Total Days/Sessions (indicative) | Of whom with disability | Reference / Basis
Learners (11-18 years) - Camp 1W | 384 | 160 | 37 (3% target) | 384 CBLFs 16 x 24 learners/facility; 66.7% female per facility-ratio
Learners (11-18 years) - Camp 6 | 360 | 150 | 34 (3% target) | 15 CBLFs x 24 learners/facility
Learners (11-18 years) - Camp 21 | 240 | 100 | 23 (3% target) | 10 CBLFs x 24 learners/facility
Learners (11-18 years) - Camp 24 | 240 | 100 | 23 (3% target) | 10 CBLFs x 24 learners/facility
Learners (11-18 years) - TOTAL | 1,224 | - | 37 (3% target) | 51 CBLFs x 24 learners/facility, 2 shifts; matches Narrative Proposal & FIVDB Detailed Budget row 65
CESG members (7-8 per group, ~26 groups) | 204 | - | - | FIVDB Detailed Budget, R1A5; camp split not independently specified
Parents / caregivers (1 per enrolled child) | 1,224 | - | - | FIVDB Detailed Budget, R1A5; follows learner enrolment 1:1, so mirrors the camp split above
Teachers / facilitators (refugee + host) | 68 | - | - | Annex 2, EiE_PIB tab; 51 refugee + 17 host, camp split not independently specified
Learners are broken down camp-wise using the direct, defensible relationship confirmed in the Narrative Proposal: each CBLF serves exactly 24 learners (2 shifts) - so Learners per camp = CBLFs per camp (Section A.1) x 24. This gives clean, source-derived numbers (384/360/240/240), not an estimate. The 'Total Days/Sessions' column for camp-level learner rows shows an indicative female sub-count (applying the same 66.7%/33.3% facility-based sex ratio used in A.1) - not an independently confirmed sex split by camp; validate with PIB. CESG members, Parents/caregivers and Teachers do NOT have an independently confirmed camp-wise split in either the Narrative Proposal or FIVDB Detailed Budget - showing the Total only for these rows is more honest than fabricating a camp breakdown; a camp-wise split can be computed once FIVDB confirms actual CESG/teacher deployment per camp.
B. Child Protection (Result 2) Targets
B.1 Facility / structure targets
Structure | Camp 1W | Camp 6 | Camp 21 | Camp 24 | Total | Reference
MPCAC - newly established | 1 | 1 | 1 | 1 | 4 | Narrative Proposal; Detailed Budget R2A3
MPCAC - refurbished | 1 | 0 | 0 | 1 | 2 | Narrative Proposal; Detailed Budget R2A3
MPCAC total facility actions | 2 | 1 | 1 | 2 | 6 | Narrative Proposal; Detailed Budget R2A3
Case Management Offices | 1 | 1 | 1 | 1 | 4 | FIVDB Detailed Budget, R2A1
Community-Based Child Protection Committees (CBCPCs, 2 per camp x 4 camps) | - | - | - | - | 8 | FIVDB Detailed Budget, R2A4
CONFIRMED: MPCAC (4 new + 2 refurbished = 6) matches exactly between the Narrative Proposal and the Detailed Budget. CBCPCs updated to 8 committees (2 per camp x 4 camps, 17 members each = 136 total members) per the Detailed Budget - more precise than the earlier 'indicative 4' estimate.
B.2 Beneficiary targets (life of project)
Category | Female | Male | Total | Of whom with disability | Reference
Children in case management (R2A1) | 160 | 160 | 320 | TBD | FIVDB Detailed Budget, R2A1
Adolescents in PALS sessions (R2A4) | 2,160 | 2,160 | 4,320 | TBD | FIVDB Detailed Budget, R2A4
Parents/Caregivers in PALS sessions (R2A4) | TBD | TBD | 4,320 | - | FIVDB Detailed Budget, R2A4
CBCPC members (2 x 4 camps x 17) | TBD | TBD | 136 | - | FIVDB Detailed Budget, R2A4
Persons receiving Dignity/MHM kits (CP side, R2A3) | 1,814 | - | 1,814 | - | FIVDB Detailed Budget, R2A3
Community Leaders & Volunteers - DRR/Climate training (R2A4) | TBD | TBD | 240 | - | FIVDB Detailed Budget, R2A4
Case management volunteers (2 per camp x 4 camps) | TBD | TBD | 8 | - | FIVDB Detailed Budget, R2A1
CP total (FIVDB, indicative, categories overlap) | - | - | See rows above | -
UPDATED from the FIVDB Detailed Budget: case management children 314->320; PALS adolescents/caregivers 4,234->4,320; CBCPC members 132->136. Dignity/MHM kits (CP side, 1,814 persons) and the DRR/Climate training cohort (240) are new rows not previously captured. Sex splits marked 'TBD' are not specified in the Budget/Narrative at this level of detail - the CP unique-total row from the previous version has been removed because these categories overlap (e.g. a PALS adolescent may also be a case-management child or CBCPC-linked); summing them would double-count. Validate all figures and true unique headcounts with PIB.
C. Notes on Combined FIVDB Reach
A single combined FIVDB headcount (Education + Protection) is not shown here because several Protection categories (PALS adolescents, CBCPC members, case-management children) overlap with each other and potentially with Education learners, and the Budget/Narrative do not provide a de-duplicated total. For consortium-level unique-beneficiary reporting, defer to PIB's consolidated Beneficiary Table rather than summing the rows above.

## 6d. Key Milestones
6d. Key Milestones - FIVDB (SURAKKHA)
Every FIVDB sub-activity with its expected completion window, derived live from the same planned-quarter data used in the Activity Tracker (Sheet 8) - Q1 = Jun-Aug 2026 through Q8 = Mar-May 2028.
Activity Code | Milestone | Expected Month/Year of Completion | Responsible Person
Result 1: Adolescent girls and boys have sustained access to inclusive, quality learning opportunities in safe, protective, community-based learning facilities.
R1A1.1 | Conduct household survey through community volunteers to identify out-of-school and dropout children. | Jun 2026 - May 2027 | Education Officer
R1A1.2 | Conduct technical/disability assessment and screening of identified children (minimum 3% disability target), referring complex cases to Humanity & Inclusion (HI) under FIVDB's MoU. | Jun 2026 - May 2027 | Education Officer
R1A1.3 | Print placement/assessment and disability-screening tools. | Jun 2026 - May 2027 | Education Officer
R1A2.1 | Provide monthly incentives to host-community teacher volunteers. | Jun 2026 - May 2028 | Education Officer
R1A2.2 | Provide monthly incentives to refugee-community teacher volunteers. | Jun 2026 - May 2028 | Education Officer
R1A2.3 | Distribute scholastic material kits (exercise books, ALP books, drawing books, pens, pencils, water bottle, erasers, sharpeners) to enrolled children, 2 shifts per CBLF. | Jun 2026 - May 2027 | Education Officer
R1A2.4 | Distribute one school bag per enrolled child (one-time distribution). | Jun 2026 - Aug 2026 | Education Officer
R1A2.5 | Provide assistive devices and reasonable accommodation for children with disabilities (device cost only; assessment carried out by HI). | Jun 2026 - May 2027 | Education Officer
R1A2.6 | Provide the CBLF minimum package (floor mats, whiteboards, boxes, stationery, cleaning materials). | Jun 2026 - May 2027 | Education Officer
R1A2.7 | Install solar panels, lighting and fire extinguishers at all CBLFs. | Jun 2026 - May 2027 | Education Officer
R1A2.8 | Cover ongoing CBLF maintenance costs. | Jun 2026 - May 2028 | Education Officer
R1A2.9 | Produce and display IEC materials (safeguarding, child protection, PSHEA posters) at all CBLFs. | Jun 2026 - May 2027 | Education Officer
R1A2.10 | Provide teacher kits (diary, pens, water bottle, teacher's guide). | Jun 2026 - May 2027 | Education Officer
R1A2.11 | Provide teacher kits (bag and umbrella), annual distribution. | Jun 2026 - May 2028 | Education Officer
R1A3.1 | Distribute standard MHM kits (reusable pads, underwear, laundry soap) to adolescent girls. | Jun 2026 - May 2027 | Education Officer
R1A4.1 | Deliver the 5-day basic training for teaching volunteers (once every 2 years, TiCC-aligned, CBLF-based). | Jun 2026 - May 2027 | Education Officer
R1A4.2 | Deliver the 6-day subject-based (ALP curriculum) training for teaching volunteers. | Jun 2026 - May 2027 | Education Officer
R1A4.3 | Deliver quarterly refresher training for project personnel and teaching volunteers within the CBLF. | Jun 2026 - May 2028 | Education Officer
R1A4.4 | Deliver cascading training for teachers on PSS, gender, SRHR, CAAFAG and referral mechanisms. | Jun 2026 - May 2027 | Education Officer
R1A4.5 | Deliver the 2-day cascade training on Protective Education Services for teaching volunteers. | Jun 2026 - May 2027 | Education Officer
R1A4.6 | Deliver ToT on Gender-Responsive Pedagogy for Inclusive and Gender-Responsive Learning (staff). | Jun 2026 - May 2027 | Education Officer
R1A4.7 | Cascade the Gender-Responsive Pedagogy training from staff ToT to all teaching volunteers. | Jun 2026 - May 2027 | Education Officer
R1A4.8 | Deliver ToT on Empowerment: Decision-Making and Resilience for Rohingya Women and Adolescent Girls (staff). | Jun 2026 - May 2027 | Education Officer
R1A4.9 | Cascade the Empowerment/Decision-Making/Resilience session from staff ToT to teaching volunteers. | Jun 2026 - May 2027 | Education Officer
R1A4.10 | Hold quarterly Male Allyship and Community Leadership Circles for Gender Justice (camp-based, incl. SC). | Jun 2026 - May 2028 | Technical Coordinator–Protection
R1A4.11 | Deliver ToT on Gender Equality in Education for field staff, facilitators and consortium partners. | Jun 2026 - May 2027 | Education Officer
R1A4.12 | Cascade the Gender Equality in Education training from ToT to field staff/facilitators. | Jun 2026 - May 2027 | Education Officer
R1A4.13 | Facilitate Adolescent Girls' Safe Circles for Leadership and Protection (per centre, peer group). | Jun 2026 - May 2028 | Education Officer
R1A4.14 | Hold monthly project progress/coordination meetings. | Jun 2026 - May 2028 | Project Manager
R1A5.1 | Provide SEL storybooks to CBLFs to ensure a joyful learning environment. | Jun 2026 - May 2027 | Education Officer
R1A5.2 | Hold bi-monthly CESG meetings (7-8 members per CESG, 1 CESG per 2 CBLFs). | Jun 2026 - May 2028 | Education Officer
R1A5.3 | Hold bi-monthly parent/caregiver engagement meetings (1 parent per enrolled child). | Jun 2026 - May 2028 | Education Officer
Result 2: Strengthened, inclusive child protection services prevent and respond to protection risks of girls, boys, women and men affected by the Rohingya crisis.
R2A1.1 | Identify and enhance the capacity of alternative-care family members (foster and kinship) for unaccompanied/separated children (UASC). | Jun 2026 - May 2027 | Technical Coordinator–Protection
R2A1.2 | Provide case-management need-based and emergency support (NFIs) to children/families in active cases. | Jun 2026 - May 2028 | Technical Coordinator–Protection
R2A1.3 | Maintain functioning Case Management Offices (1 per camp). | Jun 2026 - May 2028 | Technical Coordinator–Protection
R2A1.4 | Deliver case management services per the CPMS 7-step process (non-budgetary - covered by CM Officer/volunteer time). | Jun 2026 - May 2028 | Case Management Officer
R2A1.5 | Train para-social workers, volunteers and facilitators on referral pathways. | Jun 2026 - May 2027 | Technical Coordinator–Protection
R2A1.6 | Provide monthly incentives to case-management volunteers (2 per camp, all refugees) for identification and referral. | Jun 2026 - May 2027 | Technical Coordinator–Protection
R2A1.7 | Provide support-material kits (case-worker kits) for case-management service providers. | Jun 2026 - May 2027 | Technical Coordinator–Protection
R2A3.1 | Construct new MPCACs and refurbish existing MPCACs, including running costs. | Jun 2026 - May 2027 | Technical Coordinator–Protection
R2A3.2 | Roll out 'I Support My Friend' (ISMF) at community level, including inception meeting and adolescent training. | Jun 2026 - May 2027 | Technical Coordinator–Protection
R2A3.3 | Deploy MPCAC facilitators (refugee volunteers, host-community volunteers, security guards) to run PSS/awareness sessions. | Jun 2026 - May 2028 | Technical Coordinator–Protection
R2A3.4 | Orient and engage proactive Men and Boys in GBV prevention and response (bi-weekly sessions). | Jun 2026 - May 2028 | Technical Coordinator–Protection
R2A3.5 | Deliver community-led activities on CP and GBV issues (day/event observation). | Jun 2026 - May 2028 | Technical Coordinator–Protection
R2A3.6 | Provide Dignity Kits and Menstrual and Hygiene Management (MHM) kit support to adolescent girls (CP side). | Jun 2026 - May 2027 | Technical Coordinator–Protection
R2A4.1 | Deliver DRR & Climate Resilience training for community leaders and volunteers. | Jun 2026 - May 2027 | Technical Coordinator–Protection
R2A4.2 | Deliver PALS sessions for parents and adolescents (10-14 sessions per group). | Jun 2026 - May 2028 | Technical Coordinator–Protection
R2A4.3 | Form/reform CBCPCs and hold monthly/bi-monthly meetings (2 CBCPCs per camp, 17 members each). | Jun 2026 - May 2028 | Technical Coordinator–Protection
R2A4.4 | Deliver 2-day CBCPC member training, twice yearly (2 CBCPCs/camp x 17 members x 4 camps). | Jun 2026 - May 2028 | Technical Coordinator–Protection
R2A4.5 | Conduct child-protection risk mapping and develop community-led prevention/response/referral plans. | Jun 2026 - May 2027 | Technical Coordinator–Protection
R2A4.6 | Deliver Art for Awareness - Interactive Popular Theatre (IPT) and puppet shows for CP & GBV behaviour change. | Jun 2026 - May 2028 | Technical Coordinator–Protection
R2A5.1 | Deliver capacity-enhancing training for other-sector staff (health, education, nutrition, WASH) on CP integration and case-referral systems. | Jun 2026 - May 2027 | Technical Coordinator–Protection
R2A5.2 | Hold quarterly coordination meetings with camp service providers (CiC and relevant stakeholders). | Jun 2026 - May 2028 | Project Manager
R2A5.3 | Enhance the capacity of implementing partners on CP and operations. | Jun 2026 - May 2027 | Technical Coordinator–Protection
R2A5.4 | Conduct quarterly joint field-monitoring visits with government officials (CiC office and other actors). | Jun 2026 - May 2028 | Project Manager
R2A5.5 | Hold a project inception workshop with relevant stakeholders at camp level. | Jun 2026 - Aug 2026 | Project Manager

## 6e. Logframe
6e. Logframe - FIVDB (SURAKKHA)
Matches the structure of Annex 1 (Logframe) submitted separately to PIB - Level / Ref / Performance Indicator / Target / Agency / Agency Target / Indicator Definition / Comments. Ref codes here (e.g. R1.1) are a THIRD numbering system, distinct from the IPTT's indicator codes (R1-I1) and the Activity Tracker's budget codes (R1A1) - see the Cover sheet FAQ for how the three relate.
Level | Ref | Performance Indicator | Target | Agency | Agency Target | Indicator Definition | Comments / Clarifications
Outcome statement | SO | Girls and boys, including the most vulnerable and children with disabilities, have safe and equitable access to quality, inclusive non-formal education and child protection services.
Outcome indicator | SO.1 | % of beneficiaries reporting that humanitarian assistance is delivered in a safe, accessible, accountable and participatory manner | 85% | FIVDB | 85% | Officially approved Logframe (Annex I) target.
Outcome indicator | SO.2 | % targeted girls and boys who are retained in education at the end of the action | 90% | FIVDB | 90% | Denominator = FIVDB's 1,224 enrolled learners.
Output statement | R1 | Adolescent girls and boys have sustained access to inclusive, quality learning opportunities in safe, protective, community-based learning facilities.
Output indicator | R1.1 | Number of targeted girls and boys enrolled in non-formal education services | 1224 | FIVDB | 1224 |  | 816 girls + 408 boys across 51 CBLFs.
Output indicator | R1.2 | Number of learning spaces established or restored to minimum standards for safe learning | 51 | FIVDB | 51 |  | 34 girls' + 17 boys' CBLFs across Camps 1W, 6, 21, 24.
Output indicator | R1.3 | Number of teachers provided with teaching aids/materials | 68 | FIVDB | 68 |  | 51 refugee + 17 host.
Output indicator | R1.4 | Number of girls and boys provided with learning materials | 1224 | FIVDB | 1224 |  | Same 1,224 learners as R1.1.
Output indicator | R1.5 | Number of teachers/education personnel showing increased knowledge and teaching skills | 68 | FIVDB | 68 |  | 100% of FIVDB's own teachers targeted.
Output indicator | R1.6 | Number of students, teachers and other education personnel provided with psycho-social support services | 2516 | FIVDB | 2516 |  | 68 teachers + 1,224 learners + 1,224 parents/caregivers.
Output indicator | R1.7 | Number of teachers and other education personnel showing increased knowledge and skills to address protection needs | 68 | FIVDB | 68 |  | FIVDB's own teaching cohort.
Output indicator | R1.8 | Number of girls and boys referred to specialised services | 122 | FIVDB | 122 |  | ~10% of 1,224 enrolled learners (projection).
Output indicator | R1.9 | % educational facilities carrying out environmental and climate friendly activities day-to-day | 65% | FIVDB | 65% |  | ~33 of FIVDB's 51 CBLFs.
Output statement | R2 | Strengthened, inclusive child protection services prevent and respond to protection risks of girls, boys, women and men affected by the Rohingya crisis (FIVDB: Activities 1, 3, 4, 5).
Output indicator | R2.1 | (MANDATORY) % of children and caregivers whose urgent child protection needs/risks have been addressed | 95% | FIVDB | 95% |  | 320 children in case management, 4 Case Management Offices.
Output indicator | R2.2 | % of CAAFAG who benefit from appropriate care and services | 80% | FIVDB | 80% |  | Within FIVDB's caseload.
Output indicator | R2.3 | Average % knowledge increase amongst participants on the protection subject in focus | 80% | FIVDB | 80% |  | Pre-/post-test knowledge gain.
Output indicator | R2.4 | (MANDATORY) % of persons who receive appropriate PSS reporting improved wellbeing | 80% | FIVDB | 80% |  | 6 MPCACs (4 new + 2 refurbished), PALS reaching 4,320 + 4,320.
Output indicator | R2.5 | % of caseworkers whose knowledge assessment score is at least 70% | 75% | FIVDB | 75% |  | Annual Case Worker Capacity Assessment.
Output indicator (reference) | R2.Ref | (MANDATORY) Number of minimum standards for care for survivors achieved | 12 | FIVDB/PLAN | 12 | SC-led overall (Activity 2); FIVDB's role is referral-only. PLAN's own sub-target is 12 (of 31 reviewed); SC's separate target is 16.

## 7. IPTT
7. Indicator Performance Tracking Table (IPTT) - FIVDB
>>> SET CURRENT REPORTING QUARTER HERE (1-8): | 1 | (everything in this workbook depends on this cell)
Consortium baselines/targets from the Logframe (Annex I). FIVDB's LOP Target = indicative FIVDB contribution derived from Annex 2 (EiE_PIB / CP_PIB_V2). 'Linked Activity/ies' shows the primary (first-listed) Activity Tracker SUB-ACTIVITY code (Sheet 8) whose own Linked Indicator(s) field matches this indicator - auto-computed, single source of truth. Where more than one sub-activity feeds the same indicator, the rest are listed in 'Additional Linked Sub-Activities' immediately to its right, rather than crammed into one cell. TARGET columns are auto-calculated from LOP Target using the phasing assumptions below (blue cells = editable inputs). ACTUAL columns: for 'Number'-unit indicators, ACTUAL is now AUTOMATIC - cumulative sum, by quarter, of every Activity Tracker (Sheet 8) sub-activity ACTUAL total whose Linked Indicator(s) matches this indicator's code (light-blue cells; no manual entry, recalculates as Sheets 10-11 are populated). For '%'-unit indicators, FIVDB enters cumulative-to-date achievement directly into the quarter cell (yellow cells; survey/assessment-based - a percentage cannot be derived from headcount sums). Validate all figures with PIB at inception.
HOW TO READ THIS SHEET - answers to the most common PIB review questions: (1) LOP Target (column O) is always FIVDB's OWN contribution only - never the wider consortium (SC+FIVDB/PLAN) total; the consortium total and the full breakdown behind every composite figure (e.g. 'X teachers + Y learners + Z parents') are always spelled out in the Comments column so every number is traceable, not just asserted. (2) Several '%'-unit LOP Targets across Result 2 look similar (75-95%) because they are the officially approved figures from the same Logframe (Annex I) table, reflecting comparable prior-phase (ECHO HIP 2023) performance baselines across CP/PSS/GBV service lines - not copied from one row to another; each has its own distinct source paragraph in Comments. (3) Result 2 has 5 Activities; FIVDB delivers Activities 1, 3, 4, 5. Activity 2 (adult 18+ GBV case management) is SC-led and explicitly defined in the Narrative Proposal ('Result 2 - Activity 2'), with FIVDB's role limited to referral - this is why it has no FIVDB budget code (R2A2) anywhere in the Activity Tracker. (4) 'Reference' indicator rows (R2-Ref1-3) are led by another consortium agency, shown here for traceability only - FIVDB is not directly accountable for the full consortium figure on those rows. (5) Any Annex number cited in a Comments cell (e.g. Annex 27) refers to an annex of the consortium's DG ECHO Single Form proposal, held by PIB/SC, not a standalone FIVDB document.
ONGOING-delivery phasing (training, referrals, PSS, case management - accrues continuously) - used only for Status calculation below, not shown per-indicator: | [12 empty] | 5% | 15% | 30% | 45% | 62% | 78% | 92% | 100%
ENROLMENT/ESTABLISHMENT phasing (learners enrolled, facilities/teachers set up - front-loaded, then RETAINED not re-enrolled): | [12 empty] | 45% | 85% | 97% | 100% | 100% | 100% | 100% | 100%
RATIONALE for TWO phasing curves, not one: enrolment/establishment-type indicators (learners enrolled, facilities/teachers/kits set up) do NOT grow every quarter - once a learner is enrolled or a CBLF is established, they don't get 're-enrolled' or 're-established' again next quarter; almost all of the growth happens once, early (CBLF opening, initial enrolment drive), then the LOP target is essentially reached and held (minus/plus small dropout replacement, tracked separately in the Dropout Tracker, Sheet 12). Ongoing-delivery indicators (training sessions, referrals, PSS, case management, knowledge assessments) behave differently - they genuinely accrue new instances every quarter as activities continue - so they follow the original S-curve instead. R1-I1, R1-I2, R1-I3 and R1-I4 (enrolment, facilities, teacher/learner materials) use the ENROLMENT/ESTABLISHMENT curve; every other Number-unit indicator uses the ONGOING-delivery curve - edit either blue/orange row directly if FIVDB's actual pattern differs; the Status column recalculates automatically from whichever row it's assigned to.
Result | Indicator Code | Linked Activity/ies (primary sub-activity) | Additional Linked Sub-Activities | Indicator | Reference Source (indicator origin) | Indicator Definition | Measurement Methodology | Disaggregation Required | Baseline | Target Population / Denominator (indicative) | LOP Target (FIVDB) | Unit | ACTUAL (cumulative, by quarter - auto-linked for Number indicators; FIVDB to complete for % indicators) | [7 empty] | % of LOP Target Achieved | Status | Means of Verification | Source and Method of Data Collection | Verification / QA Step | Frequency | Responsible | Support Type (how they support) | Risks / Assumptions | How to Articulate in Narrative Report | Comments | CUMULATIVE SEX/AGE DISAGGREGATION (auto, from Sheets 10-11)
[13 empty] | Q1 | Q2 | Q3 | Q4 | Q5 | Q6 | Q7 | Q8 | [11 empty] | Girls <18 | Boys <18 | Women 18+ | Men 18+
RESULT 1 - EDUCATION IN EMERGENCIES (FIVDB Activities 1-7)
Result 1 | R1-I1 | R1A1.1 | R1A1.2, R1A1.3 | Number of targeted girls and boys enrolled in non-formal education services | Logframe (Annex I), Result 1 indicators - code R1-I1 | Enrolled = registered to participate in non-formal education. NFE is usually not accredited by the national education system (e.g. catch-up programmes, homework support, basic literacy/numeracy, language support, remedial education). For learners enrolled in both formal and complementary NFE services, a clear breakdown of multi-service enrolment must be provided. Disaggregate by sex, NFE type/level of education (primary, lower secondary, upper secondary) and disability. | Enrolment registers maintained at CBLF level plus daily attendance sheets completed by teaching volunteers, recorded at facility level and compiled regularly by CBLF facilitators. | Sex, level of education, disability | 0 | - | 1224 | Number | ACTUAL (cumulative, by quarter - auto-linked for Number indicators; FIVDB to complete for % indicators) Q1: 0 | 0% | Behind | CBLF enrolment registers, daily attendance sheets (compiled quarterly by MEAL focal points) | Source: enrolment registers maintained at CBLF level, daily attendance sheets completed by teaching volunteers. Method: recorded at facility level, compiled regularly by CBLF facilitators. Frequency: attendance recorded daily; enrolment and quality-monitoring data compiled, validated and reported quarterly by MEAL focal points. | Monthly PIB spot-check (min. 10% sample) of enrolment registers against attendance records; quarterly FIVDB-PIB reconciliation. | Attendance recorded daily; enrolment and quality-monitoring data compiled, validated and reported quarterly by MEAL focal points | MEAL Officer | Data consolidation, quality assurance & reporting | New arrivals/relocation may disrupt enrolment tracking; mitigate via regular registry updates and coordination with camp CiC. | During the reporting period (cumulative through Q1), FIVDB reported 0 against the indicator 'Number of targeted girls and boys enrolled in non-formal education services' - 0% of the 1,224 life-of-project target. Disaggregated: 0 girls (<18), 0 boys (<18), 0 women (18+), 0 men (18+). | Narrative Proposal, Result 1 Indicator 1: consortium Baseline 1,340 (SC's continuing learners from ECHO HIP 2023) / consortium Target 4,067 (SC 2,843: 2,293 girls, 550 boys; PLAN/FIVDB 1,224: 816 girls, 408 boys, >=3% disability). FIVDB's own baseline is 0 (out-of-school children, all new enrolment). FIVDB target 1,224 confirmed twice: Narrative Proposal AND FIVDB Detailed Budget (kits line item). CLARIFICATION: 1,224 = 816 girls + 408 boys, across 51 CBLFs (34 girls' + 17 boys') x 24 learners/facility x 2 shifts. Age range 11-18 (Narrative Proposal: 'children and adolescents aged 11-18... 51 CBLFs run by PLAN'). Minimum 3% (~37) with disability. Consortium total 4,067 = SC's 2,843 + FIVDB's 1,224 - FIVDB is not accountable for SC's share. | 0 | 0 | 0 | 0
Result 1 | R1-I2 | R1A2.6 | R1A2.7, R1A2.8, INC-5, GEN-2 | Number of learning spaces established or restored to minimum standards for safe learning | Logframe (Annex I), Result 1 indicators - code R1-I2 | Learning spaces reported as classroom units (or equivalent) where possible. Minimum standards for safe learning follow the Education Sector Standard guideline (INEE-aligned), covering DRR, safe routes to/from school, minimum accessibility/reasonable accommodation, GBV risk management, WASH standards and student perceptions of safety, with design/implementation gender- and age-responsive in line with the EU Gender-Age Marker. | Site completion reports, infrastructure assessment and CBLF monitoring checklists, and teaching-volunteer/mentor supervision records, verified against the Education Sector Standard guideline (Annex - Education Sector's Standards). | N/A (facility-level indicator) | 0 | - | 51 | Number | ACTUAL (cumulative, by quarter - auto-linked for Number indicators; FIVDB to complete for % indicators) Q1: 0 | 0% | Behind | Site completion reports, infrastructure assessment, CBLF monitoring checklists, photographic documentation | Source: site completion reports, infrastructure assessment, CBLF monitoring checklists, teaching-volunteer/mentor supervision records. Method: verified against the Education Sector Standard guideline (Annex - Education Sector's Standards). Frequency: regular site visits and monitoring visits by programme and MEAL teams; cross-checked through document review and field validation. | Quarterly joint FIVDB-PIB site visit against the Facility Monitoring Checklist; photographic evidence retained. | Regular site visits and monitoring visits by programme and MEAL teams; cross-checked through document review and field validation | Education Officer | Field data collection & first-line reporting | Delays in rehab/construction approvals or procurement of materials (solar, fencing) may push completion into later quarters. | During the reporting period (cumulative through Q1), FIVDB reported 0 against the indicator 'Number of learning spaces established or restored to minimum standards for safe learning' - 0% of the 51 life-of-project target. Disaggregated: 0 girls (<18), 0 boys (<18), 0 women (18+), 0 men (18+). | Narrative Proposal, Result 1 Indicator 2: consortium Baseline 66 (SC's existing CBLFs maintained since ECHO HIP 2023) / consortium Target 121 (SC 70: 62 CBLFs+5 GoLFs+1 girls club+1 boys club+1 MPC; PLAN/FIVDB 51 new CBLFs). FIVDB's own baseline is 0 (all 51 CBLFs newly established under this action). CLARIFICATION: 51 = 16 (Camp 1W) + 15 (Camp 6) + 10 (Camp 21) + 10 (Camp 24), per Annex 3 site mapping. All 51 are NEW facilities (FIVDB's own baseline = 0); SC's 70 are separately maintained/continuing facilities from a prior phase, not part of FIVDB's count. | 0 | 0 | 0 | 0
Result 1 | R1-I3 | R1A2.1 | R1A2.2, R1A2.10, R1A2.11 | Number of teachers provided with teaching aids/materials | Logframe (Annex I), Result 1 indicators - code R1-I3 | Minimum package = blackboard (or equivalent), textbooks/teaching guides and stationery, including adaptations for teachers/learners with disabilities and materials tailored to identified language needs. Materials may be supplied directly or via logistical/technical/advocacy support to education authorities. Disaggregate by sex, NFE type/level of education and disability. | Distribution lists, signed receipt forms, muster rolls, attendance sheets and inventory records maintained at partner and learning-facility level, documenting provision of teaching aids/materials to targeted teachers. | Sex, level of education, disability | 0 | - | 68 | Number | ACTUAL (cumulative, by quarter - auto-linked for Number indicators; FIVDB to complete for % indicators) Q1: 0 | 0% | Behind | Distribution lists, signed receipt forms, muster rolls, inventory records | Source: distribution lists, signed receipt forms, muster rolls, attendance sheets, inventory records. Method: maintained at partner and learning-facility level. Frequency: compiled and validated by programme/MEAL staff prior to reporting; verified through routine monitoring visits and spot checks. | Signed waybills cross-checked against teacher roster; PIB logistics spot-check per distribution round. | Compiled and validated by programme/MEAL staff prior to reporting; verified through routine monitoring visits and spot checks | Education Officer | Field data collection & first-line reporting | Procurement/supply-chain delays (printing, customs/import for specialised materials) may delay distribution. | During the reporting period (cumulative through Q1), FIVDB reported 0 against the indicator 'Number of teachers provided with teaching aids/materials' - 0% of the 68 life-of-project target. Disaggregated: 0 girls (<18), 0 boys (<18), 0 women (18+), 0 men (18+). | Narrative Proposal, Result 1 Indicator 3: consortium Baseline 93 (SC's continuing teachers from prior action) / consortium Target 168 (SC 100: 79 female, 21 male; PLAN/FIVDB 68: 45 female, 23 male - 51 Rohingya + 17 host). FIVDB's own baseline is 0 (all 68 teachers newly supported under this action). CLARIFICATION: 68 = 1 teacher per CBLF x 51 CBLFs + 17 additional host-community teachers = 45 female + 23 male. | 0 | 0 | 0 | 0
Result 1 | R1-I4 | R1A2.3 | R1A2.4, R1A2.5, R1A3.1 | Number of girls and boys provided with learning materials | Logframe (Annex I), Result 1 indicators - code R1-I4 | Minimum package = textbooks (or equivalent), reading materials and stationery, including adaptations for learners with disabilities and materials tailored to identified language needs. Where kits are provided per classroom, a content breakdown must justify reasonable provision per child. Disaggregate by sex, NFE type/level of education and disability. | Distribution lists and learner registers at facility level, with signed beneficiary receipts as primary evidence, verified through Post-Distribution Monitoring (PDM) surveys including PM KOI questions and CBLF monitoring reports. | Sex, level of education, disability | 0 | - | 1224 | Number | ACTUAL (cumulative, by quarter - auto-linked for Number indicators; FIVDB to complete for % indicators) Q1: 0 | 0% | Behind | Distribution lists, learner registers, signed beneficiary receipts, PDM survey | Source: distribution lists, learner registers at facility level, signed beneficiary receipts. Method: verified through Post-Distribution Monitoring (PDM) surveys including PM KOI questions and CBLF monitoring reports. Frequency: consolidated, cross-checked and validated by programme/MEAL staff prior to reporting; routine monitoring visits validate the distribution process. | Distribution records cross-checked against enrolment register to confirm no double-counting or non-enrolled recipients. | Consolidated, cross-checked and validated by programme/MEAL staff prior to reporting; routine monitoring visits validate the distribution process | MEAL Officer | Data consolidation, quality assurance & reporting | Procurement/supply-chain delays affecting print runs; new enrolments after a distribution round may require top-up kits. | During the reporting period (cumulative through Q1), FIVDB reported 0 against the indicator 'Number of girls and boys provided with learning materials' - 0% of the 1,224 life-of-project target. Disaggregated: 0 girls (<18), 0 boys (<18), 0 women (18+), 0 men (18+). | Narrative Proposal, Result 1 Indicator 4: consortium Baseline 0 (explicit - 'new materials will be distributed under this phase') / consortium Target 4,067 (SC 2,843: 2,293 girls, 550 boys; PLAN/FIVDB all 1,224 unique enrolled learners: 816 girls, 408 boys), aligned with ESWG guidance and the Myanmar Curriculum/ALP levels I-II. CLARIFICATION: Same 1,224 learners as R1-I1 (every enrolled learner receives materials - not an additional/separate group). FIVDB's own baseline = 0 (all new distribution this action). | 0 | 0 | 0 | 0
Result 1 | R1-I5 | R1A4.1 | R1A4.2, R1A4.3, R1A4.6, R1A4.7, R1A4.11, R1A4.12 | Number of teachers/education personnel showing increased knowledge and teaching skills to address children's learning needs | Logframe (Annex I), Result 1 indicators - code R1-I5 | Support = training, mentoring and coaching on skills/strategies to address identified learning needs (e.g. mixed-ability pedagogy, specific course content, basic literacy/numeracy, language pedagogy). Learning needs specified in the comments field. Disaggregate by sex, NFE type/level of education and disability. | Structured pre- and post-training assessments using a consortium-wide Teacher Assessment Tool aligned with training content, applied during Outcome Assessments; supplemented by classroom observation reports and teacher/student/mentor surveys. | Sex, role (teacher/other personnel) | 0 | 68 teachers/facilitators (training pool) | 68 | Number | ACTUAL (cumulative, by quarter - auto-linked for Number indicators; FIVDB to complete for % indicators) Q1: 0 | 0% | Behind | Teacher Assessment Tool (pre/post), classroom observation reports, OA survey | Source: Teacher Assessment Tool (structured pre/post training assessment). Method: applied during Outcome Assessments, supplemented by classroom observation reports and teacher/student/mentor surveys. Frequency: training data compiled quarterly; Outcome Assessment data collected periodically, reviewed through routine monitoring. | Pre/post test scoring reviewed by Education Coordinator; PIB samples a subset of assessment sheets each quarter. | Training data compiled quarterly; Outcome Assessment data collected periodically, reviewed through routine monitoring | Education Officer | Field data collection & first-line reporting | Training attendance may be disrupted by seasonal access constraints, competing duties, or facilitator turnover. | During the reporting period (cumulative through Q1), FIVDB reported 0 against the indicator 'Number of teachers/education personnel showing increased knowledge and teaching skills to address children's learning needs' - 0% of the 68 life-of-project target. Disaggregated: 0 girls (<18), 0 boys (<18), 0 women (18+), 0 men (18+). | Narrative Proposal, Result 1 Indicator 5: consortium Baseline 84 (SC-supported teachers who demonstrated improved knowledge/skills under ECHO HIP 2023, per the Teacher Assessment Tool) / consortium Target 140 (83% of the pooled 168 teachers: SC 100 + PLAN/FIVDB 68). FIVDB will recruit new teaching volunteers; all receive additional training to strengthen competencies. CLARIFICATION: 68 = all of FIVDB's teachers (same 68 as R1-I3) - FIVDB targets 100% of its own teachers to show improved knowledge/skills. The consortium's 140 (83% of 168) blends SC's lower pass-rate assumption with FIVDB's full-cohort target; the two are not directly comparable 1:1. | 0 | 0 | 0 | 0
Result 1 | R1-I6 | R1A4.13 | R1A5.1 | Number of students, teachers and other education personnel provided with psycho-social support services | Logframe (Annex I), Result 1 indicators - code R1-I6 | Psychosocial support (PSS) helps individuals recover after a crisis has disrupted their lives and return to normality after adverse events; limited to non-specialised service provision (not specialised mental health or CP case management). Education personnel may include parent-teacher associations, mothers-students associations, school management associations. Disaggregate by sex, NFE type/level of education, beneficiary type (student/teacher/other) and disability. | Beneficiary lists, attendance sheets, learning-material distribution registers, and PSS participation reports, compiled by CBLF facilitators and implementing-partner staff. | Sex, beneficiary type (student/teacher/other), disability | 0 | - | 2516 | Number | ACTUAL (cumulative, by quarter - auto-linked for Number indicators; FIVDB to complete for % indicators) Q1: 0 | 0% | Behind | Beneficiary lists, attendance sheets, PSS participation reports | Source: beneficiary lists, attendance sheets, learning-material distribution registers, PSS participation reports. Method: compiled by CBLF facilitators and implementing-partner staff. Frequency: monthly monitoring and document checks. | PSS attendance logs reconciled monthly against enrolment/staff rosters to avoid duplicate counting across sessions. | Monthly monitoring and document checks | MEAL Officer | Data consolidation, quality assurance & reporting | Uptake may be affected by stigma around PSS/MHPSS or scheduling conflicts with academic sessions. | During the reporting period (cumulative through Q1), FIVDB reported 0 against the indicator 'Number of students, teachers and other education personnel provided with psycho-social support services' - 0% of the 2,516 life-of-project target. Disaggregated: 0 girls (<18), 0 boys (<18), 0 women (18+), 0 men (18+). | Narrative Proposal, Result 1 Indicator 6: consortium Baseline 2,781 (beneficiaries oriented on PFA during ECHO HIP 2023) / consortium Target 8,302 (SC ~5,786: 2,843 learners w/ SEL + 100 teachers w/ PFA/PSS training + 2,843 parents w/ PFA orientation; PLAN/FIVDB 2,516: 68 teachers + 1,224 learners w/ Playful Minds for Wellbeing + 1,224 parents: 612 women, 612 men, via bi-monthly parenting sessions). Corrected from an earlier internal draft that showed 2,741 - the breakdown always summed to 2,516; the LOP Target has been aligned to match. CLARIFICATION: 2,516 = 68 teachers + 1,224 learners (all of R1-I1) + 1,224 parents/caregivers (1 per enrolled learner, 612 women + 612 men via bi-monthly parenting sessions). This LOP target was corrected from an earlier internal draft that showed 2,741 - the breakdown always summed to 2,516; the target figure is now aligned to match. | 0 | 0 | 0 | 0
Result 1 | R1-I7 | R1A4.4 | R1A4.5 | Number of teachers and other education personnel showing increased knowledge and skills to address the protection needs of girls and boys | Logframe (Annex I), Result 1 indicators - code R1-I7 | Other education personnel may include parent-teacher associations, mothers-students associations, school management associations. Protection needs defined per context (child protection, PSS, SGBV information, mine/UXO risk education, HIV/AIDS, nutrition, health/hygiene, gender-sensitive and conflict-sensitive education). Disaggregate by sex, NFE type/level of education and disability. | Pre- and post-training assessment records, observation checklists, and supervision visit reports, compiled by CBLF teaching volunteers, implementing partners and Education Officers. | Sex, role | 0 | 68 teachers/facilitators (training pool) | 68 | Number | ACTUAL (cumulative, by quarter - auto-linked for Number indicators; FIVDB to complete for % indicators) Q1: 0 | 0% | Behind | Pre/post training assessment records, observation checklists, supervision reports | Source: pre/post training assessment records, observation checklists, supervision visit reports. Method: compiled by CBLF teaching volunteers, implementing partners and Education Officers. Frequency: quarterly; Outcome Assessment data collected periodically. | Pre/post assessment scores reviewed by Education Coordinator; PIB technical review of training content each cycle. | Quarterly; Outcome Assessment data collected periodically | Education Officer | Field data collection & first-line reporting | Turnover of trained teachers/facilitators may erode cumulative protection knowledge within the workforce. | During the reporting period (cumulative through Q1), FIVDB reported 0 against the indicator 'Number of teachers and other education personnel showing increased knowledge and skills to address the protection needs of girls and boys' - 0% of the 68 life-of-project target. Disaggregated: 0 girls (<18), 0 boys (<18), 0 women (18+), 0 men (18+). | Narrative Proposal, Result 1 Indicator 7: consortium Baseline 280 (CESG members trained under ECHO HIP 2023) / consortium Target 408 (SC 240: 140 CESG members across 35 CESGs + 100 teachers; PLAN/FIVDB 168: 68 teachers/education personnel + 100 members across ~26 CESGs). CLARIFICATION: FIVDB's own contribution to the consortium's 168 sub-total is 68 teachers only (the 100 CESG members in that 168 figure sit under R1-I6-adjacent community-engagement activities, not 'other education personnel' here) - see Activity Tracker R1A4 rows for the exact training cohorts. | 0 | 0 | 0 | 0
Result 1 | R1-I8 | R1-A4 |  | Number of girls and boys referred to specialised services (e.g. child protection, health, MHPSS) | Logframe (Annex I), Result 1 indicators - code R1-I8 | Referrals must be based on up-to-date referral mechanisms assessing both availability and quality of service delivery. Disaggregate by sex, NFE type/level of education and disability. | Standardized referral logbooks and case-management databases maintained by implementing partners and service providers; trained case workers record referral type, pathway and expected feedback timelines, disaggregated by sex, age, disability and sector. | Sex, level of education, disability | 0 | - | 122 | Number | ACTUAL (cumulative, by quarter - auto-linked for Number indicators; FIVDB to complete for % indicators) Q1: 0 | 0% | Behind | Referral logbook, case management database | Source: standardized referral logbooks, case-management databases. Method: maintained by implementing partners and service providers; trained case workers record referral type, pathway and expected feedback timelines, disaggregated by sex, age, disability and sector. Frequency: referral data collected and reviewed monthly; reported through partner progress reports and quarterly project reports. | Referral tracker cross-checked monthly against confirmation received from CP/Health/MHPSS receiving services. | Referral data collected and reviewed monthly; reported through partner progress reports and quarterly project reports | MEAL Officer | Data consolidation, quality assurance & reporting | Referral-pathway bottlenecks at receiving CP/Health services may delay confirmed uptake, understating the indicator. | During the reporting period (cumulative through Q1), FIVDB reported 0 against the indicator 'Number of girls and boys referred to specialised services (e.g. child protection, health, MHPSS)' - 0% of the 122 life-of-project target. Disaggregated: 0 girls (<18), 0 boys (<18), 0 women (18+), 0 men (18+). | Narrative Proposal, Result 1 Indicator 8: consortium Baseline 0 / consortium Target 406, projected at ~10% of enrolled learners requiring referral (SC ~284 of 2,843; PLAN/FIVDB ~122 of 1,224). Explicitly noted as a projection based on historical trends that may vary depending on identified needs. Corrected from an earlier internal draft that showed 131 - the 10% calculation always gave ~122; the LOP Target has been aligned to match. CLARIFICATION: 122 = ~10% of 1,224 enrolled learners. Explicitly a projection, not a fixed quota - referral volume 'may vary depending on identified needs' per the Narrative Proposal. This LOP target was corrected from an earlier internal draft that showed 131. | 0 | 0 | 0 | 0
Result 1 | R1-I9 | R1-A1 |  | % educational facilities that are carrying out environmental and climate friendly activities day-to-day | Logframe (Annex I), Result 1 indicators - code R1-I9 | Environmental/climate-friendly activities may take place during the school day (lesson modules) or after school (extra-curricular). Examples: planting/maintaining school (vegetable) gardens, tree planting, solid waste sorting, upcycling, energy/water-consumption reduction actions. | Activity and event reports, photographic documentation, observation reports, and monitoring visit reports, compiled by Education MIS and MEAL staff. | N/A (facility-level indicator) | 0% | 51 FIVDB-supported facilities | 65% | % | [9 empty] | No data yet | Activity/event reports, photographic documentation, monitoring visit reports | Source: activity and event reports, photographic documentation, observation reports, monitoring visit reports. Method: compiled by Education MIS and MEAL staff. Frequency: monthly and quarterly reporting; routine monitoring visits. | Facility Monitoring Checklist verified on-site quarterly; photographic evidence of the activity retained. | Monthly and quarterly reporting; routine monitoring visits | Education Officer | Field data collection & first-line reporting | Environmental activities may be deprioritised against core education delivery if resources/time are constrained. | [P]% of FIVDB-supported facilities ([X] of 51) were implementing environmental/climate-friendly activities as of [date], against a 65% target. | Narrative Proposal, Result 1 Indicator 9: consortium Baseline 0% (pilot intervention, not previously implemented) / consortium Target 65% of all 121 supported facilities (SC: 70 facilities target >=33 implementing; PLAN/FIVDB: 51 CBLFs target >=33 implementing), primarily via homestead vertical gardening adapted to the camp context. CLARIFICATION: 65% of FIVDB's 51 CBLFs = ~33 facilities. This is the officially approved consortium-wide %, applied identically to FIVDB's own facility count (not an FIVDB-specific calculation). | N/A | N/A | N/A | N/A
RESULT 2 - CHILD PROTECTION (FIVDB Activities 1, 3, 4, 5)
Result 2 | R2-I1 | R2A1.2 | R2A1.3, R2A1.4, R2A1.6, R2A1.7 | (MANDATORY) % of children and caregivers whose urgent child protection needs/risks have been addressed through the case management process | Logframe (Annex I), Result 2 indicators - code R2-I1 | Numerator = children and caregivers surveyed reporting their urgent child protection needs were addressed via the case-management (CM) process. Denominator = total children and caregivers surveyed who received CM. Survey administered at case closure or case follow-up; children and caregivers measured separately. Case-management quality demonstrated by meeting the CP Case Management Minimum Standards in Humanitarian Settings (7-step process). | CPIMS+, case management registers, individual case files/hard-copy case records, and survey reports, recorded by caseworkers. | Children and caregivers measured separately; sex, age | 0% | ~320 FIVDB case-management caseload (A1) | 95% | % | [9 empty] | No data yet | CPIMS+, case management registers, individual case files, survey reports | Source: CPIMS+, case management registers, individual case files/hard-copy case records, survey reports. Method: recorded by caseworkers, per the CP Case Management Minimum Standards (7-step process). Frequency: case reporting monthly; satisfaction survey reports annually. | PIB technical supervisor reviews a sample of closed case files each month against closure-survey responses. | Case reporting monthly; satisfaction survey reports annually | Technical Coordinator–Protection | Field data collection, case oversight & first-line reporting | Case backlog if caseworker-to-case ratio exceeds CPMS standards; high mobility of families may disrupt follow-up. | [P]% of children and caregivers surveyed reported that their urgent child protection needs were addressed through FIVDB's case management process during [reporting period], against a 95% target. | Narrative Proposal, Result 2 Indicator 1 (mandatory): Baseline 0 (not systematically tracked pre-action) / Target 95%, based on performance achieved in previous ECHO-funded CP case management in Cox's Bazar, factoring anticipated caseload/complexity, staffing/supervision capacity and planned investment in caseworker training and quality referrals. CLARIFICATION: 95% is the officially approved Logframe (Annex I) target, not FIVDB-set. R2-I1 through R2-I5 percentages cluster in the 75-95% range because they come from the same approved Logframe table and comparable ECHO HIP 2023 baselines - each has its own distinct source paragraph in the Narrative Proposal, not a copied figure. | N/A | N/A | N/A | N/A
Result 2 | R2-I2 | R2A1.1 | - | % of children separated from or allegedly associated with armed groups and armed forces who benefit from appropriate care and services | Logframe (Annex I), Result 2 indicators - code R2-I2 | Children Associated with Armed Forces and Armed Groups (CAAFAG) = all children, including girls, under age 18 who are or have been recruited or used by any armed force or group in any capacity. Numerator = identified CAAFAG children who receive care/services. Denominator = total identified CAAFAG children. Appropriate care/services can include health care, education, legal aid, MHPSS, interim care, reintegration into family/community. Measure each service separately. | CPIMS+, case management registers, individual case files/hard-copy case records, and relevant survey reports, recorded by caseworkers. | Sex, age | 0% | Subset of 314 caseload (# CAAFAG confirmed at identification) | 80% | % | [9 empty] | No data yet | Case management database | Source: CPIMS+, case management registers, individual case files/hard-copy case records, relevant survey reports. Method: recorded by caseworkers, measured per service type separately. Frequency: case data daily; reporting monthly; survey reports annually. | Case-file review cross-checked with service-provision records (health, education, legal aid, MHPSS, interim care). | Case data daily; reporting monthly; survey reports annually | Technical Coordinator–Protection | Field data collection, case oversight & first-line reporting | Under-identification of CAAFAG cases due to stigma/fear of reprisal; service availability gaps at receiving agencies. | [P]% of identified CAAFAG children benefited from at least one appropriate care/service during [reporting period], against an 80% target. | Narrative Proposal, Result 2 Indicator 2 (CAAFAG): Baseline 0% (no action-specific reference value) / Target 80%, informed by previous ECHO-funded CAAFAG/CP programming in Cox's Bazar, factoring expected caseload, sensitivity/complexity of CAAFAG cases, security/access constraints, and referral-pathway capacity. CLARIFICATION: 80% applies only to children identified as CAAFAG within FIVDB's caseload - not a general child-protection percentage across all 320 case-management children. | N/A | N/A | N/A | N/A
Result 2 | R2-I3 | R2A1.5 | R2A4.1, R2A4.4, R2A5.1, R2A5.3 | Average % knowledge increase amongst participants on the protection subject in focus | Logframe (Annex I), Result 2 indicators - code R2-I3 | Comments field defines: type of participants (population/authorities/armed forces/armed groups etc.), number of expected participants, and subject of training. Reports disaggregate number of participants by age and sex. | Pre-test and post-test assessment forms, training attendance records, and capacity assessment survey questionnaires, compiled by CP, MIS and MEAL focal points. | Age, sex | 0% | FIVDB frontline staff/volunteers attending R2-A5 trainings | 80% | % | [9 empty] | No data yet | Pre/post assessment forms, training attendance records, capacity assessment survey | Source: pre-test and post-test assessment forms, training attendance records, capacity assessment survey questionnaires. Method: compiled by CP, MIS and MEAL focal points; participant type/number/subject specified in comments. Frequency: assessment reports monthly; comprehensive training reports quarterly; survey reports annually. | MEAL Officer verifies pre/post test scoring for each session; PIB reviews a sample of training packs quarterly. | Assessment reports monthly; comprehensive training reports quarterly; survey reports annually | MEAL Officer | Data consolidation, quality assurance & reporting | High staff/volunteer turnover may erode cumulative knowledge retention between training cycles. | Frontline staff and volunteers trained by FIVDB showed an average knowledge increase of [P]% during [reporting period], against an 80% target. | Narrative Proposal, Result 2 Indicator 3: Baseline 0% (increase is measured through pre/post tests introduced under the action) / Target 80% average knowledge increase, informed by performance in previous HIP activities. Consortium-wide, this indicator covers an estimated 4,805 unique participants (carers, adolescents, community leaders, para-social workers, volunteers, multi-sector staff) across all capacity-building activities on protection subjects. CLARIFICATION: Measures average knowledge GAIN (post-test minus pre-test, divided by pre-test), not an absolute post-test score. | N/A | N/A | N/A | N/A
Result 2 | R2-I4 | R2A3.1 | R2A3.2, R2A3.3, R2A3.4, R2A3.5, R2A3.6, R2A4.2, R2A4.3, R2A4.5, R2A4.6, INC-5, GEN-2 | (MANDATORY) % of persons who receive appropriate PSS reporting improved mental health and psychosocial well-being OR capacities to cope | Logframe (Annex I), Result 2 indicators - code R2-I4 | Mental health and psychosocial wellbeing measured using one of the six IASC Common M&E Framework domains: functioning; subjective wellbeing; disabling distress/symptoms; coping; social behaviour; social connectedness. Delivered as a layered system of complementary supports, with safe, confidential, timely referrals, per IASC MHPSS in Emergency Settings Guideline and the MHPSS Minimum Service Package. | Standardized pre- and post-assessment tools (validated for context/language), wellbeing surveys, focus group discussions, key informant interviews, case files, and MHPSS activity records, following the IASC Common M&E Framework. | Sex, age; IASC domain used | 0% | ~8,640 in PALS/MPCAC/WGSS/community groups (A3-A4) | 80% | % | [9 empty] | No data yet | Pre/post PSS assessment tool (IASC domains), wellbeing surveys, case files | Source: standardized pre-/post-assessment tools (validated for context/language), wellbeing surveys, focus group discussions, key informant interviews, case files, MHPSS activity records. Method: following the IASC Common M&E Framework (6 domains). Frequency: recorded at PSS phase start/end; compiled monthly for ongoing monitoring; comprehensive outcome reports (quantitative + qualitative) annually. | PIB technical supervisor reviews a sample of pre/post assessment pairs each quarter for consistency. | Recorded at PSS phase start/end; compiled monthly for ongoing monitoring; comprehensive outcome reports (quantitative + qualitative) annually | Technical Coordinator–Protection | Field data collection, case oversight & first-line reporting | Under-reporting of distress due to stigma; drop-out between group entry and exit reduces paired-assessment sample size. | [P]% of persons receiving psychosocial support through FIVDB's MPCAC/WGSS/community-group sessions reported improved wellbeing or coping during [reporting period], against an 80% target. | Narrative Proposal, Result 2 Indicator 7 (mandatory): Baseline 0% (wellbeing/coping can only be measured after participants complete PSS support) / Target 80%, justified by previous PSS intervention results, the IASC-aligned package delivered through MPCACs/WGSSs, trained facilitators, and functioning referral pathways. CLARIFICATION: Numbered 'Result 2 Indicator 7' in the consortium's full 8-indicator Result 2 set (3 of the 8 are SC-led GBV-specific reference items tracked separately - see R2-Ref rows). | N/A | N/A | N/A | N/A
Result 2 | R2-I5 | INC-12 | - | % of caseworkers whose knowledge assessment score is at least 70% | Logframe (Annex I), Result 2 indicators - code R2-I5 | Numerator = case workers who score 70% or higher on the knowledge assessment. Denominator = case workers who finalised the Case Worker Capacity Assessment. Assesses caseworker attitudes, knowledge and skills against minimum competency standards for case management service providers, identifying possible service-quality gaps. | Case Worker Capacity Assessment Tool, applied by implementing-partner staff and the consortium's Case Management/MEAL teams. | Sex | 0% | All active FIVDB case workers | 75% | % | [9 empty] | No data yet | Case Worker Capacity Assessment Tool | Source: Case Worker Capacity Assessment Tool. Method: applied by implementing-partner staff and the consortium's Case Management/MEAL teams, assessed against minimum competency standards for case management service providers. Frequency: annually. | PIB technical supervisor co-scores a sample of assessments to check inter-rater consistency. | Annually | Technical Coordinator–Protection | Field data collection, case oversight & first-line reporting | High case-worker turnover may mean new starters are assessed before consolidating knowledge; coaching capacity constraints. | [P]% of FIVDB case workers assessed scored 70% or above on the Case Worker Capacity Assessment during [reporting period], against a 75% target. | Narrative Proposal, Result 2 Indicator 8 (Protection of individuals): Baseline 75% expected pass rate is itself the assumption underpinning the target - the Narrative states 'it is expected that at least 75% of trainees will achieve a minimum score of 70%'. Results to be disaggregated by agency (SC/PLAN), sex, age, disability status and role where feasible. CLARIFICATION: Numerator = caseworkers scoring >=70%; Denominator = caseworkers who completed the assessment (not all caseworkers on payroll, only those assessed). | N/A | N/A | N/A | N/A
RESULT 2 - REFERENCE ONLY: GBV Case Management (SC-led, Activity 2 - NOT delivered by FIVDB)
Result 2 (ref.) | R2-Ref1 | R2-A2 (SC) |  | (MANDATORY) Number of minimum standards for care for survivors achieved | Logframe (Annex I), Result 2 indicators - SC-led (reference only, not FIVDB-delivered) | For baseline: Numerator = minimum standards of care for survivors met prior to action start. Denominator = total minimum standards of care for survivors. For target: Numerator = standards met prior to action start PLUS standards to be met within the action timeframe. Denominator = total minimum standards. Checklist contextualised and submitted at proposal stage. | Structured service quality assessment using a contextualized GBV Minimum Standards Checklist (adapted from the Inter-Agency GBV Case Management Guidelines, 2017); only standards assessed as 'Met' count toward the numerator; consolidated at service-point level and validated by GBV supervisors. | N/A (standards checklist, SC-led) | 0 | N/A | N/A | Number | ACTUAL (cumulative, by quarter - auto-linked for Number indicators; FIVDB to complete for % indicators) Q1: 0 | N/A | N/A | GBV minimum standards checklist | Source: contextualized GBV Minimum Standards Checklist (adapted from the Inter-Agency GBV Case Management Guidelines, 2017). Method: only standards assessed as 'Met' count toward the numerator; consolidated at service-point level and validated by GBV supervisors. Frequency: initial assessment followed by quarterly monitoring. | N/A - SC-led verification. | Initial assessment followed by quarterly monitoring | SC | Field data collection & first-line reporting | Not a FIVDB risk owner - dependent on SC's GBV case-management capacity and standards implementation. | During the reporting period (cumulative through Q1), FIVDB reported 0 against the indicator '(MANDATORY) Number of minimum standards for care for survivors achieved' - N/A of the N/A life-of-project target. Disaggregated: 0 girls (<18), 0 boys (<18), 0 women (18+), 0 men (18+). | Narrative Proposal, Result 2 Indicator 5 (GBV, mandatory, minimum standards for survivor care): Baseline 0 (checklist-based measurement introduced under this action). Based on a review of 31 minimum standards (Annex 27): SC target = 16 standards (reflecting its EiE, protection and health interventions); PLAN target = 12 standards (aligned with its EiE and Child Protection interventions - separate from, and not solely 'SC-led', though FIVDB's own role in the underlying GBV case management activity, R2-A2, remains referral-only). CLARIFICATION: Annex 27 = the GBV Minimum Standards Checklist referenced in the Narrative Proposal (Result 2, Activity 2 section) - an annex to the consortium's DG ECHO Single Form, held by PIB/SC, not a standalone FIVDB document. This row is shown for traceability only; FIVDB is not directly accountable for it since the underlying Activity 2 is SC-led. | 0 | 0 | 0 | 0
Result 2 (ref.) | R2-Ref2 | R2-A2 (SC) |  | Number of individuals benefiting from GBV response services (SC-led, R2-A2) | Logframe (Annex I), Result 2 indicators - SC-led (reference only, not FIVDB-delivered) | Covers response services to survivors of GBV (women, men, girls, boys); disaggregated by age, sex and service(s) received; strategies applied to avoid double counting. | SC's GBV case-management database. FIVDB contributes only via safe identification/referral, not direct service delivery, so this indicator is tracked by SC, not FIVDB. | Age, sex, service type (SC-led) | 0% | N/A | N/A | % | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | GBV case management database (SC) | Not specified in Narrative Proposal - to be defined by FIVDB/PIB. | N/A - SC-led verification. | n/a | SC | Field data collection & first-line reporting | Not a FIVDB risk owner - dependent on SC's GBV case-management capacity. | Not reported in FIVDB's own narrative - this is delivered by SC under Result 2-Activity 2. Where relevant, describe FIVDB's referral contribution qualitatively rather than against this target. | Consortium target 750 - not FIVDB-delivered; referral only | N/A | N/A | N/A | N/A
Result 2 (ref.) | R2-Ref3 | R2-A2 (SC) |  | % of GBV high-risk cases supervised (SC-led, R2-A2) | Logframe (Annex I), Result 2 indicators - SC-led (reference only, not FIVDB-delivered) | Numerator = total high-risk cases reviewed by a supervisor. Denominator = total high-risk cases in the case-management process. High-risk = immediate threat to survivor safety/health requiring urgent action. | SC's GBV supervision log (one-on-one, group, on-the-job observation/coaching, team meetings). Not applicable to FIVDB, which does not hold GBV case-management caseload under R2-A2. | N/A (case-level, SC-led) | 0% | N/A | N/A | % | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | GBV case management database (SC) | Not specified in Narrative Proposal - to be defined by FIVDB/PIB. | N/A - SC-led verification. | n/a | SC | Field data collection & first-line reporting | Not a FIVDB risk owner - FIVDB has no GBV case-management caseload under R2-A2. | Not reported in FIVDB's own narrative - this is delivered by SC under Result 2-Activity 2; FIVDB has no caseload against this indicator. | Consortium target 95% - not FIVDB-delivered; referral only | N/A | N/A | N/A | N/A
SPECIFIC-OBJECTIVE / CROSS-CUTTING INDICATORS
Specific objective | SO-I1 | R1A5.2 | R1A5.3, INC-6, GEN-4 | % of beneficiaries reporting that humanitarian assistance is delivered in a safe, accessible, accountable and participatory manner | Logframe (Annex I), Specific Objective indicators - code SO-I1 | This is more a process than an outcome indicator; DG ECHO wants to ensure sufficient attention is given to protection mainstreaming so corrective measures are identified and implemented when required during the action. At reporting stage, also state the total number of beneficiaries interviewed. Disaggregate figures (% and absolute numbers) by sex, age and disability. | KOI perception surveys, Post-Distribution Monitoring (PDM) reports, client satisfaction surveys, and outcome assessment reports, administered by skilled enumerators and implementing-partner staff. | Sex, age, disability | 0% | Survey sample (size confirmed per round) | 85% | % | [9 empty] | No data yet | Community perception survey | Source: KOI perception surveys, Post-Distribution Monitoring (PDM) reports, client satisfaction surveys, outcome assessment reports. Method: administered by skilled enumerators and implementing-partner staff, disaggregated by sex, age and disability. Frequency: every four months, plus annual reporting. | Survey tool piloted and reviewed by PIB M&E before each round; data entry double-checked against paper/digital forms. | Every four months, plus annual reporting | MEAL Officer | Data consolidation, quality assurance & reporting | Survey response bias or low response rate; sensitive questions may be under-reported without skilled enumerators. | [P]% of [N] beneficiaries surveyed in FIVDB's camps reported that assistance was delivered safely, accessibly, accountably and participatorily, against an 85% target. | Consortium specific-objective target 85%; FIVDB tracks its respondent share | N/A | N/A | N/A | N/A
Specific objective | SO-I2 | R1-A1 to R1-A7 |  | % targeted girls and boys who are retained in education at the end of the action | Logframe (Annex I), Specific Objective indicators - code SO-I2 | Measures the % of children targeted for EiE support who remain in some form of education at the end of the action. Targeted girls and boys = any child supported by the project (including those already enrolled at action start and those newly enrolled during the action). Retained = still enrolled in NFE or formal education at the end of the action; actions ending during school holidays use the last academic term as the end point. Learners completing the final grade of secondary school count as still in education. Disaggregate by sex, NFE type/level of education and disability. | Enrolment registers, daily attendance sheets, retention tracking records, endline attendance documentation, cross-checked with the Education Management Information System (EMIS) database, compiled by CBLF facilitators and consolidated by the Education/MEAL team. | Sex, level/type of education, disability | 0% | 1,224 targeted learners | 90% | % | [9 empty] | No data yet | CBLF enrolment & tracking registers | Source: enrolment registers, daily attendance sheets, retention tracking records, endline attendance documentation. Method: cross-checked with the Education Management Information System (EMIS) database; compiled by CBLF facilitators and consolidated by the Education/MEAL team. Frequency: monthly reviews, final retention calculation at endline. | Endline tracking cross-checked against attendance/drop-out records; PIB verifies a sample against household follow-up. | Monthly reviews; final retention calculation at endline | Education Officer | Field data collection & first-line reporting | High mobility of the Rohingya population (incl. potential relocation to Bhasan Char) may affect endline tracking accuracy. | [P]% of FIVDB's 1,224 targeted learners ([X] children) remained enrolled in education at the end of the action, against a 90% target. | Consortium specific-objective target 90%; applies to FIVDB's 1,224 learners (updated from 1,187 per Detailed Budget/Narrative Proposal) | N/A | N/A | N/A | N/A

## 8. Activity Tracker
8. Activity Tracker - FIVDB Implementation Activities (Sub-activity Level)
Tracks physical progress of FIVDB's workplan sub-activities, separate from the outcome/output indicators in the IPTT. Each Activity Code (R1A1, R2A1, etc.) IS the FIVDB Detailed Budget's own Reference code - used directly, not a cross-reference. 'Sub-sub-activity' further splits a sub-activity into its distinct component tasks where useful (e.g. 'establish' vs 'refurbish', or two different kit types bundled in one description) - populated only where a split adds real tracking value; blank elsewhere. 'Process (How Conducted)' summarises the delivery method for each sub-activity; 'Contribution to Indicator' explains how the sub-activity's output feeds its linked IPTT indicator(s). 'Source Reference' cites the exact Detailed Budget row for every sub-activity. 'Related Budget Line' and 'Approved Budget (EUR/BDT)' show the full budget line total this sub-activity draws on - shared across several sub-activities/rows below; do not sum this column. Example: all 14 sub-activities under R1A4 show the SAME Approved Budget figure (that budget line's full total) - this is intentional, not 14 separate budgets; see Sheet 13 (Budget Tracker) for the actual itemised cost breakdown within each line. PLANNED (by quarter) is a MANUAL numeric entry - FIVDB enters the target number planned for that specific quarter (yellow cells; e.g. 20 learners planned in Q1, 15 in Q2, etc. - not cumulative). ACTUAL (by quarter) is fully AUTOMATIC - the sum of 'Total Participants' (Sheet 10, Activity Data Log) plus 'Total Recipients' (Sheet 11, Distribution Log) logged against this exact Activity/Sub-activity Code within that quarter. No manual entry; recalculates as Sheets 10-11 are populated. % Physical Progress = cumulative ACTUAL up to the current reporting quarter (Sheet 7) / cumulative PLANNED up to the same quarter. RAG Status: On Track >=90%, Slightly Behind 70-89%, Behind <70%. 'Data Log Cross-Check' shows the underlying entry count/average from Sheet 10, for transparency. Output targets, locations and budget categories are indicative planning estimates - to be validated with PIB and FIVDB's detailed budget at inception.
Result | Activity Code | Sub-activity Code | Sub-activity Description | Sub-sub-activity (where applicable) | Process (How Conducted) | Location / Camps | Output Target (indicative) | Linked Indicator(s) | Contribution to Indicator | Target Number | Unit | PLANNED (by quarter) - FIVDB manual target number | [7 empty] | ACTUAL (by quarter) - auto total from Sheets 10-11 | [7 empty] | % Physical Progress (auto) | RAG Status | Budget Category (indicative) | Related Budget Line (see Sheet 13) | Approved Budget (EUR, full line) | Approved Budget (BDT, full line) | Data Log Cross-Check (Sheet 10, latest entry) | How to Articulate in Narrative Report | Means of Verification | Source Reference | Responsible | Comments
[12 empty] | Q1 | Q2 | Q3 | Q4 | Q5 | Q6 | Q7 | Q8 | Q1 | Q2 | Q3 | Q4 | Q5 | Q6 | Q7 | Q8
R1A1 - Identification, Assessment & Placement of Out-of-School/Dropout Children (Budget Ref R1A1, BDT 40,000 / EUR 279.72)
Result 1 | R1A1 | R1A1.1 | Conduct household survey through community volunteers to identify out-of-school and dropout children. |  | Delivered as a planned field activity by FIVDB staff/volunteers, following the sub-activity description, with progress recorded in this tracker. | Camps 1W, 6, 21, 24 | All target households surveyed | R1-I1 | Generates the count of outputs (facilities/people/sessions, as applicable) reported under R1-I1. | See target description | survey | [17 empty] | No data yet | R1A1 (Budget) | R1A1 (Budget) | 279.72 | 39999.96 | No Data Log entries yet | During [reporting period], FIVDB delivered: Conduct household survey through community volunteers to identify out-of-school and dropout children. (target: All target households surveyed), contributing to indicator 'Number of targeted girls and boys enrolled in non-formal education services' (R1-I1). Source: FIVDB Detailed Budget, row 46 (Household survey through community volunteers). | Survey tool; household tracking log | FIVDB Detailed Budget, row 46 (Household survey through community volunteers) | Education Officer | Non-budgetary - carried out by teaching volunteers as part of their incentivised role (no separate cost line). CLARIFICATION: This is the household SURVEY step (identification), not enrolment itself - it has no separate numeric target because it covers 'all target households' in the 4 camps. The 1,224 enrolment figure only appears once children are actually registered (see R1A2.1 onward, feeding indicator R1-I1).
Result 1 | R1A1 | R1A1.2 | Conduct technical/disability assessment and screening of identified children (minimum 3% disability target), referring complex cases to Humanity & Inclusion (HI) under FIVDB's MoU. |  | Individual identification, intake/assessment, case planning, service delivery and follow-up, per the CP Case Management Minimum Standards 7-step process. | Camps 1W, 6, 21, 24 | Minimum 3% of 1,224 children (~37) | R1-I1 | Generates the count of outputs (facilities/people/sessions, as applicable) reported under R1-I1. | 3 | children | [17 empty] | No data yet | R1A1 (Budget) | R1A1 (Budget) | 279.72 | 39999.96 | No Data Log entries yet | During [reporting period], FIVDB delivered: Conduct technical/disability assessment and screening of identified children (minimum 3% disability target), referring complex cases to Humanity & Inclusion (HI) under FIVDB's MoU. (target: Minimum 3% of 1,224 children (~37)), contributing to indicator 'Number of targeted girls and boys enrolled in non-formal education services' (R1-I1). Source: FIVDB Detailed Budget, row 48 (Technical assessment; HI MoU; 3% disability target). | Screening/assessment form; HI referral record | FIVDB Detailed Budget, row 48 (Technical assessment; HI MoU; 3% disability target) | Education Officer | HI also trains FIVDB staff/volunteers on identification and referral; technical assessment itself is non-budgetary beyond HI partnership. CLARIFICATION: Target = 3 (representing the minimum 3% disability-screening rate applied against the 1,224 total, i.e. ~37 children) - NOT a target of 3 children. See indicator R1-I1 (IPTT, Sheet 7) for the full 1,224 enrolment target this screening step supports.
Result 1 | R1A1 | R1A1.3 | Print placement/assessment and disability-screening tools. | Step 1: Raise PR for tool printing (Purchase Request). Step 2: PR approval by Project Manager/Finance. Step 3: Procurement/vendor selection per FIVDB procurement policy. Step 4: Goods received at warehouse and quality-checked. Step 5: Dispatch/distribution to camps. Step 6: Signed waybill/distribution record filed (last step). | Individual identification, intake/assessment, case planning, service delivery and follow-up, per the CP Case Management Minimum Standards 7-step process. | Camps 1W, 6, 21, 24 | 1 lumpsum print run, 4 times | R1-I1 | Generates the count of outputs (facilities/people/sessions, as applicable) reported under R1-I1. | 1 | lumpsum | [17 empty] | No data yet | R1A1 (Budget) | R1A1 (Budget) | 279.72 | 39999.96 | No Data Log entries yet | During [reporting period], FIVDB delivered: Print placement/assessment and disability-screening tools. (target: 1 lumpsum print run, 4 times), contributing to indicator 'Number of targeted girls and boys enrolled in non-formal education services' (R1-I1). Source: FIVDB Detailed Budget, row 49 (Printing of tools for placement/assessment/disability screening). | Printed tool sets; procurement record | FIVDB Detailed Budget, row 49 (Printing of tools for placement/assessment/disability screening) | Education Officer | BDT 40,000 total (1 lumpsum x 4 times x 10,000). CLARIFICATION: Target = 1 lumpsum print run (repeated 4 times across the action) - a procurement/output unit, not a beneficiary headcount. This activity supports indicator R1-I1 but does not itself carry the 1,224 figure.
R1A2 - Education Service Delivery Support: Learning Materials, Teaching-Volunteer Incentives & Assistive Devices (Budget Ref R1A2, BDT 27,698,100 / EUR 193,693.01)
Result 1 | R1A2 | R1A2.1 | Provide monthly incentives to host-community teacher volunteers. |  | Delivered as a planned field activity by FIVDB staff/volunteers, following the sub-activity description, with progress recorded in this tracker. | Camps 1W, 6, 21, 24 | 17 volunteers x 22 months | R1-I3 | Generates the count of outputs (facilities/people/sessions, as applicable) reported under R1-I3. | 17 | volunteers | [17 empty] | No data yet | R1A2 (Budget) | R1A2 (Budget) | 193693.01 | 27698100.43 | No Data Log entries yet | During [reporting period], FIVDB delivered: Provide monthly incentives to host-community teacher volunteers. (target: 17 volunteers x 22 months), contributing to indicator 'Number of teachers provided with teaching aids/materials' (R1-I3). Source: FIVDB Detailed Budget, row 52 (Incentives for teacher volunteers from host community). | Payroll/incentive disbursement record | FIVDB Detailed Budget, row 52 (Incentives for teacher volunteers from host community) | Education Officer | BDT 15,500/volunteer/month x 17 x 22 = 5,797,000.
Result 1 | R1A2 | R1A2.2 | Provide monthly incentives to refugee-community teacher volunteers. |  | Delivered as a planned field activity by FIVDB staff/volunteers, following the sub-activity description, with progress recorded in this tracker. | Camps 1W, 6, 21, 24 | 51 volunteers x 22 months | R1-I3 | Generates the count of outputs (facilities/people/sessions, as applicable) reported under R1-I3. | 51 | volunteers | [17 empty] | No data yet | R1A2 (Budget) | R1A2 (Budget) | 193693.01 | 27698100.43 | No Data Log entries yet | During [reporting period], FIVDB delivered: Provide monthly incentives to refugee-community teacher volunteers. (target: 51 volunteers x 22 months), contributing to indicator 'Number of teachers provided with teaching aids/materials' (R1-I3). Source: FIVDB Detailed Budget, row 53 (Incentives for teacher volunteers from refugee community). | Payroll/incentive disbursement record | FIVDB Detailed Budget, row 53 (Incentives for teacher volunteers from refugee community) | Education Officer | BDT 13,000/volunteer/month x 51 x 22 = 14,586,000.
Result 1 | R1A2 | R1A2.3 | Distribute scholastic material kits (exercise books, ALP books, drawing books, pens, pencils, water bottle, erasers, sharpeners) to enrolled children, 2 shifts per CBLF. | Step 1: Raise PR for scholastic material kits (Purchase Request). Step 2: PR approval by Project Manager/Finance. Step 3: Procurement/vendor selection per FIVDB procurement policy. Step 4: Goods received at warehouse and quality-checked. Step 5: Dispatch/distribution to camps. Step 6: Signed waybill/distribution record filed (last step). | Planned distribution or provision, with beneficiary verification, signed waybill/record, and post-distribution monitoring where applicable. | Camps 1W, 6, 21, 24 | 1,224 children, 2-year supply | R1-I4 | Generates the count of outputs (facilities/people/sessions, as applicable) reported under R1-I4. | 1224 | children | [17 empty] | No data yet | R1A2 (Budget) | R1A2 (Budget) | 193693.01 | 27698100.43 | No Data Log entries yet | During [reporting period], FIVDB delivered: Distribute scholastic material kits (exercise books, ALP books, drawing books, pens, pencils, water bottle, erasers, sharpeners) to enrolled children, 2 shifts per CBLF. (target: 1,224 children, 2-year supply), contributing to indicator 'Number of girls and boys provided with learning materials' (R1-I4). Source: FIVDB Detailed Budget, row 54 (Kits scholastic materials, 24 per CBLF). | Distribution record signed by recipients | FIVDB Detailed Budget, row 54 (Kits scholastic materials, 24 per CBLF) | Education Officer | 12 children x 2 shifts = 24 per CBLF x 51 CBLF = 1,224; BDT 1,500/child/2yrs = 3,672,000. Note: source comment mentions '24*60=1440' as a leftover reference to an earlier 60-CBLF draft - the Qty field (1,224) and the confirmed 51-CBLF total are authoritative.
Result 1 | R1A2 | R1A2.4 | Distribute one school bag per enrolled child (one-time distribution). | Step 1: Raise PR for school bags (Purchase Request). Step 2: PR approval by Project Manager/Finance. Step 3: Procurement/vendor selection per FIVDB procurement policy. Step 4: Goods received at warehouse and quality-checked. Step 5: Dispatch/distribution to camps. Step 6: Signed waybill/distribution record filed (last step). | Planned distribution or provision, with beneficiary verification, signed waybill/record, and post-distribution monitoring where applicable. | Camps 1W, 6, 21, 24 | 1,224 children, one-time | R1-I4 | Generates the count of outputs (facilities/people/sessions, as applicable) reported under R1-I4. | 1224 | children | [17 empty] | No data yet | R1A2 (Budget) | R1A2 (Budget) | 193693.01 | 27698100.43 | No Data Log entries yet | During [reporting period], FIVDB delivered: Distribute one school bag per enrolled child (one-time distribution). (target: 1,224 children, one-time), contributing to indicator 'Number of girls and boys provided with learning materials' (R1-I4). Source: FIVDB Detailed Budget, row 55 (Bag, provided only once). | Distribution record signed by recipients | FIVDB Detailed Budget, row 55 (Bag, provided only once) | Education Officer | BDT 800/child = 979,200.
Result 1 | R1A2 | R1A2.5 | Provide assistive devices and reasonable accommodation for children with disabilities (device cost only; assessment carried out by HI). | Step 1: Raise PR for assistive devices (Purchase Request). Step 2: PR approval by Project Manager/Finance. Step 3: Procurement/vendor selection per FIVDB procurement policy. Step 4: Goods received at warehouse and quality-checked. Step 5: Dispatch/distribution to camps. Step 6: Signed waybill/distribution record filed (last step). | Delivered as a planned field activity by FIVDB staff/volunteers, following the sub-activity description, with progress recorded in this tracker. | Camps 1W, 6, 21, 24 | ~37 children (3% of 1,224) | R1-I4 | Generates the count of outputs (facilities/people/sessions, as applicable) reported under R1-I4. | 37 | children | [17 empty] | No data yet | R1A2 (Budget) | R1A2 (Budget) | 193693.01 | 27698100.43 | No Data Log entries yet | During [reporting period], FIVDB delivered: Provide assistive devices and reasonable accommodation for children with disabilities (device cost only; assessment carried out by HI). (target: ~37 children (3% of 1,224)), contributing to indicator 'Number of girls and boys provided with learning materials' (R1-I4). Source: FIVDB Detailed Budget, row 56 (Assistive devices and reasonable accommodation). | Distribution record; HI assessment reference | FIVDB Detailed Budget, row 56 (Assistive devices and reasonable accommodation) | Education Officer | BDT 10,000/child average lumpsum x 36.72 = 367,200.
Result 1 | R1A2 | R1A2.6 | Provide the CBLF minimum package (floor mats, whiteboards, boxes, stationery, cleaning materials). | Step 1: Raise PR for CBLF minimum package items (Purchase Request). Step 2: PR approval by Project Manager/Finance. Step 3: Procurement/vendor selection per FIVDB procurement policy. Step 4: Goods received at warehouse and quality-checked. Step 5: Dispatch/distribution to camps. Step 6: Signed waybill/distribution record filed (last step). | Delivered as a planned field activity by FIVDB staff/volunteers, following the sub-activity description, with progress recorded in this tracker. | Camps 1W, 6, 21, 24 | 51 CBLFs, 2-year supply | R1-I2 | Generates the count of outputs (facilities/people/sessions, as applicable) reported under R1-I2. | 51 | facilities | [17 empty] | No data yet | R1A2 (Budget) | R1A2 (Budget) | 193693.01 | 27698100.43 | No Data Log entries yet | During [reporting period], FIVDB delivered: Provide the CBLF minimum package (floor mats, whiteboards, boxes, stationery, cleaning materials). (target: 51 CBLFs, 2-year supply), contributing to indicator 'Number of learning spaces established or restored to minimum standards for safe learning' (R1-I2). Source: FIVDB Detailed Budget, row 57 (Minimum package). | Facility inventory / handover record | FIVDB Detailed Budget, row 57 (Minimum package) | Education Officer | BDT 5,000/CBLF/2yrs = 510,000.
Result 1 | R1A2 | R1A2.7 | Install solar panels, lighting and fire extinguishers at all CBLFs. | Step 1: Raise PR for solar panels/lights/fire extinguishers (Purchase Request). Step 2: PR approval by Project Manager/Finance. Step 3: Procurement/vendor selection per FIVDB procurement policy. Step 4: Goods received at warehouse and quality-checked. Step 5: Dispatch/distribution to camps. Step 6: Signed waybill/distribution record filed (last step). | Delivered as a planned field activity by FIVDB staff/volunteers, following the sub-activity description, with progress recorded in this tracker. | Camps 1W, 6, 21, 24 | 51 CBLFs, one-time | R1-I2 | Generates the count of outputs (facilities/people/sessions, as applicable) reported under R1-I2. | 51 | facilities | [17 empty] | No data yet | R1A2 (Budget) | R1A2 (Budget) | 193693.01 | 27698100.43 | No Data Log entries yet | During [reporting period], FIVDB delivered: Install solar panels, lighting and fire extinguishers at all CBLFs. (target: 51 CBLFs, one-time), contributing to indicator 'Number of learning spaces established or restored to minimum standards for safe learning' (R1-I2). Source: FIVDB Detailed Budget, row 58 (Solar panels, lights, fire extinguisher). | Installation/handover certificate; site photos | FIVDB Detailed Budget, row 58 (Solar panels, lights, fire extinguisher) | Education Officer | BDT 25,000/CBLF one-time = 1,275,000.
Result 1 | R1A2 | R1A2.8 | Cover ongoing CBLF maintenance costs. |  | Delivered as a planned field activity by FIVDB staff/volunteers, following the sub-activity description, with progress recorded in this tracker. | Camps 1W, 6, 21, 24 | 51 CBLFs, half-yearly x4 | R1-I2 | Generates the count of outputs (facilities/people/sessions, as applicable) reported under R1-I2. | 51 | facilities | [17 empty] | No data yet | R1A2 (Budget) | R1A2 (Budget) | 193693.01 | 27698100.43 | No Data Log entries yet | During [reporting period], FIVDB delivered: Cover ongoing CBLF maintenance costs. (target: 51 CBLFs, half-yearly x4), contributing to indicator 'Number of learning spaces established or restored to minimum standards for safe learning' (R1-I2). Source: FIVDB Detailed Budget, row 59 (Maintenance costs for CBLF). | Maintenance log; expenditure record | FIVDB Detailed Budget, row 59 (Maintenance costs for CBLF) | Education Officer | BDT 1,000/CBLF x 4 half-year periods = 204,000.
Result 1 | R1A2 | R1A2.9 | Produce and display IEC materials (safeguarding, child protection, PSHEA posters) at all CBLFs. | Step 1: Raise PR for IEC material printing (Purchase Request). Step 2: PR approval by Project Manager/Finance. Step 3: Procurement/vendor selection per FIVDB procurement policy. Step 4: Goods received at warehouse and quality-checked. Step 5: Dispatch/distribution to camps. Step 6: Signed waybill/distribution record filed (last step). | Delivered as a planned field activity by FIVDB staff/volunteers, following the sub-activity description, with progress recorded in this tracker. | Camps 1W, 6, 21, 24 | 51 CBLFs, one-time | GEN-3 | Generates the count of outputs (facilities/people/sessions, as applicable) reported under GEN-3. | 51 | facilities | [17 empty] | No data yet | R1A2 (Budget) | R1A2 (Budget) | 193693.01 | 27698100.43 | No Data Log entries yet | During [reporting period], FIVDB delivered: Produce and display IEC materials (safeguarding, child protection, PSHEA posters) at all CBLFs. (target: 51 CBLFs, one-time), contributing to indicator '' (GEN-3). Source: FIVDB Detailed Budget, row 60 (IEC materials). | Site inspection; photo record | FIVDB Detailed Budget, row 60 (IEC materials) | Education Officer | BDT 1,500/CBLF one-time = 76,500.
Result 1 | R1A2 | R1A2.10 | Provide teacher kits (diary, pens, water bottle, teacher's guide). | Step 1: Raise PR for teacher kit items (diary/pens/bottle/guide) (Purchase Request). Step 2: PR approval by Project Manager/Finance. Step 3: Procurement/vendor selection per FIVDB procurement policy. Step 4: Goods received at warehouse and quality-checked. Step 5: Dispatch/distribution to camps. Step 6: Signed waybill/distribution record filed (last step). | Planned distribution or provision, with beneficiary verification, signed waybill/record, and post-distribution monitoring where applicable. | Camps 1W, 6, 21, 24 | 68 teachers, 2-year supply | R1-I3 | Generates the count of outputs (facilities/people/sessions, as applicable) reported under R1-I3. | 68 | teachers | [17 empty] | No data yet | R1A2 (Budget) | R1A2 (Budget) | 193693.01 | 27698100.43 | No Data Log entries yet | During [reporting period], FIVDB delivered: Provide teacher kits (diary, pens, water bottle, teacher's guide). (target: 68 teachers, 2-year supply), contributing to indicator 'Number of teachers provided with teaching aids/materials' (R1-I3). Source: FIVDB Detailed Budget, row 61 (Teacher kits: diary, pens, water bottle, guide). | Distribution record signed by recipients | FIVDB Detailed Budget, row 61 (Teacher kits: diary, pens, water bottle, guide) | Education Officer | BDT 1,000/teacher/2yrs = 136,000.
Result 1 | R1A2 | R1A2.11 | Provide teacher kits (bag and umbrella), annual distribution. | Step 1: Raise PR for teacher bags/umbrellas (Purchase Request). Step 2: PR approval by Project Manager/Finance. Step 3: Procurement/vendor selection per FIVDB procurement policy. Step 4: Goods received at warehouse and quality-checked. Step 5: Dispatch/distribution to camps. Step 6: Signed waybill/distribution record filed (last step). | Planned distribution or provision, with beneficiary verification, signed waybill/record, and post-distribution monitoring where applicable. | Camps 1W, 6, 21, 24 | 68 teachers, annual | R1-I3 | Generates the count of outputs (facilities/people/sessions, as applicable) reported under R1-I3. | 68 | teachers | [17 empty] | No data yet | R1A2 (Budget) | R1A2 (Budget) | 193693.01 | 27698100.43 | No Data Log entries yet | During [reporting period], FIVDB delivered: Provide teacher kits (bag and umbrella), annual distribution. (target: 68 teachers, annual), contributing to indicator 'Number of teachers provided with teaching aids/materials' (R1-I3). Source: FIVDB Detailed Budget, row 62 (Teacher kits: bag + umbrella). | Distribution record signed by recipients | FIVDB Detailed Budget, row 62 (Teacher kits: bag + umbrella) | Education Officer | BDT 1,400/teacher/year = 95,200.
R1A3 - Gender-Appropriate Dignity Kits & MHM Support for Adolescent Girls (Budget Ref R1A3, BDT 2,460,240 / EUR 17,204.48)
Result 1 | R1A3 | R1A3.1 | Distribute standard MHM kits (reusable pads, underwear, laundry soap) to adolescent girls. | Step 1: Raise PR for MHM kit items (Purchase Request). Step 2: PR approval by Project Manager/Finance. Step 3: Procurement/vendor selection per FIVDB procurement policy. Step 4: Goods received at warehouse and quality-checked. Step 5: Dispatch/distribution to camps. Step 6: Signed waybill/distribution record filed (last step). | Planned distribution or provision, with beneficiary verification, signed waybill/record, and post-distribution monitoring where applicable. | Camps 1W, 6, 21, 24 | ~820 girls, 2-year supply | R1-I4 | Generates the count of outputs (facilities/people/sessions, as applicable) reported under R1-I4. | 820 | girls | [17 empty] | No data yet | R1A3 (Budget) | R1A3 (Budget) | 17204.48 | 2460240.64 | No Data Log entries yet | During [reporting period], FIVDB delivered: Distribute standard MHM kits (reusable pads, underwear, laundry soap) to adolescent girls. (target: ~820 girls, 2-year supply), contributing to indicator 'Number of girls and boys provided with learning materials' (R1-I4). Source: FIVDB Detailed Budget, row 66 (Standard MHM kits with reusable pads, underwear, laundry soap). | Distribution record signed by recipients/guardians | FIVDB Detailed Budget, row 66 (Standard MHM kits with reusable pads, underwear, laundry soap) | Education Officer | BDT 1,500/girl/2yrs x 820.08 = 2,460,240 (~67% of 1,224 children, FIVDB calculation).
R1A4 - Strengthening Technical & Operational Capacities of Staff, Teaching Volunteers & Consortium Partners (Budget Ref R1A4, BDT 1,248,000 / EUR 8,727.27)
Result 1 | R1A4 | R1A4.1 | Deliver the 5-day basic training for teaching volunteers (once every 2 years, TiCC-aligned, CBLF-based). |  | Facilitated in-person training/workshop with a structured curriculum, attendance record, and pre/post assessment where applicable. | Camps 1W, 6, 21, 24 | 68 participants, 5 days | R1-I5 | Generates the count of outputs (facilities/people/sessions, as applicable) reported under R1-I5. | 68 | participants | [17 empty] | No data yet | R1A4 (Budget) | R1A4 (Budget) | 8727.27 | 1247999.61 | No Data Log entries yet | During [reporting period], FIVDB delivered: Deliver the 5-day basic training for teaching volunteers (once every 2 years, TiCC-aligned, CBLF-based). (target: 68 participants, 5 days), contributing to indicator 'Number of teachers/education personnel showing increased knowledge and teaching skills to address children's learning needs' (R1-I5). Source: FIVDB Detailed Budget, rows 69-71 (Cascade down basic training). | Training register; pre/post test | FIVDB Detailed Budget, rows 69-71 (Cascade down basic training) | Education Officer | Food BDT 350 x 68 x 5 days = 119,000; materials 1,500.
Result 1 | R1A4 | R1A4.2 | Deliver the 6-day subject-based (ALP curriculum) training for teaching volunteers. |  | Facilitated in-person training/workshop with a structured curriculum, attendance record, and pre/post assessment where applicable. | Camps 1W, 6, 21, 24 | 68 participants, 12 days total | R1-I5 | Generates the count of outputs (facilities/people/sessions, as applicable) reported under R1-I5. | 68 | participants | [17 empty] | No data yet | R1A4 (Budget) | R1A4 (Budget) | 8727.27 | 1247999.61 | No Data Log entries yet | During [reporting period], FIVDB delivered: Deliver the 6-day subject-based (ALP curriculum) training for teaching volunteers. (target: 68 participants, 12 days total), contributing to indicator 'Number of teachers/education personnel showing increased knowledge and teaching skills to address children's learning needs' (R1-I5). Source: FIVDB Detailed Budget, rows 72-74 (Cascade down subject-based training). | Training register; pre/post test | FIVDB Detailed Budget, rows 72-74 (Cascade down subject-based training) | Education Officer | Food BDT 350 x 68 x 12 days = 285,600; materials 3,000 (2 rounds).
Result 1 | R1A4 | R1A4.3 | Deliver quarterly refresher training for project personnel and teaching volunteers within the CBLF. |  | Facilitated in-person training/workshop with a structured curriculum, attendance record, and pre/post assessment where applicable. | Camps 1W, 6, 21, 24 | 68 participants, 7 days/year | R1-I5 | Generates the count of outputs (facilities/people/sessions, as applicable) reported under R1-I5. | 68 | participants | [17 empty] | No data yet | R1A4 (Budget) | R1A4 (Budget) | 8727.27 | 1247999.61 | No Data Log entries yet | During [reporting period], FIVDB delivered: Deliver quarterly refresher training for project personnel and teaching volunteers within the CBLF. (target: 68 participants, 7 days/year), contributing to indicator 'Number of teachers/education personnel showing increased knowledge and teaching skills to address children's learning needs' (R1-I5). Source: FIVDB Detailed Budget, rows 75-77 (Quarterly refresher training). | Training register; pre/post test | FIVDB Detailed Budget, rows 75-77 (Quarterly refresher training) | Education Officer | Food BDT 350 x 68 x 7 days = 166,600; materials 7,000 (7 rounds).
Result 1 | R1A4 | R1A4.4 | Deliver cascading training for teachers on PSS, gender, SRHR, CAAFAG and referral mechanisms. |  | Facilitated in-person training/workshop with a structured curriculum, attendance record, and pre/post assessment where applicable. | Camps 1W, 6, 21, 24 | 68 participants, 4 days | R1-I7 | Generates the count of outputs (facilities/people/sessions, as applicable) reported under R1-I7. | 68 | participants | [17 empty] | No data yet | R1A4 (Budget) | R1A4 (Budget) | 8727.27 | 1247999.61 | No Data Log entries yet | During [reporting period], FIVDB delivered: Deliver cascading training for teachers on PSS, gender, SRHR, CAAFAG and referral mechanisms. (target: 68 participants, 4 days), contributing to indicator 'Number of teachers and other education personnel showing increased knowledge and skills to address the protection needs of girls and boys' (R1-I7). Source: FIVDB Detailed Budget, rows 78-80 (Cascading training PSS/gender/SRHR/CAAFAG/referral). | Training register; pre/post test | FIVDB Detailed Budget, rows 78-80 (Cascading training PSS/gender/SRHR/CAAFAG/referral) | Education Officer | Food BDT 350 x 68 x 4 days = 95,200; materials 6,000.
Result 1 | R1A4 | R1A4.5 | Deliver the 2-day cascade training on Protective Education Services for teaching volunteers. |  | Facilitated in-person training/workshop with a structured curriculum, attendance record, and pre/post assessment where applicable. | Camps 1W, 6, 21, 24 | 68 participants, 2 days | R1-I7 | Generates the count of outputs (facilities/people/sessions, as applicable) reported under R1-I7. | 68 | participants | [17 empty] | No data yet | R1A4 (Budget) | R1A4 (Budget) | 8727.27 | 1247999.61 | No Data Log entries yet | During [reporting period], FIVDB delivered: Deliver the 2-day cascade training on Protective Education Services for teaching volunteers. (target: 68 participants, 2 days), contributing to indicator 'Number of teachers and other education personnel showing increased knowledge and skills to address the protection needs of girls and boys' (R1-I7). Source: FIVDB Detailed Budget, rows 81-83 (Cascade training Protective Education Services). | Training register; pre/post test | FIVDB Detailed Budget, rows 81-83 (Cascade training Protective Education Services) | Education Officer | Food BDT 350 x 68 x 2 days = 47,600; materials 1,000.
Result 1 | R1A4 | R1A4.6 | Deliver ToT on Gender-Responsive Pedagogy for Inclusive and Gender-Responsive Learning (staff). |  | Facilitated in-person training/workshop with a structured curriculum, attendance record, and pre/post assessment where applicable. | Camps 1W, 6, 21, 24 | 15 participants, 2 days | R1-I5, GEN-4 | Generates the count of outputs (facilities/people/sessions, as applicable) reported under R1-I5, GEN-4. | 15 | participants | [17 empty] | No data yet | R1A4 (Budget) | R1A4 (Budget) | 8727.27 | 1247999.61 | No Data Log entries yet | During [reporting period], FIVDB delivered: Deliver ToT on Gender-Responsive Pedagogy for Inclusive and Gender-Responsive Learning (staff). (target: 15 participants, 2 days), contributing to indicator 'Number of teachers/education personnel showing increased knowledge and teaching skills to address children's learning needs' (R1-I5, GEN-4). Source: FIVDB Detailed Budget, rows 84-87 (ToT Gender-Responsive Pedagogy). | Training register; pre/post test | FIVDB Detailed Budget, rows 84-87 (ToT Gender-Responsive Pedagogy) | Education Officer | Venue + food BDT 600 x 15 x 2 days = 18,000; materials 1,000.
Result 1 | R1A4 | R1A4.7 | Cascade the Gender-Responsive Pedagogy training from staff ToT to all teaching volunteers. |  | Facilitated in-person training/workshop with a structured curriculum, attendance record, and pre/post assessment where applicable. | Camps 1W, 6, 21, 24 | 68 participants, 1 day | R1-I5, GEN-4 | Generates the count of outputs (facilities/people/sessions, as applicable) reported under R1-I5, GEN-4. | 68 | participants | [17 empty] | No data yet | R1A4 (Budget) | R1A4 (Budget) | 8727.27 | 1247999.61 | No Data Log entries yet | During [reporting period], FIVDB delivered: Cascade the Gender-Responsive Pedagogy training from staff ToT to all teaching volunteers. (target: 68 participants, 1 day), contributing to indicator 'Number of teachers/education personnel showing increased knowledge and teaching skills to address children's learning needs' (R1-I5, GEN-4). Source: FIVDB Detailed Budget, rows 88-90 (Cascading Gender-Responsive Pedagogy training, roll out). | Training register; pre/post test | FIVDB Detailed Budget, rows 88-90 (Cascading Gender-Responsive Pedagogy training, roll out) | Education Officer | Food BDT 350 x 68 = 23,800; materials 6,000 (4 rounds).
Result 1 | R1A4 | R1A4.8 | Deliver ToT on Empowerment: Decision-Making and Resilience for Rohingya Women and Adolescent Girls (staff). |  | Facilitated in-person training/workshop with a structured curriculum, attendance record, and pre/post assessment where applicable. | Camps 1W, 6, 21, 24 | 12 participants, 1 day | GEN-4 | Generates the count of outputs (facilities/people/sessions, as applicable) reported under GEN-4. | 12 | participants | [17 empty] | No data yet | R1A4 (Budget) | R1A4 (Budget) | 8727.27 | 1247999.61 | No Data Log entries yet | During [reporting period], FIVDB delivered: Deliver ToT on Empowerment: Decision-Making and Resilience for Rohingya Women and Adolescent Girls (staff). (target: 12 participants, 1 day), contributing to indicator '' (GEN-4). Source: FIVDB Detailed Budget, rows 91-94 (ToT Empowerment session). | Training register; pre/post test | FIVDB Detailed Budget, rows 91-94 (ToT Empowerment session) | Education Officer | Venue + food BDT 600 x 12 = 7,200; materials 1,000.
Result 1 | R1A4 | R1A4.9 | Cascade the Empowerment/Decision-Making/Resilience session from staff ToT to teaching volunteers. |  | Facilitated in-person training/workshop with a structured curriculum, attendance record, and pre/post assessment where applicable. | Camps 1W, 6, 21, 24 | 68 participants, 1 day | GEN-4 | Generates the count of outputs (facilities/people/sessions, as applicable) reported under GEN-4. | 68 | participants | [17 empty] | No data yet | R1A4 (Budget) | R1A4 (Budget) | 8727.27 | 1247999.61 | No Data Log entries yet | During [reporting period], FIVDB delivered: Cascade the Empowerment/Decision-Making/Resilience session from staff ToT to teaching volunteers. (target: 68 participants, 1 day), contributing to indicator '' (GEN-4). Source: FIVDB Detailed Budget, rows 95-97 (Cascading Empowerment session, roll out). | Training register; pre/post test | FIVDB Detailed Budget, rows 95-97 (Cascading Empowerment session, roll out) | Education Officer | Food BDT 350 x 68 = 23,800; materials 1,500.
Result 1 | R1A4 | R1A4.10 | Hold quarterly Male Allyship and Community Leadership Circles for Gender Justice (camp-based, incl. SC). |  | Delivered as a planned field activity by FIVDB staff/volunteers, following the sub-activity description, with progress recorded in this tracker. | Camps 1W, 6, 21, 24 | 200 male participants, quarterly | GEN-4 | Generates the count of outputs (facilities/people/sessions, as applicable) reported under GEN-4. | 200 | participants | [17 empty] | No data yet | R1A4 (Budget) | R1A4 (Budget) | 8727.27 | 1247999.61 | No Data Log entries yet | During [reporting period], FIVDB delivered: Hold quarterly Male Allyship and Community Leadership Circles for Gender Justice (camp-based, incl. SC). (target: 200 male participants, quarterly), contributing to indicator '' (GEN-4). Source: FIVDB Detailed Budget, rows 98-101 (Male Allyship and Community Leadership Circles, 8 sessions). | Session attendance log | FIVDB Detailed Budget, rows 98-101 (Male Allyship and Community Leadership Circles, 8 sessions) | Technical Coordinator–Protection | Food BDT 350 x 200 = 70,000; materials 1,000; 8 sessions total incl. SC co-delivery.
Result 1 | R1A4 | R1A4.11 | Deliver ToT on Gender Equality in Education for field staff, facilitators and consortium partners. |  | Facilitated in-person training/workshop with a structured curriculum, attendance record, and pre/post assessment where applicable. | Camps 1W, 6, 21, 24 | 25 participants, 2 days | R1-I5, GEN-4 | Generates the count of outputs (facilities/people/sessions, as applicable) reported under R1-I5, GEN-4. | 25 | participants | [17 empty] | No data yet | R1A4 (Budget) | R1A4 (Budget) | 8727.27 | 1247999.61 | No Data Log entries yet | During [reporting period], FIVDB delivered: Deliver ToT on Gender Equality in Education for field staff, facilitators and consortium partners. (target: 25 participants, 2 days), contributing to indicator 'Number of teachers/education personnel showing increased knowledge and teaching skills to address children's learning needs' (R1-I5, GEN-4). Source: FIVDB Detailed Budget, rows 102-105 (ToT Gender Equality in Education). | Training register; pre/post test | FIVDB Detailed Budget, rows 102-105 (ToT Gender Equality in Education) | Education Officer | Venue + food BDT 600 x 25 x 2 days = 30,000; materials 2,000.
Result 1 | R1A4 | R1A4.12 | Cascade the Gender Equality in Education training from ToT to field staff/facilitators. |  | Facilitated in-person training/workshop with a structured curriculum, attendance record, and pre/post assessment where applicable. | Camps 1W, 6, 21, 24 | 68 participants, 4 days | R1-I5, GEN-4 | Generates the count of outputs (facilities/people/sessions, as applicable) reported under R1-I5, GEN-4. | 68 | participants | [17 empty] | No data yet | R1A4 (Budget) | R1A4 (Budget) | 8727.27 | 1247999.61 | No Data Log entries yet | During [reporting period], FIVDB delivered: Cascade the Gender Equality in Education training from ToT to field staff/facilitators. (target: 68 participants, 4 days), contributing to indicator 'Number of teachers/education personnel showing increased knowledge and teaching skills to address children's learning needs' (R1-I5, GEN-4). Source: FIVDB Detailed Budget, rows 106-108 (Cascading Gender Equality in Education, roll out). | Training register; pre/post test | FIVDB Detailed Budget, rows 106-108 (Cascading Gender Equality in Education, roll out) | Education Officer | Food BDT 350 x 68 x 4 days = 95,200; materials 6,000.
Result 1 | R1A4 | R1A4.13 | Facilitate Adolescent Girls' Safe Circles for Leadership and Protection (per centre, peer group). |  | Delivered as a planned field activity by FIVDB staff/volunteers, following the sub-activity description, with progress recorded in this tracker. | Camps 1W, 6, 21, 24 | 22 participants, 1 day | GEN-4, R1-I6 | Generates the count of outputs (facilities/people/sessions, as applicable) reported under GEN-4, R1-I6. | 22 | participants | [17 empty] | No data yet | R1A4 (Budget) | R1A4 (Budget) | 8727.27 | 1247999.61 | No Data Log entries yet | During [reporting period], FIVDB delivered: Facilitate Adolescent Girls' Safe Circles for Leadership and Protection (per centre, peer group). (target: 22 participants, 1 day), contributing to indicator '' (GEN-4, R1-I6). Source: FIVDB Detailed Budget, rows 109-112 (Adolescent Girls' Safe Circles - non-budgetary). | Session attendance log | FIVDB Detailed Budget, rows 109-112 (Adolescent Girls' Safe Circles - non-budgetary) | Education Officer | Marked non-budgetary in source; delivered within existing facilitator time.
Result 1 | R1A4 | R1A4.14 | Hold monthly project progress/coordination meetings. |  | Scheduled meeting or dialogue with the relevant stakeholders, with minutes/attendance recorded and follow-up actions tracked. | Camps 1W, 6, 21, 24 | 15 participants, 24 days/2yrs | - | Enables or supports delivery of other indicator-linked activities; not directly counted under any single IPTT indicator. | 15 | participants | [17 empty] | No data yet | R1A4 (Budget) | R1A4 (Budget) | 8727.27 | 1247999.61 | No Data Log entries yet | During [reporting period], FIVDB delivered: Hold monthly project progress/coordination meetings. (target: 15 participants, 24 days/2yrs). Source: FIVDB Detailed Budget, rows 113-116 (Monthly project progress/coordination meeting). | Meeting minutes; attendance record | FIVDB Detailed Budget, rows 113-116 (Monthly project progress/coordination meeting) | Project Manager | Venue + food BDT 600 x 15 x 24 = 216,000; materials 12,000 (24 rounds).
R1A5 - Community Engagement, CESG Oversight, Caregiver Support & SEL (Budget Ref R1A5, BDT 1,095,160 / EUR 7,658.46)
Result 1 | R1A5 | R1A5.1 | Provide SEL storybooks to CBLFs to ensure a joyful learning environment. |  | Delivered as a planned field activity by FIVDB staff/volunteers, following the sub-activity description, with progress recorded in this tracker. | Camps 1W, 6, 21, 24 | 67 copies, one-time | R1-I6 | Generates the count of outputs (facilities/people/sessions, as applicable) reported under R1-I6. | 67 | copies | [17 empty] | No data yet | R1A5 (Budget) | R1A5 (Budget) | 7658.46 | 1095159.78 | No Data Log entries yet | During [reporting period], FIVDB delivered: Provide SEL storybooks to CBLFs to ensure a joyful learning environment. (target: 67 copies, one-time), contributing to indicator 'Number of students, teachers and other education personnel provided with psycho-social support services' (R1-I6). Source: FIVDB Detailed Budget, rows 118-119 (Storybook on SEL, printing module). | Distribution record; facility inventory | FIVDB Detailed Budget, rows 118-119 (Storybook on SEL, printing module) | Education Officer | BDT 1,000/copy x 67 = 67,000. CLARIFICATION: Target = 67 storybook copies (a one-time print/distribution output), not the 2,516 beneficiary figure on indicator R1-I6 that this activity contributes to alongside R1A4.14 (parenting sessions) and others.
Result 1 | R1A5 | R1A5.2 | Hold bi-monthly CESG meetings (7-8 members per CESG, 1 CESG per 2 CBLFs). |  | Scheduled meeting or dialogue with the relevant stakeholders, with minutes/attendance recorded and follow-up actions tracked. | Camps 1W, 6, 21, 24 | 204 persons, 12 sessions/2yrs | SO-I1 | Generates the count of outputs (facilities/people/sessions, as applicable) reported under SO-I1. | 204 | persons | [17 empty] | No data yet | R1A5 (Budget) | R1A5 (Budget) | 7658.46 | 1095159.78 | No Data Log entries yet | During [reporting period], FIVDB delivered: Hold bi-monthly CESG meetings (7-8 members per CESG, 1 CESG per 2 CBLFs). (target: 204 persons, 12 sessions/2yrs), contributing to indicator '% of beneficiaries reporting that humanitarian assistance is delivered in a safe, accessible, accountable and participatory manner' (SO-I1). Source: FIVDB Detailed Budget, rows 122-123 (Bi-monthly CESG meetings, snacks). | Meeting minutes; attendance record | FIVDB Detailed Budget, rows 122-123 (Bi-monthly CESG meetings, snacks) | Education Officer | Snacks BDT 60/person x 204 x 12 = 146,880; ~26 CESGs.
Result 1 | R1A5 | R1A5.3 | Hold bi-monthly parent/caregiver engagement meetings (1 parent per enrolled child). |  | Scheduled meeting or dialogue with the relevant stakeholders, with minutes/attendance recorded and follow-up actions tracked. | Camps 1W, 6, 21, 24 | 1,224 persons, 12 sessions/2yrs | SO-I1 | Generates the count of outputs (facilities/people/sessions, as applicable) reported under SO-I1. | 1224 | persons | [17 empty] | No data yet | R1A5 (Budget) | R1A5 (Budget) | 7658.46 | 1095159.78 | No Data Log entries yet | During [reporting period], FIVDB delivered: Hold bi-monthly parent/caregiver engagement meetings (1 parent per enrolled child). (target: 1,224 persons, 12 sessions/2yrs), contributing to indicator '% of beneficiaries reporting that humanitarian assistance is delivered in a safe, accessible, accountable and participatory manner' (SO-I1). Source: FIVDB Detailed Budget, rows 126-127 (Bi-monthly parent meetings, snacks). | Meeting minutes; attendance record | FIVDB Detailed Budget, rows 126-127 (Bi-monthly parent meetings, snacks) | Education Officer | Snacks BDT 60/person x 1,224 x 12 = 881,280.
R2A1 - Child Protection Case Management (Budget Ref R2A1, BDT 1,963,000 / EUR 13,727.27)
Result 2 | R2A1 | R2A1.1 | Identify and enhance the capacity of alternative-care family members (foster and kinship) for unaccompanied/separated children (UASC). |  | Individual identification, intake/assessment, case planning, service delivery and follow-up, per the CP Case Management Minimum Standards 7-step process. | Camps 1W, 6, 21, 24 | 12 participants, 3-day training | R2-I2 | Generates the count of outputs (facilities/people/sessions, as applicable) reported under R2-I2. | 12 | participants | [17 empty] | No data yet | R2A1 (Budget) | R2A1 (Budget) | 13727.27 | 1962999.61 | No Data Log entries yet | During [reporting period], FIVDB delivered: Identify and enhance the capacity of alternative-care family members (foster and kinship) for unaccompanied/separated children (UASC). (target: 12 participants, 3-day training), contributing to indicator '% of children separated from or allegedly associated with armed groups and armed forces who benefit from appropriate care and services' (R2-I2). Source: FIVDB Detailed Budget, rows 131-136 (2.1.1 Identifying and enhancing capacity of alternative care family members). | Training register; case file cross-check | FIVDB Detailed Budget, rows 131-136 (2.1.1 Identifying and enhancing capacity of alternative care family members) | Technical Coordinator–Protection | Venue 45,000; refreshment 54,000; materials 6,000; accommodation 48,000; travel 24,000.
Result 2 | R2A1 | R2A1.2 | Provide case-management need-based and emergency support (NFIs) to children/families in active cases. |  | Individual identification, intake/assessment, case planning, service delivery and follow-up, per the CP Case Management Minimum Standards 7-step process. | Camps 1W, 6, 21, 24 | 320 children, needs-based | R2-I1 | Generates the count of outputs (facilities/people/sessions, as applicable) reported under R2-I1. | 320 | children | [17 empty] | No data yet | R2A1 (Budget) | R2A1 (Budget) | 13727.27 | 1962999.61 | No Data Log entries yet | During [reporting period], FIVDB delivered: Provide case-management need-based and emergency support (NFIs) to children/families in active cases. (target: 320 children, needs-based), contributing to indicator '(MANDATORY) % of children and caregivers whose urgent child protection needs/risks have been addressed through the case management process' (R2-I1). Source: FIVDB Detailed Budget, rows 137-138 (2.1.2 Case management need-based and emergency support). | Case file; distribution record | FIVDB Detailed Budget, rows 137-138 (2.1.2 Case management need-based and emergency support) | Technical Coordinator–Protection | BDT 1,200/case average x 320 = 384,000.
Result 2 | R2A1 | R2A1.3 | Maintain functioning Case Management Offices (1 per camp). |  | Individual identification, intake/assessment, case planning, service delivery and follow-up, per the CP Case Management Minimum Standards 7-step process. | Camps 1W, 6, 21, 24 | 4 camps, one-time set-up + running | R2-I1 | Generates the count of outputs (facilities/people/sessions, as applicable) reported under R2-I1. | 4 | camps | [17 empty] | No data yet | R2A1 (Budget) | R2A1 (Budget) | 13727.27 | 1962999.61 | No Data Log entries yet | During [reporting period], FIVDB delivered: Maintain functioning Case Management Offices (1 per camp). (target: 4 camps, one-time set-up + running), contributing to indicator '(MANDATORY) % of children and caregivers whose urgent child protection needs/risks have been addressed through the case management process' (R2-I1). Source: FIVDB Detailed Budget, row 139 (2.1.3 Case Management Office functioning and running costs). | Office inventory; running-cost record | FIVDB Detailed Budget, row 139 (2.1.3 Case Management Office functioning and running costs) | Technical Coordinator–Protection | BDT 10,000/camp x 4 = 40,000.
Result 2 | R2A1 | R2A1.4 | Deliver case management services per the CPMS 7-step process (non-budgetary - covered by CM Officer/volunteer time). |  | Individual identification, intake/assessment, case planning, service delivery and follow-up, per the CP Case Management Minimum Standards 7-step process. | Camps 1W, 6, 21, 24 | 320 children caseload | R2-I1 | Generates the count of outputs (facilities/people/sessions, as applicable) reported under R2-I1. | 320 | children | [17 empty] | No data yet | R2A1 (Budget) | R2A1 (Budget) | 13727.27 | 1962999.61 | No Data Log entries yet | During [reporting period], FIVDB delivered: Deliver case management services per the CPMS 7-step process (non-budgetary - covered by CM Officer/volunteer time). (target: 320 children caseload), contributing to indicator '(MANDATORY) % of children and caregivers whose urgent child protection needs/risks have been addressed through the case management process' (R2-I1). Source: FIVDB Detailed Budget, row 140 (2.1.4 Case Management Services - non-budgetary). | Case management database | FIVDB Detailed Budget, row 140 (2.1.4 Case Management Services - non-budgetary) | Case Management Officer | Non-budgetary; delivered through the 8 Case Management Officer posts under Human Resources.
Result 2 | R2A1 | R2A1.5 | Train para-social workers, volunteers and facilitators on referral pathways. |  | Inter-sector coordination to define and formalise the referral SOP, tested and monitored through the referral tracker. | Camps 1W, 6, 21, 24 | 20 participants, 1 day | R2-I3 | Generates the count of outputs (facilities/people/sessions, as applicable) reported under R2-I3. | 20 | participants | [17 empty] | No data yet | R2A1 (Budget) | R2A1 (Budget) | 13727.27 | 1962999.61 | No Data Log entries yet | During [reporting period], FIVDB delivered: Train para-social workers, volunteers and facilitators on referral pathways. (target: 20 participants, 1 day), contributing to indicator 'Average % knowledge increase amongst participants on the protection subject in focus' (R2-I3). Source: FIVDB Detailed Budget, rows 141-143 (2.1.5 Training for para-social workers and volunteers on referral pathways). | Training register; pre/post test | FIVDB Detailed Budget, rows 141-143 (2.1.5 Training for para-social workers and volunteers on referral pathways) | Technical Coordinator–Protection | Venue at office (0 cost); refreshment BDT 350 x 20 = 7,000.
Result 2 | R2A1 | R2A1.6 | Provide monthly incentives to case-management volunteers (2 per camp, all refugees) for identification and referral. |  | Individual identification, intake/assessment, case planning, service delivery and follow-up, per the CP Case Management Minimum Standards 7-step process. | Camps 1W, 6, 21, 24 | 8 volunteers x 11 months | R2-I1 | Generates the count of outputs (facilities/people/sessions, as applicable) reported under R2-I1. | 8 | volunteers | [17 empty] | No data yet | R2A1 (Budget) | R2A1 (Budget) | 13727.27 | 1962999.61 | No Data Log entries yet | During [reporting period], FIVDB delivered: Provide monthly incentives to case-management volunteers (2 per camp, all refugees) for identification and referral. (target: 8 volunteers x 11 months), contributing to indicator '(MANDATORY) % of children and caregivers whose urgent child protection needs/risks have been addressed through the case management process' (R2-I1). Source: FIVDB Detailed Budget, row 144 (Incentive for case management volunteers). | Payroll/incentive disbursement record | FIVDB Detailed Budget, row 144 (Incentive for case management volunteers) | Technical Coordinator–Protection | BDT 15,000/volunteer/month x 8 x 11 = 1,320,000.
Result 2 | R2A1 | R2A1.7 | Provide support-material kits (case-worker kits) for case-management service providers. | Step 1: Raise PR for case-worker support kits (Purchase Request). Step 2: PR approval by Project Manager/Finance. Step 3: Procurement/vendor selection per FIVDB procurement policy. Step 4: Goods received at warehouse and quality-checked. Step 5: Dispatch/distribution to camps. Step 6: Signed waybill/distribution record filed (last step). | Planned distribution or provision, with beneficiary verification, signed waybill/record, and post-distribution monitoring where applicable. | Camps 1W, 6, 21, 24 | 10 participants, lumpsum | R2-I1 | Generates the count of outputs (facilities/people/sessions, as applicable) reported under R2-I1. | 10 | participants | [17 empty] | No data yet | R2A1 (Budget) | R2A1 (Budget) | 13727.27 | 1962999.61 | No Data Log entries yet | During [reporting period], FIVDB delivered: Provide support-material kits (case-worker kits) for case-management service providers. (target: 10 participants, lumpsum), contributing to indicator '(MANDATORY) % of children and caregivers whose urgent child protection needs/risks have been addressed through the case management process' (R2-I1). Source: FIVDB Detailed Budget, rows 145-146 (2.1.7 Provision of support kits for case management service providers). | Distribution record | FIVDB Detailed Budget, rows 145-146 (2.1.7 Provision of support kits for case management service providers) | Technical Coordinator–Protection | BDT 3,500/participant x 10 = 35,000.
R2A3 - MPCAC Establishment & PSS/Protection Group Interventions (Budget Ref R2A3, BDT 10,455,800 / EUR 73,117.48)
Result 2 | R2A3 | R2A3.1 | Construct new MPCACs and refurbish existing MPCACs, including running costs. | R2A3.1a: Establish 4 new MPCACs (Camp 1W, Camp 6, Camp 21, Camp 24). ¦ R2A3.1b: Refurbish 2 existing MPCACs (Camp 1W, Camp 24). ¦ R2A3.1c: Cover running/materials costs for all 6 MPCACs. | Site/structure identification, agreement with camp authorities, procurement/construction or formation, and handover or launch. | Camps 1W, 6, 21, 24 | 4 new + 2 refurbished + 6 running | R2-I4 | Generates the count of outputs (facilities/people/sessions, as applicable) reported under R2-I4. | 4 | facilities | [17 empty] | No data yet | R2A3 (Budget) | R2A3 (Budget) | 73117.48 | 10455799.64 | No Data Log entries yet | During [reporting period], FIVDB delivered: Construct new MPCACs and refurbish existing MPCACs, including running costs. (target: 4 new + 2 refurbished + 6 running), contributing to indicator '(MANDATORY) % of persons who receive appropriate PSS reporting improved mental health and psychosocial well-being OR capacities to cope' (R2-I4). Source: FIVDB Detailed Budget, rows 150-153 (2.3.1 Construction and/or refurbishment of MPCAC). | Completion/handover certificate; site photos | FIVDB Detailed Budget, rows 150-153 (2.3.1 Construction and/or refurbishment of MPCAC) | Technical Coordinator–Protection | New BDT 850,000 x 4 = 3,400,000; refurb BDT 200,000 x 2 = 400,000; running BDT 70,000 x 6 = 420,000. Block detail: Camp 1W Blocks A-G, Camp 6 A-D, Camp 21 A-C, Camp 24 A-E, per Annex 3.
Result 2 | R2A3 | R2A3.2 | Roll out 'I Support My Friend' (ISMF) at community level, including inception meeting and adolescent training. |  | Facilitated in-person training/workshop with a structured curriculum, attendance record, and pre/post assessment where applicable. | Camps 1W, 6, 21, 24 | 100 participants, inception + 3-day training | R2-I4 | Generates the count of outputs (facilities/people/sessions, as applicable) reported under R2-I4. | 100 | participants | [17 empty] | No data yet | R2A3 (Budget) | R2A3 (Budget) | 73117.48 | 10455799.64 | No Data Log entries yet | During [reporting period], FIVDB delivered: Roll out 'I Support My Friend' (ISMF) at community level, including inception meeting and adolescent training. (target: 100 participants, inception + 3-day training), contributing to indicator '(MANDATORY) % of persons who receive appropriate PSS reporting improved mental health and psychosocial well-being OR capacities to cope' (R2-I4). Source: FIVDB Detailed Budget, rows 154-156 (2.3.2 Roll out of I Support My Friend at community level). | Session attendance log | FIVDB Detailed Budget, rows 154-156 (2.3.2 Roll out of I Support My Friend at community level) | Technical Coordinator–Protection | Inception BDT 35,000; training BDT 350 x 100 x 3 days = 105,000.
Result 2 | R2A3 | R2A3.3 | Deploy MPCAC facilitators (refugee volunteers, host-community volunteers, security guards) to run PSS/awareness sessions. |  | Facilitated group session(s) with participants, using a structured curriculum/module and attendance tracking. | Camps 1W, 6, 21, 24 | 18 persons (6+6+6) x 11 months | R2-I4 | Generates the count of outputs (facilities/people/sessions, as applicable) reported under R2-I4. | 18 | persons | [17 empty] | No data yet | R2A3 (Budget) | R2A3 (Budget) | 73117.48 | 10455799.64 | No Data Log entries yet | During [reporting period], FIVDB delivered: Deploy MPCAC facilitators (refugee volunteers, host-community volunteers, security guards) to run PSS/awareness sessions. (target: 18 persons (6+6+6) x 11 months), contributing to indicator '(MANDATORY) % of persons who receive appropriate PSS reporting improved mental health and psychosocial well-being OR capacities to cope' (R2-I4). Source: FIVDB Detailed Budget, rows 157-160 (2.3.3 Facilitators of the MPCAC). | Payroll/incentive disbursement record | FIVDB Detailed Budget, rows 157-160 (2.3.3 Facilitators of the MPCAC) | Technical Coordinator–Protection | Refugee volunteers BDT 15,000 x 6 x 11 = 990,000; host volunteers BDT 17,000 x 6 x 11 = 1,122,000; security BDT 10,000 x 6 x 11 = 660,000.
Result 2 | R2A3 | R2A3.4 | Orient and engage proactive Men and Boys in GBV prevention and response (bi-weekly sessions). |  | Facilitated group session(s) with participants, using a structured curriculum/module and attendance tracking. | Camps 1W, 6, 21, 24 | 20 persons/camp x 4 camps, 88 sessions | GEN-4, R2-I4 | Generates the count of outputs (facilities/people/sessions, as applicable) reported under GEN-4, R2-I4. | 20 | persons | [17 empty] | No data yet | R2A3 (Budget) | R2A3 (Budget) | 73117.48 | 10455799.64 | No Data Log entries yet | During [reporting period], FIVDB delivered: Orient and engage proactive Men and Boys in GBV prevention and response (bi-weekly sessions). (target: 20 persons/camp x 4 camps, 88 sessions), contributing to indicator '' (GEN-4, R2-I4). Source: FIVDB Detailed Budget, rows 161-163 (2.3.5 Men and Boys Engagement to prevent and respond to GBV). | Session attendance log | FIVDB Detailed Budget, rows 161-163 (2.3.5 Men and Boys Engagement to prevent and respond to GBV) | Technical Coordinator–Protection | Marked with 0 unit cost in source (in-kind/volunteer-led); orientation + bi-weekly refreshment sessions.
Result 2 | R2A3 | R2A3.5 | Deliver community-led activities on CP and GBV issues (day/event observation). |  | Direct observation/inspection against a standard checklist, with findings recorded and shared for follow-up action. | Camps 1W, 6, 21, 24 | 4 events, 3 times | R2-I4 | Generates the count of outputs (facilities/people/sessions, as applicable) reported under R2-I4. | 4 | events | [17 empty] | No data yet | R2A3 (Budget) | R2A3 (Budget) | 73117.48 | 10455799.64 | No Data Log entries yet | During [reporting period], FIVDB delivered: Deliver community-led activities on CP and GBV issues (day/event observation). (target: 4 events, 3 times), contributing to indicator '(MANDATORY) % of persons who receive appropriate PSS reporting improved mental health and psychosocial well-being OR capacities to cope' (R2-I4). Source: FIVDB Detailed Budget, rows 164-165 (2.3.6 Community led activities on CP & GBV issue). | Event report | FIVDB Detailed Budget, rows 164-165 (2.3.6 Community led activities on CP & GBV issue) | Technical Coordinator–Protection | BDT 20,000/event x 4 x 3 = 240,000.
Result 2 | R2A3 | R2A3.6 | Provide Dignity Kits and Menstrual and Hygiene Management (MHM) kit support to adolescent girls (CP side). | Step 1: Raise PR for dignity/MHM kit items (CP side) (Purchase Request). Step 2: PR approval by Project Manager/Finance. Step 3: Procurement/vendor selection per FIVDB procurement policy. Step 4: Goods received at warehouse and quality-checked. Step 5: Dispatch/distribution to camps. Step 6: Signed waybill/distribution record filed (last step). | Planned distribution or provision, with beneficiary verification, signed waybill/record, and post-distribution monitoring where applicable. | Camps 1W, 6, 21, 24 | 1,814 persons | R2-I4 | Generates the count of outputs (facilities/people/sessions, as applicable) reported under R2-I4. | 1814 | persons | [17 empty] | No data yet | R2A3 (Budget) | R2A3 (Budget) | 73117.48 | 10455799.64 | No Data Log entries yet | During [reporting period], FIVDB delivered: Provide Dignity Kits and Menstrual and Hygiene Management (MHM) kit support to adolescent girls (CP side). (target: 1,814 persons), contributing to indicator '(MANDATORY) % of persons who receive appropriate PSS reporting improved mental health and psychosocial well-being OR capacities to cope' (R2-I4). Source: FIVDB Detailed Budget, rows 166-167 (2.3.7 Dignity/MHM Kit support to adolescent girls). | Distribution record signed by recipients/guardians | FIVDB Detailed Budget, rows 166-167 (2.3.7 Dignity/MHM Kit support to adolescent girls) | Technical Coordinator–Protection | BDT 1,700/person x 1,814 = 3,083,800.
R2A4 - Strengthening Community-Based Protection Mechanisms (Budget Ref R2A4, BDT 11,822,800 / EUR 82,676.92)
Result 2 | R2A4 | R2A4.1 | Deliver DRR & Climate Resilience training for community leaders and volunteers. |  | Facilitated in-person training/workshop with a structured curriculum, attendance record, and pre/post assessment where applicable. | Camps 1W, 6, 21, 24 | 240 persons, 2 days | R2-I3 | Generates the count of outputs (facilities/people/sessions, as applicable) reported under R2-I3. | 240 | persons | [17 empty] | No data yet | R2A4 (Budget) | R2A4 (Budget) | 82676.92 | 11822799.56 | No Data Log entries yet | During [reporting period], FIVDB delivered: Deliver DRR & Climate Resilience training for community leaders and volunteers. (target: 240 persons, 2 days), contributing to indicator 'Average % knowledge increase amongst participants on the protection subject in focus' (R2-I3). Source: FIVDB Detailed Budget, rows 170-173 (2.4.1 Training on DRR & Climate Resilience). | Training register; attendance record | FIVDB Detailed Budget, rows 170-173 (2.4.1 Training on DRR & Climate Resilience) | Technical Coordinator–Protection | Refreshment BDT 350 x 240 x 2 days = 168,000; materials BDT 200 x 240 = 48,000.
Result 2 | R2A4 | R2A4.2 | Deliver PALS sessions for parents and adolescents (10-14 sessions per group). |  | Facilitated group session(s) with participants, using a structured curriculum/module and attendance tracking. | Camps 1W, 6, 21, 24 | 4,320 adolescents + 4,320 caregivers | R2-I4 | Generates the count of outputs (facilities/people/sessions, as applicable) reported under R2-I4. | 4320 | individuals | [17 empty] | No data yet | R2A4 (Budget) | R2A4 (Budget) | 82676.92 | 11822799.56 | No Data Log entries yet | During [reporting period], FIVDB delivered: Deliver PALS sessions for parents and adolescents (10-14 sessions per group). (target: 4,320 adolescents + 4,320 caregivers), contributing to indicator '(MANDATORY) % of persons who receive appropriate PSS reporting improved mental health and psychosocial well-being OR capacities to cope' (R2-I4). Source: FIVDB Detailed Budget, rows 174-178 (2.4.2 Provision of PALS sessions for Parents and Adolescents). | PSS session attendance log | FIVDB Detailed Budget, rows 174-178 (2.4.2 Provision of PALS sessions for Parents and Adolescents) | Technical Coordinator–Protection | 24 refugee PSS volunteers BDT 15,000 x 11 = 3,960,000; printing 50,000; snacks adolescents BDT 50 x 4,320 x 14 = 3,024,000; snacks parents BDT 60 x 4,320 x 10 = 2,592,000.
Result 2 | R2A4 | R2A4.3 | Form/reform CBCPCs and hold monthly/bi-monthly meetings (2 CBCPCs per camp, 17 members each). |  | Scheduled meeting or dialogue with the relevant stakeholders, with minutes/attendance recorded and follow-up actions tracked. | Camps 1W, 6, 21, 24 | 136 members, monthly x10 | R2-I4 | Generates the count of outputs (facilities/people/sessions, as applicable) reported under R2-I4. | 136 | members | [17 empty] | No data yet | R2A4 (Budget) | R2A4 (Budget) | 82676.92 | 11822799.56 | No Data Log entries yet | During [reporting period], FIVDB delivered: Form/reform CBCPCs and hold monthly/bi-monthly meetings (2 CBCPCs per camp, 17 members each). (target: 136 members, monthly x10), contributing to indicator '(MANDATORY) % of persons who receive appropriate PSS reporting improved mental health and psychosocial well-being OR capacities to cope' (R2-I4). Source: FIVDB Detailed Budget, rows 179-181 (2.4.3 CBCPC formation, reformation and monthly/bi-monthly meetings). | Meeting minutes; attendance record | FIVDB Detailed Budget, rows 179-181 (2.4.3 CBCPC formation, reformation and monthly/bi-monthly meetings) | Technical Coordinator–Protection | Refreshment BDT 350 x 136 x 10 = 476,000; protection gear BDT 500 x 136 = 68,000.
Result 2 | R2A4 | R2A4.4 | Deliver 2-day CBCPC member training, twice yearly (2 CBCPCs/camp x 17 members x 4 camps). |  | Facilitated in-person training/workshop with a structured curriculum, attendance record, and pre/post assessment where applicable. | Camps 1W, 6, 21, 24 | 136 members, 2 days x2/year | R2-I3 | Generates the count of outputs (facilities/people/sessions, as applicable) reported under R2-I3. | 136 | members | [17 empty] | No data yet | R2A4 (Budget) | R2A4 (Budget) | 82676.92 | 11822799.56 | No Data Log entries yet | During [reporting period], FIVDB delivered: Deliver 2-day CBCPC member training, twice yearly (2 CBCPCs/camp x 17 members x 4 camps). (target: 136 members, 2 days x2/year), contributing to indicator 'Average % knowledge increase amongst participants on the protection subject in focus' (R2-I3). Source: FIVDB Detailed Budget, rows 182-183 (2.4.4 Training for CBCPC members). | Training register; attendance record | FIVDB Detailed Budget, rows 182-183 (2.4.4 Training for CBCPC members) | Technical Coordinator–Protection | Food and materials BDT 400 x 136 x 2 days = 108,800.
Result 2 | R2A4 | R2A4.5 | Conduct child-protection risk mapping and develop community-led prevention/response/referral plans. |  | Delivered as a planned field activity by FIVDB staff/volunteers, following the sub-activity description, with progress recorded in this tracker. | Camps 1W, 6, 21, 24 | 8 mapping exercises | R2-I4 | Generates the count of outputs (facilities/people/sessions, as applicable) reported under R2-I4. | 8 | mapping | [17 empty] | No data yet | R2A4 (Budget) | R2A4 (Budget) | 82676.92 | 11822799.56 | No Data Log entries yet | During [reporting period], FIVDB delivered: Conduct child-protection risk mapping and develop community-led prevention/response/referral plans. (target: 8 mapping exercises), contributing to indicator '(MANDATORY) % of persons who receive appropriate PSS reporting improved mental health and psychosocial well-being OR capacities to cope' (R2-I4). Source: FIVDB Detailed Budget, rows 184-185 (2.4.5 Child protection risk mapping). | Risk map; community action plan | FIVDB Detailed Budget, rows 184-185 (2.4.5 Child protection risk mapping) | Technical Coordinator–Protection | Refreshment/materials BDT 8,000/mapping x 8 x 2 = 128,000.
Result 2 | R2A4 | R2A4.6 | Deliver Art for Awareness - Interactive Popular Theatre (IPT) and puppet shows for CP & GBV behaviour change. |  | Community-facing awareness or engagement activity delivered at facility or camp level, with attendance/participation recorded. | Camps 1W, 6, 21, 24 | 4 events | R2-I4 | Generates the count of outputs (facilities/people/sessions, as applicable) reported under R2-I4. | 4 | events | [17 empty] | No data yet | R2A4 (Budget) | R2A4 (Budget) | 82676.92 | 11822799.56 | No Data Log entries yet | During [reporting period], FIVDB delivered: Deliver Art for Awareness - Interactive Popular Theatre (IPT) and puppet shows for CP & GBV behaviour change. (target: 4 events), contributing to indicator '(MANDATORY) % of persons who receive appropriate PSS reporting improved mental health and psychosocial well-being OR capacities to cope' (R2-I4). Source: FIVDB Detailed Budget, rows 186-191 (2.4.6 Art for Awareness - IPT and Puppet for CP & GBV). | Event report; audience attendance log | FIVDB Detailed Budget, rows 186-191 (2.4.6 Art for Awareness - IPT and Puppet for CP & GBV) | Technical Coordinator–Protection | Script workshop 120,000; development workshop 200,000; props/costumes 120,000; facilitator 280,000; performance/dissemination 480,000.
R2A5 - Capacity Building for Frontline Staff & Volunteers on CP-GBV Integration (Budget Ref R2A5, BDT 295,200 / EUR 2,064.34)
Result 2 | R2A5 | R2A5.1 | Deliver capacity-enhancing training for other-sector staff (health, education, nutrition, WASH) on CP integration and case-referral systems. |  | Facilitated in-person training/workshop with a structured curriculum, attendance record, and pre/post assessment where applicable. | Camps 1W, 6, 21, 24 | 25 participants, 1 day | R2-I3 | Generates the count of outputs (facilities/people/sessions, as applicable) reported under R2-I3. | 25 | participants | [17 empty] | No data yet | R2A5 (Budget) | R2A5 (Budget) | 2064.34 | 295200.62 | No Data Log entries yet | During [reporting period], FIVDB delivered: Deliver capacity-enhancing training for other-sector staff (health, education, nutrition, WASH) on CP integration and case-referral systems. (target: 25 participants, 1 day), contributing to indicator 'Average % knowledge increase amongst participants on the protection subject in focus' (R2-I3). Source: FIVDB Detailed Budget, rows 194-197 (2.5.9 Capacity enhancing training for other sector staff). | Training register; attendance record | FIVDB Detailed Budget, rows 194-197 (2.5.9 Capacity enhancing training for other sector staff) | Technical Coordinator–Protection | Venue 20,000; refreshment BDT 1,500 x 25 = 37,500; materials BDT 300 x 25 = 7,500.
Result 2 | R2A5 | R2A5.2 | Hold quarterly coordination meetings with camp service providers (CiC and relevant stakeholders). |  | Scheduled meeting or dialogue with the relevant stakeholders, with minutes/attendance recorded and follow-up actions tracked. | Camps 1W, 6, 21, 24 | 4 camps, quarterly x2 | - | Enables or supports delivery of other indicator-linked activities; not directly counted under any single IPTT indicator. | 4 | camps | [17 empty] | No data yet | R2A5 (Budget) | R2A5 (Budget) | 2064.34 | 295200.62 | No Data Log entries yet | During [reporting period], FIVDB delivered: Hold quarterly coordination meetings with camp service providers (CiC and relevant stakeholders). (target: 4 camps, quarterly x2). Source: FIVDB Detailed Budget, rows 198-201 (2.5.10 Quarterly Coordination meeting with service providers at camp). | Meeting minutes; attendance record | FIVDB Detailed Budget, rows 198-201 (2.5.10 Quarterly Coordination meeting with service providers at camp) | Project Manager | Refreshment BDT 10,000/camp x 4 x 2 = 80,000; materials BDT 2,000 x 4 x 2 = 16,000.
Result 2 | R2A5 | R2A5.3 | Enhance the capacity of implementing partners on CP and operations. |  | Routine operational upkeep (maintenance, minor repairs, running costs) to keep the facility/service functioning. | Camps 1W, 6, 21, 24 | 20 participants, 1 day | R2-I3 | Generates the count of outputs (facilities/people/sessions, as applicable) reported under R2-I3. | 20 | participants | [17 empty] | No data yet | R2A5 (Budget) | R2A5 (Budget) | 2064.34 | 295200.62 | No Data Log entries yet | During [reporting period], FIVDB delivered: Enhance the capacity of implementing partners on CP and operations. (target: 20 participants, 1 day), contributing to indicator 'Average % knowledge increase amongst participants on the protection subject in focus' (R2-I3). Source: FIVDB Detailed Budget, rows 202-205 (2.5.11 Enhancing the Capacity of Implementing Partners on CP and Operations). | Training register; attendance record | FIVDB Detailed Budget, rows 202-205 (2.5.11 Enhancing the Capacity of Implementing Partners on CP and Operations) | Technical Coordinator–Protection | Refreshment BDT 600 x 20 = 12,000; materials BDT 300 x 20 = 6,000.
Result 2 | R2A5 | R2A5.4 | Conduct quarterly joint field-monitoring visits with government officials (CiC office and other actors). |  | Direct observation/inspection against a standard checklist, with findings recorded and shared for follow-up action. | Camps 1W, 6, 21, 24 | 4 camps, quarterly x4 | - | Enables or supports delivery of other indicator-linked activities; not directly counted under any single IPTT indicator. | 4 | camps | [17 empty] | No data yet | R2A5 (Budget) | R2A5 (Budget) | 2064.34 | 295200.62 | No Data Log entries yet | During [reporting period], FIVDB delivered: Conduct quarterly joint field-monitoring visits with government officials (CiC office and other actors). (target: 4 camps, quarterly x4). Source: FIVDB Detailed Budget, rows 206-207 (2.5.12 Quarterly Joint field monitoring visit with government officials). | Field visit report | FIVDB Detailed Budget, rows 206-207 (2.5.12 Quarterly Joint field monitoring visit with government officials) | Project Manager | Travel allowance BDT 3,200/camp x 4 x 4 = 51,200.
Result 2 | R2A5 | R2A5.5 | Hold a project inception workshop with relevant stakeholders at camp level. |  | Facilitated in-person training/workshop with a structured curriculum, attendance record, and pre/post assessment where applicable. | Camps 1W, 6, 21, 24 | 4 camps, one-time | - | Enables or supports delivery of other indicator-linked activities; not directly counted under any single IPTT indicator. | 4 | camps | [17 empty] | No data yet | R2A5 (Budget) | R2A5 (Budget) | 2064.34 | 295200.62 | No Data Log entries yet | During [reporting period], FIVDB delivered: Hold a project inception workshop with relevant stakeholders at camp level. (target: 4 camps, one-time). Source: FIVDB Detailed Budget, rows 208-211 (2.5.13 Project inception workshop with different relevant stakeholders at camp level). | Workshop report; attendance record | FIVDB Detailed Budget, rows 208-211 (2.5.13 Project inception workshop with different relevant stakeholders at camp level) | Project Manager | Refreshment BDT 15,000/camp x 4 = 60,000; logistics/materials 5,000.
INC - Inception & Start-up (Preparatory Activities)
Preparatory | INC | INC-1 | Recruit and onboard FIVDB Education and Child Protection staff (Education Officer, Education Assistant, Technical Coordinator–Protection, case workers, facilitators). |  | HR process: recruitment/selection, contracting, and onboarding/orientation of staff or volunteers. | Camps 1W, 6, 21, 24 | Full staffing complement in place | - | Enables or supports delivery of other indicator-linked activities; not directly counted under any single IPTT indicator. | See target description | staff | [17 empty] | No data yet | Start-up / HR | Human Resources + Running Costs (shared) | 174890.55 | 25009348.65 | No Data Log entries yet | During [reporting period], FIVDB delivered: Recruit and onboard FIVDB Education and Child Protection staff (Education Officer, Education Assistant, Technical Coordinator–Protection, case workers, facilitators). (target: Full staffing complement in place). Source: Annex 18 Workplan, Row 149 (Staff Recruitment and posting in place). | Recruitment records; onboarding checklist | Annex 18 Workplan, Row 149 (Staff Recruitment and posting in place) | Project Manager | Precedes all other activities.
Preparatory | INC | INC-2 | Coordinate FD7 government approval process with SC/PIB for FIVDB's operational camps. |  | Routine operational upkeep (maintenance, minor repairs, running costs) to keep the facility/service functioning. | Camps 1W, 6, 21, 24 | FD7 approval secured | - | Enables or supports delivery of other indicator-linked activities; not directly counted under any single IPTT indicator. | 7 | approval | [17 empty] | No data yet | Start-up / compliance | Human Resources + Running Costs (shared) | 174890.55 | 25009348.65 | No Data Log entries yet | During [reporting period], FIVDB delivered: Coordinate FD7 government approval process with SC/PIB for FIVDB's operational camps. (target: FD7 approval secured). Source: Annex 18 Workplan, Row 14 (FD7 approval). | FD7 approval letter | Annex 18 Workplan, Row 14 (FD7 approval) | Project Manager | Pre-condition for field implementation; tracked as a project risk.
Preparatory | INC | INC-3 | Participate in project kick-off meeting and partnership review meetings (CP, Education) with PIB and SC. |  | Scheduled meeting or dialogue with the relevant stakeholders, with minutes/attendance recorded and follow-up actions tracked. | Cox's Bazar (consortium level) | Kick-off + quarterly partnership review | - | Enables or supports delivery of other indicator-linked activities; not directly counted under any single IPTT indicator. | See target description | meetings | [17 empty] | No data yet | Coordination | Human Resources + Running Costs (shared) | 174890.55 | 25009348.65 | No Data Log entries yet | During [reporting period], FIVDB delivered: Participate in project kick-off meeting and partnership review meetings (CP, Education) with PIB and SC. (target: Kick-off + quarterly partnership review). Source: Annex 18 Workplan, Rows 15-17 (Kick off meeting with member; Project kick off meeting with partners; Partnership review meeting). | Meeting minutes | Annex 18 Workplan, Rows 15-17 (Kick off meeting with member; Project kick off meeting with partners; Partnership review meeting) | Project Manager | Month 1.
Preparatory | INC | INC-4 | Adopt/contextualise SOPs (case management, referral pathway, safeguarding, MEAL tools) jointly with PIB. |  | Individual identification, intake/assessment, case planning, service delivery and follow-up, per the CP Case Management Minimum Standards 7-step process. | Camps 1W, 6, 21, 24 | SOPs signed off | - | Enables or supports delivery of other indicator-linked activities; not directly counted under any single IPTT indicator. | See target description | SOPs | [17 empty] | No data yet | Start-up / systems | Human Resources + Running Costs (shared) | 174890.55 | 25009348.65 | No Data Log entries yet | During [reporting period], FIVDB delivered: Adopt/contextualise SOPs (case management, referral pathway, safeguarding, MEAL tools) jointly with PIB. (target: SOPs signed off). Source: Not an explicit Annex 18 row - added as standard CP/MEAL start-up practice (Row 18 covers Health/Nutrition SOPs only). | Signed SOP documents | Not an explicit Annex 18 row - added as standard CP/MEAL start-up practice (Row 18 covers Health/Nutrition SOPs only) | Technical Coordinator–Protection | Precedes case-management and referral roll-out.
Preparatory | INC | INC-5 | Conduct joint site verification and mapping of CBLF/GoLF and MPCAC locations with PIB. |  | Delivered as a planned field activity by FIVDB staff/volunteers, following the sub-activity description, with progress recorded in this tracker. | Camps 1W, 6, 21, 24 | 51 education sites + MPCAC sites mapped | R1-I2, R2-I4 | Generates the count of outputs (facilities/people/sessions, as applicable) reported under R1-I2, R2-I4. | 51 | sites | [17 empty] | No data yet | Start-up / site planning | Human Resources + Running Costs (shared) | 174890.55 | 25009348.65 | No Data Log entries yet | During [reporting period], FIVDB delivered: Conduct joint site verification and mapping of CBLF/GoLF and MPCAC locations with PIB. (target: 51 education sites + MPCAC sites mapped), contributing to indicator 'Number of learning spaces established or restored to minimum standards for safe learning' (R1-I2, R2-I4). Source: Derived from Annex 3 (Locations & Integration Mapping) - camp-level CBLF/GoLF/MPCAC establishment references. | Site mapping report; GPS/list of confirmed sites | Derived from Annex 3 (Locations & Integration Mapping) - camp-level CBLF/GoLF/MPCAC establishment references | Education Officer | Feeds into R1-A1.1 and R2-A3.1 establishment activities.
Preparatory | INC | INC-6 | Support data collection for the baseline / KAP survey in FIVDB's camps. |  | Delivered as a planned field activity by FIVDB staff/volunteers, following the sub-activity description, with progress recorded in this tracker. | Camps 1W, 6, 21, 24 | Baseline data collected for FIVDB camps | SO-I1 | Generates the count of outputs (facilities/people/sessions, as applicable) reported under SO-I1. | See target description | survey | [17 empty] | No data yet | Start-up / MEAL | Human Resources + Running Costs (shared) | 174890.55 | 25009348.65 | No Data Log entries yet | During [reporting period], FIVDB delivered: Support data collection for the baseline / KAP survey in FIVDB's camps. (target: Baseline data collected for FIVDB camps), contributing to indicator '% of beneficiaries reporting that humanitarian assistance is delivered in a safe, accessible, accountable and participatory manner' (SO-I1). Source: Annex 18 Workplan, Row 156 (SCI-Base Line Survey, External). | Baseline survey dataset | Annex 18 Workplan, Row 156 (SCI-Base Line Survey, External) | MEAL Officer | Coordinated with PIB/SC MEAL leads; see MEAL Plan Section 9.
Preparatory | INC | INC-7 | Support preparation and submission of FD-6 documentation (distinct from the FD7 camp-access approval in INC-2). |  | Delivered as a planned field activity by FIVDB staff/volunteers, following the sub-activity description, with progress recorded in this tracker. | Cox's Bazar / national level | FD-6 submitted and cleared | - | Enables or supports delivery of other indicator-linked activities; not directly counted under any single IPTT indicator. | 6 | submission | [17 empty] | No data yet | Start-up / compliance | Human Resources + Running Costs (shared) | 174890.55 | 25009348.65 | No Data Log entries yet | During [reporting period], FIVDB delivered: Support preparation and submission of FD-6 documentation (distinct from the FD7 camp-access approval in INC-2). (target: FD-6 submitted and cleared). Source: Annex 18 Workplan, Row 148 (FD-6 Preparation and Submission). | FD-6 submission record; GoB clearance | Annex 18 Workplan, Row 148 (FD-6 Preparation and Submission) | Project Manager | Per Annex 18 Workplan, Row 148 (General Activities).
Preparatory | INC | INC-8 | Sign the FIVDB-PIB partnership/sub-agreement setting out roles, budget and reporting lines. |  | Delivered as a planned field activity by FIVDB staff/volunteers, following the sub-activity description, with progress recorded in this tracker. | Cox's Bazar (consortium level) | Signed partnership agreement | - | Enables or supports delivery of other indicator-linked activities; not directly counted under any single IPTT indicator. | See target description | agreement | [17 empty] | No data yet | Start-up / compliance | Human Resources + Running Costs (shared) | 174890.55 | 25009348.65 | No Data Log entries yet | During [reporting period], FIVDB delivered: Sign the FIVDB-PIB partnership/sub-agreement setting out roles, budget and reporting lines. (target: Signed partnership agreement). Source: Annex 18 Workplan, Row 151 (Partner Agreement). | Signed sub-agreement document | Annex 18 Workplan, Row 151 (Partner Agreement) | Project Manager | Per Annex 18 Workplan, Row 151; precedes fund disbursement.
Preparatory | INC | INC-9 | Conduct staff orientation and induction (project kick-off) for newly recruited FIVDB staff. |  | HR process: recruitment/selection, contracting, and onboarding/orientation of staff or volunteers. | Camps 1W, 6, 21, 24 | All newly recruited staff oriented | - | Enables or supports delivery of other indicator-linked activities; not directly counted under any single IPTT indicator. | See target description | staff | [17 empty] | No data yet | Start-up / HR | Human Resources + Running Costs (shared) | 174890.55 | 25009348.65 | No Data Log entries yet | During [reporting period], FIVDB delivered: Conduct staff orientation and induction (project kick-off) for newly recruited FIVDB staff. (target: All newly recruited staff oriented). Source: Annex 18 Workplan, Row 150 (Staff Orientation and Kick off). | Orientation attendance sheet | Annex 18 Workplan, Row 150 (Staff Orientation and Kick off) | Project Manager | Per Annex 18 Workplan, Row 150; follows INC-1 recruitment.
Preparatory | INC | INC-10 | Participate in the project inception meeting with government stakeholders at union, upazila, district and national level. |  | Scheduled meeting or dialogue with the relevant stakeholders, with minutes/attendance recorded and follow-up actions tracked. | Cox's Bazar + national level | Inception meeting(s) held | - | Enables or supports delivery of other indicator-linked activities; not directly counted under any single IPTT indicator. | See target description | meetings | [17 empty] | No data yet | Start-up / government liaison | Human Resources + Running Costs (shared) | 174890.55 | 25009348.65 | No Data Log entries yet | During [reporting period], FIVDB delivered: Participate in the project inception meeting with government stakeholders at union, upazila, district and national level. (target: Inception meeting(s) held). Source: Annex 18 Workplan, Row 152 (Project inception meeting with government stakeholders). | Meeting minutes/attendance record | Annex 18 Workplan, Row 152 (Project inception meeting with government stakeholders) | Project Manager | Per Annex 18 Workplan, Row 152; distinct from the consortium-partner kick-off in INC-3.
Preparatory | INC | INC-11 | Participate in the SC-led consortium MEAL Plan workshop (2 days). |  | Facilitated in-person training/workshop with a structured curriculum, attendance record, and pre/post assessment where applicable. | Cox's Bazar (consortium level) | FIVDB MEAL staff attend | - | Enables or supports delivery of other indicator-linked activities; not directly counted under any single IPTT indicator. | See target description | workshop | [17 empty] | No data yet | Start-up / MEAL | Human Resources + Running Costs (shared) | 174890.55 | 25009348.65 | No Data Log entries yet | During [reporting period], FIVDB delivered: Participate in the SC-led consortium MEAL Plan workshop (2 days). (target: FIVDB MEAL staff attend). Source: Annex 18 Workplan, Row 154 (SCI-MEAL Plan workshop, 2 days). | Workshop attendance record | Annex 18 Workplan, Row 154 (SCI-MEAL Plan workshop, 2 days) | MEAL Officer | Per Annex 18 Workplan, Row 154; aligns FIVDB's MEAL Plan (this workbook) with the consortium-wide system.
Preparatory | INC | INC-12 | Participate in SC-led training on Accountability and Safeguarding for all FIVDB staff and volunteers. |  | Facilitated in-person training/workshop with a structured curriculum, attendance record, and pre/post assessment where applicable. | Camps 1W, 6, 21, 24 | All FIVDB staff/volunteers trained | R2-I5 | Generates the count of outputs (facilities/people/sessions, as applicable) reported under R2-I5. | See target description | individuals | [17 empty] | No data yet | Start-up / safeguarding | Human Resources + Running Costs (shared) | 174890.55 | 25009348.65 | No Data Log entries yet | During [reporting period], FIVDB delivered: Participate in SC-led training on Accountability and Safeguarding for all FIVDB staff and volunteers. (target: All FIVDB staff/volunteers trained), contributing to indicator '% of caseworkers whose knowledge assessment score is at least 70%' (R2-I5). Source: Annex 18 Workplan, Row 157 (SCI-Training on Accountability and Safeguarding). | Training attendance record; signed policy acknowledgement | Annex 18 Workplan, Row 157 (SCI-Training on Accountability and Safeguarding) | Project Manager | Per Annex 18 Workplan, Row 157; complements the ongoing safeguarding activities under R2-A5.5.
GEN - Cross-cutting Coordination, Safeguarding, GBV Risk Mitigation and Gender Mainstreaming (ongoing throughout the action)
General | GEN | GEN-1 | Attend regular coordination meetings with implementing partners (PIB, SC, JCF, BTS, PHD) and other stakeholders. |  | Scheduled meeting or dialogue with the relevant stakeholders, with minutes/attendance recorded and follow-up actions tracked. | Cox's Bazar (consortium level) | Regular attendance throughout | - | Enables or supports delivery of other indicator-linked activities; not directly counted under any single IPTT indicator. | See target description | meetings | [17 empty] | No data yet | Coordination | Human Resources (shared) | 136467.47 | 19514848.21 | No Data Log entries yet | During [reporting period], FIVDB delivered: Attend regular coordination meetings with implementing partners (PIB, SC, JCF, BTS, PHD) and other stakeholders. (target: Regular attendance throughout). Source: Annex 18 Workplan, Row 155 (Regular coordination meeting with implementing partners & other stakeholders). | Meeting minutes/attendance record | Annex 18 Workplan, Row 155 (Regular coordination meeting with implementing partners & other stakeholders) | Project Manager | Per Annex 18 Workplan, Row 155; distinct from sector-specific coordination in R1-A7/R2-A4.3.
General | GEN | GEN-2 | Conduct a safeguarding and GBV risk assessment of any prospective site before it is selected/established as a CBLF, GoLF, MPCAC or other facility (venue safety, lighting, privacy, access routes, presence of known risks). |  | Site/structure identification, agreement with camp authorities, procurement/construction or formation, and handover or launch. | Camps 1W, 6, 21, 24 | All new sites screened before establishment | R1-I2, R2-I4 | Generates the count of outputs (facilities/people/sessions, as applicable) reported under R1-I2, R2-I4. | See target description | sites | [17 empty] | No data yet | Safeguarding / site safety | Human Resources (shared) | 136467.47 | 19514848.21 | No Data Log entries yet | During [reporting period], FIVDB delivered: Conduct a safeguarding and GBV risk assessment of any prospective site before it is selected/established as a CBLF, GoLF, MPCAC or other facility (venue safety, lighting, privacy, access routes, presence of known risks). (target: All new sites screened before establishment), contributing to indicator 'Number of learning spaces established or restored to minimum standards for safe learning' (R1-I2, R2-I4). Source: Not an explicit Annex 18 row - added per the GBV risk-management and safe-site requirements referenced in the Logframe's Result 1 Indicator 2 definition (minimum standards for safe learning spaces). | Site-selection safeguarding/GBV risk assessment checklist | Not an explicit Annex 18 row - added per the GBV risk-management and safe-site requirements referenced in the Logframe's Result 1 Indicator 2 definition (minimum standards for safe learning spaces) | Technical Coordinator–Protection | Precedes R1-A1.1 (CBLF establishment) and R2-A3.1 (MPCAC establishment); repeated for any new/replacement site.
General | GEN | GEN-3 | Conduct a safeguarding risk screening before any group activity, training, distribution or community event (adult-to-child ratios, presence of trusted adults, venue safety, transport/pick-up arrangements). |  | Planned distribution or provision, with beneficiary verification, signed waybill/record, and post-distribution monitoring where applicable. | Camps 1W, 6, 21, 24 | Screening completed before every group event | - | Enables or supports delivery of other indicator-linked activities; not directly counted under any single IPTT indicator. | See target description | events | [17 empty] | No data yet | Safeguarding / event safety | Human Resources (shared) | 136467.47 | 19514848.21 | No Data Log entries yet | During [reporting period], FIVDB delivered: Conduct a safeguarding risk screening before any group activity, training, distribution or community event (adult-to-child ratios, presence of trusted adults, venue safety, transport/pick-up arrangements). (target: Screening completed before every group event). Source: Not an explicit Annex 18 row - added as standard child-safeguarding practice preceding all group activities/events, complementing the ongoing Safeguarding/PSEA activities in R2-A5.5. | Pre-event safeguarding screening checklist | Not an explicit Annex 18 row - added as standard child-safeguarding practice preceding all group activities/events, complementing the ongoing Safeguarding/PSEA activities in R2-A5.5 | Technical Coordinator–Protection | Applies across Event/Activity Reports (Field Reporting Templates, Template 2) and Training Reports (Template 3).
General | GEN | GEN-4 | Ensure gender mainstreaming and EU Gender-Age Marker compliance across all FIVDB activities (gender-responsive design review of facilities and sessions, sex/age-disaggregated monitoring, gender-balanced staffing and participation). |  | Direct observation/inspection against a standard checklist, with findings recorded and shared for follow-up action. | Camps 1W, 6, 21, 24 | All activities reviewed for gender/age responsiveness | SO-I1 | Generates the count of outputs (facilities/people/sessions, as applicable) reported under SO-I1. | See target description | review | [17 empty] | No data yet | Gender mainstreaming | Human Resources (shared) | 136467.47 | 19514848.21 | No Data Log entries yet | During [reporting period], FIVDB delivered: Ensure gender mainstreaming and EU Gender-Age Marker compliance across all FIVDB activities (gender-responsive design review of facilities and sessions, sex/age-disaggregated monitoring, gender-balanced staffing and participation). (target: All activities reviewed for gender/age responsiveness), contributing to indicator '% of beneficiaries reporting that humanitarian assistance is delivered in a safe, accessible, accountable and participatory manner' (SO-I1). Source: Not an explicit Annex 18 row - added per the EU Gender-Age Marker requirement referenced in the Logframe's Result 1 Indicator 2 definition ('gender and age responsive in line with the EU Gender-Age Marker'). | Gender-responsiveness review checklist; disaggregated data in the IPTT | Not an explicit Annex 18 row - added per the EU Gender-Age Marker requirement referenced in the Logframe's Result 1 Indicator 2 definition ('gender and age responsive in line with the EU Gender-Age Marker') | MEAL Officer | Reviewed at each quarterly data review (see MEAL Plan Section 8) alongside disaggregation checks in the IPTT.
CLOSE - Learning, Evaluation and Visibility (project close-out)
Closeout | CLOSE | CLOSE-1 | Contribute to the national and local level lesson-learned workshop. |  | Facilitated in-person training/workshop with a structured curriculum, attendance record, and pre/post assessment where applicable. | Cox's Bazar + national level | FIVDB participation and case examples shared | - | Enables or supports delivery of other indicator-linked activities; not directly counted under any single IPTT indicator. | See target description | workshop | [17 empty] | No data yet | Learning / close-out | Human Resources + Running Costs (shared) | 174890.55 | 25009348.65 | No Data Log entries yet | During [reporting period], FIVDB delivered: Contribute to the national and local level lesson-learned workshop. (target: FIVDB participation and case examples shared). Source: Annex 18 Workplan, Row 153 (National and Local level lesson learned workshop). | Workshop report; presentation/case material | Annex 18 Workplan, Row 153 (National and Local level lesson learned workshop) | Project Manager | Per Annex 18 Workplan, Row 153; draws on the Case Story template (Field Reporting Templates, Template 9).
Closeout | CLOSE | CLOSE-2 | Support the SC-led external final evaluation (data access, KIIs/FGDs, verification of final indicator values). |  | Delivered as a planned field activity by FIVDB staff/volunteers, following the sub-activity description, with progress recorded in this tracker. | Camps 1W, 6, 21, 24 | Full cooperation with evaluators | - | Enables or supports delivery of other indicator-linked activities; not directly counted under any single IPTT indicator. | See target description | evaluation | [17 empty] | No data yet | Evaluation / close-out | Human Resources + Running Costs (shared) | 174890.55 | 25009348.65 | No Data Log entries yet | During [reporting period], FIVDB delivered: Support the SC-led external final evaluation (data access, KIIs/FGDs, verification of final indicator values). (target: Full cooperation with evaluators). Source: Annex 18 Workplan, Row 158 (SCI-Final Evaluation, External). | Evaluation report (SC-led); FIVDB data-access log | Annex 18 Workplan, Row 158 (SCI-Final Evaluation, External) | MEAL Officer | Per Annex 18 Workplan, Row 158; mirrors 'Final evaluation contribution' in the M&E Calendar.
Closeout | CLOSE | CLOSE-3 | Contribute FIVDB content (photos, case/success stories, quotes) to the consortium's video documentary and other visibility/media and printing products. |  | Community-facing awareness or engagement activity delivered at facility or camp level, with attendance/participation recorded. | Camps 1W, 6, 21, 24 | FIVDB content supplied on request | - | Enables or supports delivery of other indicator-linked activities; not directly counted under any single IPTT indicator. | See target description | products | [17 empty] | No data yet | Communications / visibility | Human Resources + Running Costs (shared) | 174890.55 | 25009348.65 | No Data Log entries yet | During [reporting period], FIVDB delivered: Contribute FIVDB content (photos, case/success stories, quotes) to the consortium's video documentary and other visibility/media and printing products. (target: FIVDB content supplied on request). Source: Annex 18 Workplan, Row 159 (Video documentary, Media and Printing). | Signed consent forms; content log | Annex 18 Workplan, Row 159 (Video documentary, Media and Printing) | MEAL Officer | Per Annex 18 Workplan, Row 159; must follow the consent and approval requirements in the Success Story template (Field Reporting Templates, Template 10).

## 10. Activity Data Log
10. Activity-wise Data Collection Log
One row per actual conducted session/event (not per planned activity - see the Activity Tracker for planning). Populate from the Attendance Sheets (Field Reporting Templates, Templates 14-15) after each event. 'Host' = host-community participants; 'FDMN' = Forcibly Displaced Myanmar Nationals (Rohingya refugee participants), the official Government of Bangladesh terminology. Each population is split by sex and age using Girls <18 / Boys <18 / Female 18+ / Male 18+ throughout. Select the Activity Code from the dropdown (sourced live from the Activity Tracker): Target Number and Linked Indicator(s) are then pulled automatically (relational lookup), and Discrepancy/% of Target calculate automatically against Total Participants. Pre-Test/Post-Test Score and Knowledge Change (% = (Post-Pre)/Pre) apply to training-type sessions only (leave blank otherwise) and support the IPTT's knowledge-increase indicators (R1-I5, R1-I7, R2-I3) - Evidence should reference where the actual test sheets/attendance records are filed. IMPORTANT: Event Date is REQUIRED, not optional, for every row with participants entered - Quarter and Month are auto-derived from it, and the Activity Tracker/IPTT auto-link ONLY picks up rows that have a Quarter. A row with participants but no Event Date will show correctly in this sheet's own Total Participants, but will NOT appear anywhere else (Activity Tracker ACTUAL, IPTT ACTUAL, Dashboard) - the Event Date cell turns red as a warning if this happens. Hosting Organisation records who convened/hosted the session (usually FIVDB, but note if co-hosted with PIB/SC/other). Budgetary/Non-budgetary flags whether this specific instance drew on the project budget or was delivered at no direct cost (e.g. volunteer-led, in-kind). 'Total Day(s)' excludes Friday and Saturday (Bangladesh's weekend) by default - see the Methodology Note below the table. CWD = number of participants who are children/persons with disability.
SL# | Activity Code | Event / Activity Title | Camp | Event Date (Start) | End Date | Total Day(s) (excl. weekend) | Facilitated / Conducted By | Budgetary / Non-budgetary | Hosting Organisation | Discussion Area / Topic | Sex & Age - Host (community) |  |  |  | Sex & Age - FDMN (Rohingya) |  |  |  | Total Participants | CWD (Children/Persons with Disability) | Pre-Test Score (avg) | Post-Test Score (avg) | Knowledge Change % (Post-Pre)/Pre | Target Number (from Activity Tracker) | Discrepancy (Actual - Target) | % of Target | Linked Indicator(s) (from Activity Tracker) | Quarter | Month | Evidence (document/file reference)
[11 empty] | Boys <18 | Male 18+ | Girls <18 | Female 18+ | Boys <18 | Male 18+ | Girls <18 | Female 18+
1 | [18 empty] | 0
2 | [18 empty] | 0
3 | [18 empty] | 0
4 | [18 empty] | 0
5 | [18 empty] | 0
6 | [18 empty] | 0
7 | [18 empty] | 0
8 | [18 empty] | 0
9 | [18 empty] | 0
10 | [18 empty] | 0
11 | [18 empty] | 0
12 | [18 empty] | 0
13 | [18 empty] | 0
14 | [18 empty] | 0
15 | [18 empty] | 0
16 | [18 empty] | 0
17 | [18 empty] | 0
18 | [18 empty] | 0
19 | [18 empty] | 0
20 | [18 empty] | 0
21 | [18 empty] | 0
22 | [18 empty] | 0
23 | [18 empty] | 0
24 | [18 empty] | 0
25 | [18 empty] | 0
26 | [18 empty] | 0
27 | [18 empty] | 0
28 | [18 empty] | 0
29 | [18 empty] | 0
30 | [18 empty] | 0
31 | [18 empty] | 0
32 | [18 empty] | 0
33 | [18 empty] | 0
34 | [18 empty] | 0
35 | [18 empty] | 0
36 | [18 empty] | 0
37 | [18 empty] | 0
38 | [18 empty] | 0
39 | [18 empty] | 0
40 | [18 empty] | 0
|  | TOTAL (all rows above) | [8 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Formulas:
Total Day(s) (excl. weekend) = IFERROR(IF(AND([Event Date (Start)]<>"",[End Date]<>""),NETWORKDAYS.INTL([Event Date (Start)],[End Date],7),""),"")
Quarter = IFERROR(IF([Event Date (Start)]="","","Q"&(ROUNDUP((DATEDIF(DATE(2026,6,1),[Event Date (Start)],"m")+1)/3,0))),"")

## 11. Distribution Log
11. Distribution Log
One row per item distributed per distribution event (a single distribution day covering multiple items may need multiple rows). Populate from the Distribution Report (Field Reporting Templates, Template 3) after each distribution. 'Host' = host-community recipients; 'FDMN' = Forcibly Displaced Myanmar Nationals (Rohingya refugee recipients), each split by sex and age using Girls <18 / Boys <18 / Female 18+ / Male 18+ throughout. 'Facility/Centre' records the specific CBLF/MPCAC/office (beyond just Camp) where the distribution happened. Select the Activity Code from the dropdown (sourced live from the Activity Tracker): Target Number, Discrepancy, % of Target and Linked Indicator(s) all pull/calculate automatically against Total Recipients - the same relational link used throughout this workbook. ODM = On-site/On-going Distribution Monitoring conducted during the distribution itself; PDM = Post-Distribution Monitoring conducted with a sample of recipients afterward (Field Reporting Templates, Template 3 process). ODM/PDM Findings capture what was actually observed/reported - e.g. quality issues, complaints, appropriateness of items - not just whether the check happened. IMPORTANT: Distribution Date is REQUIRED, not optional, for every row with recipients entered - Quarter/Month are auto-derived from it, and the Activity Tracker/IPTT auto-link ONLY picks up rows that have a Quarter. A row with recipients but no Distribution Date will NOT appear in Activity Tracker ACTUAL, IPTT ACTUAL or the Dashboard - the Distribution Date cell turns red as a warning if this happens. Narrative auto-drafts a fill-in-the-blank reporting sentence. Budgetary/Non-budgetary flags whether this specific distribution drew on the project budget or was delivered at no direct cost (e.g. donated/in-kind items).
SL# | Activity Code | Distribution Title | Camp | Facility / Centre | Distribution Date | Distributed By | Hosting Organisation | Budgetary / Non-budgetary | Item | Unit | Qty Planned | Qty Distributed | Recipients - Host (community) |  |  |  | Recipients - FDMN (Rohingya) |  |  |  | Total Recipients | CWD (Children/Persons with Disability) | ODM Done? (Y/N) | ODM Date | ODM Findings | PDM Done? (Y/N) | PDM Date | PDM Findings | Target Number (from Activity Tracker) | Discrepancy (Actual - Target) | % of Target | Linked Indicator(s) (from Activity Tracker) | Quarter | Month | Narrative (auto-drafted)
[13 empty] | Boys <18 | Male 18+ | Girls <18 | Female 18+ | Boys <18 | Male 18+ | Girls <18 | Female 18+
1 | [20 empty] | 0
2 | [20 empty] | 0
3 | [20 empty] | 0
4 | [20 empty] | 0
5 | [20 empty] | 0
6 | [20 empty] | 0
7 | [20 empty] | 0
8 | [20 empty] | 0
9 | [20 empty] | 0
10 | [20 empty] | 0
11 | [20 empty] | 0
12 | [20 empty] | 0
13 | [20 empty] | 0
14 | [20 empty] | 0
15 | [20 empty] | 0
16 | [20 empty] | 0
17 | [20 empty] | 0
18 | [20 empty] | 0
19 | [20 empty] | 0
20 | [20 empty] | 0
21 | [20 empty] | 0
22 | [20 empty] | 0
23 | [20 empty] | 0
24 | [20 empty] | 0
25 | [20 empty] | 0
26 | [20 empty] | 0
27 | [20 empty] | 0
28 | [20 empty] | 0
29 | [20 empty] | 0
30 | [20 empty] | 0
31 | [20 empty] | 0
32 | [20 empty] | 0
33 | [20 empty] | 0
34 | [20 empty] | 0
35 | [20 empty] | 0
36 | [20 empty] | 0
37 | [20 empty] | 0
38 | [20 empty] | 0
39 | [20 empty] | 0
40 | [20 empty] | 0
|  | TOTAL (all rows above) | [8 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Formulas:
Quarter = IFERROR(IF([Distribution Date]="","","Q"&(ROUNDUP((DATEDIF(DATE(2026,6,1),[Distribution Date],"m")+1)/3,0))),"")

## 12. Dropout Tracker
12. Dropout Tracker - Learners, Staff & Volunteers
Tracks retention/dropout by quarter for learners (feeds SO-I2), FIVDB staff (by designation), and FIVDB/community volunteers (by designation and Rohingya/Host). Sex & age segregation follows the same convention used throughout this workbook: Girls <18 / Boys <18 for learners; Female 18+ / Male 18+ for staff and volunteers. Dropout % = Dropped Out / (At Start + New during the quarter). A month-wise trend summary (Section D) sits at the end, grouped under quarter, for a quick visual check between quarterly reviews.
A. Learner Dropout (CBLFs, feeds SO-I2)
Quarter | At Start (Girls <18) | At Start (Boys <18) | New (Girls <18) | New (Boys <18) | Dropped Out (Girls <18) | Dropped Out (Boys <18) | Retained at End (1 / 2 / Total) | Dropout % (1) | Dropout % (2) | Dropout % (Total)
Q1 | [6 empty] | 0 / 0 / 0
Q2 | [6 empty] | 0 / 0 / 0
Q3 | [6 empty] | 0 / 0 / 0
Q4 | [6 empty] | 0 / 0 / 0
Q5 | [6 empty] | 0 / 0 / 0
Q6 | [6 empty] | 0 / 0 / 0
Q7 | [6 empty] | 0 / 0 / 0
Q8 | [6 empty] | 0 / 0 / 0
Cumulative | 0 | 0 | 0 | 0 | 0 | 0
B. Staff Dropout / Turnover - by Designation
Project Coordinator
Quarter | At Start (Female 18+) | At Start (Male 18+) | New (Female 18+) | New (Male 18+) | Dropped Out (Female 18+) | Dropped Out (Male 18+) | Retained at End (1 / 2 / Total) | Dropout % (1) | Dropout % (2) | Dropout % (Total)
Q1 | [6 empty] | 0 / 0 / 0
Q2 | [6 empty] | 0 / 0 / 0
Q3 | [6 empty] | 0 / 0 / 0
Q4 | [6 empty] | 0 / 0 / 0
Q5 | [6 empty] | 0 / 0 / 0
Q6 | [6 empty] | 0 / 0 / 0
Q7 | [6 empty] | 0 / 0 / 0
Q8 | [6 empty] | 0 / 0 / 0
Cumulative | 0 | 0 | 0 | 0 | 0 | 0
Technical Coordinator–Protection
Quarter | At Start (Female 18+) | At Start (Male 18+) | New (Female 18+) | New (Male 18+) | Dropped Out (Female 18+) | Dropped Out (Male 18+) | Retained at End (1 / 2 / Total) | Dropout % (1) | Dropout % (2) | Dropout % (Total)
Q1 | [6 empty] | 0 / 0 / 0
Q2 | [6 empty] | 0 / 0 / 0
Q3 | [6 empty] | 0 / 0 / 0
Q4 | [6 empty] | 0 / 0 / 0
Q5 | [6 empty] | 0 / 0 / 0
Q6 | [6 empty] | 0 / 0 / 0
Q7 | [6 empty] | 0 / 0 / 0
Q8 | [6 empty] | 0 / 0 / 0
Cumulative | 0 | 0 | 0 | 0 | 0 | 0
Child Protection Officer
Quarter | At Start (Female 18+) | At Start (Male 18+) | New (Female 18+) | New (Male 18+) | Dropped Out (Female 18+) | Dropped Out (Male 18+) | Retained at End (1 / 2 / Total) | Dropout % (1) | Dropout % (2) | Dropout % (Total)
Q1 | [6 empty] | 0 / 0 / 0
Q2 | [6 empty] | 0 / 0 / 0
Q3 | [6 empty] | 0 / 0 / 0
Q4 | [6 empty] | 0 / 0 / 0
Q5 | [6 empty] | 0 / 0 / 0
Q6 | [6 empty] | 0 / 0 / 0
Q7 | [6 empty] | 0 / 0 / 0
Q8 | [6 empty] | 0 / 0 / 0
Cumulative | 0 | 0 | 0 | 0 | 0 | 0
Case Management Officer
Quarter | At Start (Female 18+) | At Start (Male 18+) | New (Female 18+) | New (Male 18+) | Dropped Out (Female 18+) | Dropped Out (Male 18+) | Retained at End (1 / 2 / Total) | Dropout % (1) | Dropout % (2) | Dropout % (Total)
Q1 | [6 empty] | 0 / 0 / 0
Q2 | [6 empty] | 0 / 0 / 0
Q3 | [6 empty] | 0 / 0 / 0
Q4 | [6 empty] | 0 / 0 / 0
Q5 | [6 empty] | 0 / 0 / 0
Q6 | [6 empty] | 0 / 0 / 0
Q7 | [6 empty] | 0 / 0 / 0
Q8 | [6 empty] | 0 / 0 / 0
Cumulative | 0 | 0 | 0 | 0 | 0 | 0
Technical Officer – EiE
Quarter | At Start (Female 18+) | At Start (Male 18+) | New (Female 18+) | New (Male 18+) | Dropped Out (Female 18+) | Dropped Out (Male 18+) | Retained at End (1 / 2 / Total) | Dropout % (1) | Dropout % (2) | Dropout % (Total)
Q1 | [6 empty] | 0 / 0 / 0
Q2 | [6 empty] | 0 / 0 / 0
Q3 | [6 empty] | 0 / 0 / 0
Q4 | [6 empty] | 0 / 0 / 0
Q5 | [6 empty] | 0 / 0 / 0
Q6 | [6 empty] | 0 / 0 / 0
Q7 | [6 empty] | 0 / 0 / 0
Q8 | [6 empty] | 0 / 0 / 0
Cumulative | 0 | 0 | 0 | 0 | 0 | 0
Field Officer / Programme Organiser
Quarter | At Start (Female 18+) | At Start (Male 18+) | New (Female 18+) | New (Male 18+) | Dropped Out (Female 18+) | Dropped Out (Male 18+) | Retained at End (1 / 2 / Total) | Dropout % (1) | Dropout % (2) | Dropout % (Total)
Q1 | [6 empty] | 0 / 0 / 0
Q2 | [6 empty] | 0 / 0 / 0
Q3 | [6 empty] | 0 / 0 / 0
Q4 | [6 empty] | 0 / 0 / 0
Q5 | [6 empty] | 0 / 0 / 0
Q6 | [6 empty] | 0 / 0 / 0
Q7 | [6 empty] | 0 / 0 / 0
Q8 | [6 empty] | 0 / 0 / 0
Cumulative | 0 | 0 | 0 | 0 | 0 | 0
M&E Officer
Quarter | At Start (Female 18+) | At Start (Male 18+) | New (Female 18+) | New (Male 18+) | Dropped Out (Female 18+) | Dropped Out (Male 18+) | Retained at End (1 / 2 / Total) | Dropout % (1) | Dropout % (2) | Dropout % (Total)
Q1 | [6 empty] | 0 / 0 / 0
Q2 | [6 empty] | 0 / 0 / 0
Q3 | [6 empty] | 0 / 0 / 0
Q4 | [6 empty] | 0 / 0 / 0
Q5 | [6 empty] | 0 / 0 / 0
Q6 | [6 empty] | 0 / 0 / 0
Q7 | [6 empty] | 0 / 0 / 0
Q8 | [6 empty] | 0 / 0 / 0
Cumulative | 0 | 0 | 0 | 0 | 0 | 0
Admin & Finance Officer
Quarter | At Start (Female 18+) | At Start (Male 18+) | New (Female 18+) | New (Male 18+) | Dropped Out (Female 18+) | Dropped Out (Male 18+) | Retained at End (1 / 2 / Total) | Dropout % (1) | Dropout % (2) | Dropout % (Total)
Q1 | [6 empty] | 0 / 0 / 0
Q2 | [6 empty] | 0 / 0 / 0
Q3 | [6 empty] | 0 / 0 / 0
Q4 | [6 empty] | 0 / 0 / 0
Q5 | [6 empty] | 0 / 0 / 0
Q6 | [6 empty] | 0 / 0 / 0
Q7 | [6 empty] | 0 / 0 / 0
Q8 | [6 empty] | 0 / 0 / 0
Cumulative | 0 | 0 | 0 | 0 | 0 | 0
Admin & Logistics Assistant
Quarter | At Start (Female 18+) | At Start (Male 18+) | New (Female 18+) | New (Male 18+) | Dropped Out (Female 18+) | Dropped Out (Male 18+) | Retained at End (1 / 2 / Total) | Dropout % (1) | Dropout % (2) | Dropout % (Total)
Q1 | [6 empty] | 0 / 0 / 0
Q2 | [6 empty] | 0 / 0 / 0
Q3 | [6 empty] | 0 / 0 / 0
Q4 | [6 empty] | 0 / 0 / 0
Q5 | [6 empty] | 0 / 0 / 0
Q6 | [6 empty] | 0 / 0 / 0
Q7 | [6 empty] | 0 / 0 / 0
Q8 | [6 empty] | 0 / 0 / 0
Cumulative | 0 | 0 | 0 | 0 | 0 | 0
Office Support Staff
Quarter | At Start (Female 18+) | At Start (Male 18+) | New (Female 18+) | New (Male 18+) | Dropped Out (Female 18+) | Dropped Out (Male 18+) | Retained at End (1 / 2 / Total) | Dropout % (1) | Dropout % (2) | Dropout % (Total)
Q1 | [6 empty] | 0 / 0 / 0
Q2 | [6 empty] | 0 / 0 / 0
Q3 | [6 empty] | 0 / 0 / 0
Q4 | [6 empty] | 0 / 0 / 0
Q5 | [6 empty] | 0 / 0 / 0
Q6 | [6 empty] | 0 / 0 / 0
Q7 | [6 empty] | 0 / 0 / 0
Q8 | [6 empty] | 0 / 0 / 0
Cumulative | 0 | 0 | 0 | 0 | 0 | 0
C. Volunteer Dropout / Turnover - by Designation & Rohingya/Host
Teaching Volunteer – Rohingya (FDMN)
Quarter | At Start (Female 18+) | At Start (Male 18+) | New (Female 18+) | New (Male 18+) | Dropped Out (Female 18+) | Dropped Out (Male 18+) | Retained at End (1 / 2 / Total) | Dropout % (1) | Dropout % (2) | Dropout % (Total)
Q1 | [6 empty] | 0 / 0 / 0
Q2 | [6 empty] | 0 / 0 / 0
Q3 | [6 empty] | 0 / 0 / 0
Q4 | [6 empty] | 0 / 0 / 0
Q5 | [6 empty] | 0 / 0 / 0
Q6 | [6 empty] | 0 / 0 / 0
Q7 | [6 empty] | 0 / 0 / 0
Q8 | [6 empty] | 0 / 0 / 0
Cumulative | 0 | 0 | 0 | 0 | 0 | 0
Teaching Volunteer – Host
Quarter | At Start (Female 18+) | At Start (Male 18+) | New (Female 18+) | New (Male 18+) | Dropped Out (Female 18+) | Dropped Out (Male 18+) | Retained at End (1 / 2 / Total) | Dropout % (1) | Dropout % (2) | Dropout % (Total)
Q1 | [6 empty] | 0 / 0 / 0
Q2 | [6 empty] | 0 / 0 / 0
Q3 | [6 empty] | 0 / 0 / 0
Q4 | [6 empty] | 0 / 0 / 0
Q5 | [6 empty] | 0 / 0 / 0
Q6 | [6 empty] | 0 / 0 / 0
Q7 | [6 empty] | 0 / 0 / 0
Q8 | [6 empty] | 0 / 0 / 0
Cumulative | 0 | 0 | 0 | 0 | 0 | 0
Case Management Volunteer – Rohingya (FDMN)
Quarter | At Start (Female 18+) | At Start (Male 18+) | New (Female 18+) | New (Male 18+) | Dropped Out (Female 18+) | Dropped Out (Male 18+) | Retained at End (1 / 2 / Total) | Dropout % (1) | Dropout % (2) | Dropout % (Total)
Q1 | [6 empty] | 0 / 0 / 0
Q2 | [6 empty] | 0 / 0 / 0
Q3 | [6 empty] | 0 / 0 / 0
Q4 | [6 empty] | 0 / 0 / 0
Q5 | [6 empty] | 0 / 0 / 0
Q6 | [6 empty] | 0 / 0 / 0
Q7 | [6 empty] | 0 / 0 / 0
Q8 | [6 empty] | 0 / 0 / 0
Cumulative | 0 | 0 | 0 | 0 | 0 | 0
MPCAC Facilitator – Rohingya (FDMN)
Quarter | At Start (Female 18+) | At Start (Male 18+) | New (Female 18+) | New (Male 18+) | Dropped Out (Female 18+) | Dropped Out (Male 18+) | Retained at End (1 / 2 / Total) | Dropout % (1) | Dropout % (2) | Dropout % (Total)
Q1 | [6 empty] | 0 / 0 / 0
Q2 | [6 empty] | 0 / 0 / 0
Q3 | [6 empty] | 0 / 0 / 0
Q4 | [6 empty] | 0 / 0 / 0
Q5 | [6 empty] | 0 / 0 / 0
Q6 | [6 empty] | 0 / 0 / 0
Q7 | [6 empty] | 0 / 0 / 0
Q8 | [6 empty] | 0 / 0 / 0
Cumulative | 0 | 0 | 0 | 0 | 0 | 0
MPCAC Facilitator – Host
Quarter | At Start (Female 18+) | At Start (Male 18+) | New (Female 18+) | New (Male 18+) | Dropped Out (Female 18+) | Dropped Out (Male 18+) | Retained at End (1 / 2 / Total) | Dropout % (1) | Dropout % (2) | Dropout % (Total)
Q1 | [6 empty] | 0 / 0 / 0
Q2 | [6 empty] | 0 / 0 / 0
Q3 | [6 empty] | 0 / 0 / 0
Q4 | [6 empty] | 0 / 0 / 0
Q5 | [6 empty] | 0 / 0 / 0
Q6 | [6 empty] | 0 / 0 / 0
Q7 | [6 empty] | 0 / 0 / 0
Q8 | [6 empty] | 0 / 0 / 0
Cumulative | 0 | 0 | 0 | 0 | 0 | 0
PSS/PALS Volunteer – Rohingya (FDMN)
Quarter | At Start (Female 18+) | At Start (Male 18+) | New (Female 18+) | New (Male 18+) | Dropped Out (Female 18+) | Dropped Out (Male 18+) | Retained at End (1 / 2 / Total) | Dropout % (1) | Dropout % (2) | Dropout % (Total)
Q1 | [6 empty] | 0 / 0 / 0
Q2 | [6 empty] | 0 / 0 / 0
Q3 | [6 empty] | 0 / 0 / 0
Q4 | [6 empty] | 0 / 0 / 0
Q5 | [6 empty] | 0 / 0 / 0
Q6 | [6 empty] | 0 / 0 / 0
Q7 | [6 empty] | 0 / 0 / 0
Q8 | [6 empty] | 0 / 0 / 0
Cumulative | 0 | 0 | 0 | 0 | 0 | 0
D. Month-wise Dropout Trend Summary (grouped under quarter, age-segregated)
Dropped-out count per month, by category AND age/sex segment (not combined), for a quick trend check between quarterly reviews. Enter monthly totals directly - these are independent entries, not auto-summed from Sections A-C above.
Category / Segment | Q1 |  |  | Q2 |  |  | Q3 |  |  | Q4 |  |  | Q5 |  |  | Q6 |  |  | Q7 |  |  | Q8
| 06/2026 | 07/2026 | 08/2026 | 09/2026 | 10/2026 | 11/2026 | 12/2026 | 01/2027 | 02/2027 | 03/2027 | 04/2027 | 05/2027 | 06/2027 | 07/2027 | 08/2027 | 09/2027 | 10/2027 | 11/2027 | 12/2027 | 01/2028 | 02/2028 | 03/2028 | 04/2028 | 05/2028
Learners - Girls <18
Learners - Boys <18
Staff - Female 18+
Staff - Male 18+
Volunteers - Female 18+
Volunteers - Male 18+
E. Automatic Summary (aggregates Sections A-C - no manual entry, age-segregated)
Every figure below is a live formula referencing the Cumulative row of each table in Sections A-C - if those figures change, this summary updates automatically. Each age/sex segment is shown on its own row, not combined, so a gap between e.g. girls' and boys' dropout rates is visible rather than averaged away.
Category |  |  | Segment |  | At Start+New (cumulative) | Dropped Out (cumulative) | Dropout % |  | Highest Single-Row Rate
A. Learner Dropout |  |  | Girls <18 |  | 0 | 0 |  |  | 0%
A. Learner Dropout |  |  | Boys <18 |  | 0 | 0 |  |  | 0%
B. Staff Dropout / Turnover - by Designation |  |  | Female 18+ |  | 0 | 0 |  |  | 0%
B. Staff Dropout / Turnover - by Designation |  |  | Male 18+ |  | 0 | 0 |  |  | 0%
C. Volunteer Dropout / Turnover - by Designation & Rohingya/Host |  |  | Female 18+ |  | 0 | 0 |  |  | 0%
C. Volunteer Dropout / Turnover - by Designation & Rohingya/Host |  |  | Male 18+ |  | 0 | 0 |  |  | 0%

## 12b. Attendance Tracker
12b. Attendance Tracker - Learners (by Camp, Month-wise under Quarter)
Monthly average attendance rate per camp, split Girls <18 / Boys <18, grouped under quarter. Sourced from CBLF daily/weekly attendance registers (Field Reporting Templates, Attendance Sheets 14-15) - enter the monthly average enrolled and average present, and Attendance % calculates automatically. This is a facility-level trend view; event-level attendance for specific sessions/trainings is recorded per-event in the Activity Data Log (Sheet 10).
Camp | Segregation | Metric | Q1 |  |  | Q2 |  |  | Q3 |  |  | Q4 |  |  | Q5 |  |  | Q6 |  |  | Q7 |  |  | Q8
|  |  | 06/2026 | 07/2026 | 08/2026 | 09/2026 | 10/2026 | 11/2026 | 12/2026 | 01/2027 | 02/2027 | 03/2027 | 04/2027 | 05/2027 | 06/2027 | 07/2027 | 08/2027 | 09/2027 | 10/2027 | 11/2027 | 12/2027 | 01/2028 | 02/2028 | 03/2028 | 04/2028 | 05/2028
Camp 1W | Girls <18 | Avg Enrolled
Avg Present
Attendance %
| Boys <18 | Avg Enrolled
Avg Present
Attendance %
Camp 6 | Girls <18 | Avg Enrolled
Avg Present
Attendance %
| Boys <18 | Avg Enrolled
Avg Present
Attendance %
Camp 21 | Girls <18 | Avg Enrolled
Avg Present
Attendance %
| Boys <18 | Avg Enrolled
Avg Present
Attendance %
Camp 24 | Girls <18 | Avg Enrolled
Avg Present
Attendance %
| Boys <18 | Avg Enrolled
Avg Present
Attendance %
Compile - Automatic Summary (age-segregated, month-wise)
Live formulas only - each row below directly references the Attendance % row already computed for that Camp + Age segment above, consolidated here for a single month-wise read (and for the Dashboard).
Camp | Age Segment |  | Q1 |  |  | Q2 |  |  | Q3 |  |  | Q4 |  |  | Q5 |  |  | Q6 |  |  | Q7 |  |  | Q8
|  |  | 06/2026 | 07/2026 | 08/2026 | 09/2026 | 10/2026 | 11/2026 | 12/2026 | 01/2027 | 02/2027 | 03/2027 | 04/2027 | 05/2027 | 06/2027 | 07/2027 | 08/2027 | 09/2027 | 10/2027 | 11/2027 | 12/2027 | 01/2028 | 02/2028 | 03/2028 | 04/2028 | 05/2028
Camp 1W | Girls <18
Camp 1W | Boys <18
Camp 6 | Girls <18
Camp 6 | Boys <18
Camp 21 | Girls <18
Camp 21 | Boys <18
Camp 24 | Girls <18
Camp 24 | Boys <18

## 13. Budget Tracker
13. Activity-wise Smart Budget Tracking - A. Monthly
SMART = Specific (real budget lines, not lump sums), Measurable (EUR/BDT with running %), Assigned (cross-referenced to Activity Tracker codes), Realistic (FIVDB's actual approved Detailed Budget), Time-bound (tracked monthly, rolled up to quarterly/yearly/total). Uses the Detailed Budget's own R1A1-R1A7/R2A1-R2A5 coding - DIFFERENT in scope from the Activity Tracker's Annex-18-based codes; see the Activity Tracker's own 'Related Budget Line' column for the reverse cross-reference. Enter cumulative-to-date expenditure (BDT) in the month it was incurred - Total Spent, % Utilised and Remaining Budget calculate automatically. Project period: Jun 2026 - May 2028 (24 months).
Budget Line | Budget Line Title | Approved Budget (BDT) | Approved Budget (EUR) | Monthly expenditure, cumulative-to-date (BDT) - enter each month | [23 empty] | Total Spent (BDT) | % Utilised | Remaining (EUR)
|  |  |  | 06/2026 | 07/2026 | 08/2026 | 09/2026 | 10/2026 | 11/2026 | 12/2026 | 01/2027 | 02/2027 | 03/2027 | 04/2027 | 05/2027 | 06/2027 | 07/2027 | 08/2027 | 09/2027 | 10/2027 | 11/2027 | 12/2027 | 01/2028 | 02/2028 | 03/2028 | 04/2028 | 05/2028
R1A1 | Identification, assessment and appropriate placement of out-of-school and dropout children, incl. disability screening (min. 3% target) | 40000 | 279.7203 | [24 empty] | 0 | 0% | 279.7203
R1A2 | Education Service Delivery Support: learning materials, teaching-volunteer incentives, CBLF minimum package, solar/fire safety, maintenance, assistive devices | 27698100 | 193693.007 | [24 empty] | 0 | 0% | 193693.007
R1A3 | Gender-Appropriate Dignity Kits and MHM Support for adolescent girls | 2460240 | 17204.4755 | [24 empty] | 0 | 0% | 17204.4755
R1A4 | Strengthening Technical/Operational Capacities of Staff, Teaching Volunteers and Consortium Partners | 1248000 | 8727.2727 | [24 empty] | 0 | 0% | 8727.2727
R1A5 | Community Engagement (CESG), Caregiver Support and SEL Storybooks | 1095160 | 7658.4615 | [24 empty] | 0 | 0% | 7658.4615
R2A1 | Child protection case management services (identification, assessment, planning, referral, closure) | 1963000 | 13727.2727 | [24 empty] | 0 | 0% | 13727.2727
R2A2 | Establish and/or refurbish Multipurpose Centres + deliver MHPSS (shown as 0 in source - costs captured under R2A3 below) | 0 | 0 | [24 empty] | 0 |  | 0
R2A3 | PSS and protection-focused group interventions via MPCACs (incl. establishment, ISMF, Men & Boys Engagement, dignity/MHM kits) | 10455800 | 73117.4825 | [24 empty] | 0 | 0% | 73117.4825
R2A4 | Strengthening community-based protection mechanisms (CBCPC, PALS, risk mapping, IPT/puppet, DRR training) | 11822800 | 82676.9231 | [24 empty] | 0 | 0% | 82676.9231
R2A5 | Capacity-building for frontline staff/volunteers on CP-GBV integration | 295200 | 2064.3357 | [24 empty] | 0 | 0% | 2064.3357
HR | Human Resources (all local staff salaries - Project Coordinator, Technical Coordinator, officers, M&E, admin, etc.) | 19514848 | 136467.4685 | [24 empty] | 0 | 0% | 136467.4685
RunCosts | Running Costs (staff/support travel, office rent & utilities, communications) | 5494500 | 38423.0769 | [24 empty] | 0 | 0% | 38423.0769
Equip | Equipment (laptops, furniture and fixtures) | 960500 | 6716.7832 | [24 empty] | 0 | 0% | 6716.7832
Indirect | Indirect Costs (Local Partner ICR, max 2% of direct costs) | 1660963.59 | 11615.13 | [24 empty] | 0 | 0% | 11615.13
| TOTAL (all budget lines) | 84709111.59 | 592371.4097 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | 592371.4097

## 13b. Budget - Quarterly
13b. Activity-wise Smart Budget Tracking - B. Quarterly
Auto-rolled up from the Monthly tab (Sheet 13) - Q1 = Jun-Aug 2026 ... Q8 = Mar-May 2028. Cumulative expenditure to the END of each quarter.
Budget Line | Budget Line Title | Approved Budget (BDT) | Cumulative expenditure by quarter (BDT) | [7 empty] | Total Spent (BDT) | % Utilised
|  |  | Q1 | Q2 | Q3 | Q4 | Q5 | Q6 | Q7 | Q8
R1A1 | Identification, assessment and appropriate placement of out-of-school and dropout children, incl. disability screening (min. 3% target) | 40000 | [8 empty] | 0 | 0%
R1A2 | Education Service Delivery Support: learning materials, teaching-volunteer incentives, CBLF minimum package, solar/fire safety, maintenance, assistive devices | 27698100 | [8 empty] | 0 | 0%
R1A3 | Gender-Appropriate Dignity Kits and MHM Support for adolescent girls | 2460240 | [8 empty] | 0 | 0%
R1A4 | Strengthening Technical/Operational Capacities of Staff, Teaching Volunteers and Consortium Partners | 1248000 | [8 empty] | 0 | 0%
R1A5 | Community Engagement (CESG), Caregiver Support and SEL Storybooks | 1095160 | [8 empty] | 0 | 0%
R2A1 | Child protection case management services (identification, assessment, planning, referral, closure) | 1963000 | [8 empty] | 0 | 0%
R2A2 | Establish and/or refurbish Multipurpose Centres + deliver MHPSS (shown as 0 in source - costs captured under R2A3 below) | 0 | [8 empty] | 0
R2A3 | PSS and protection-focused group interventions via MPCACs (incl. establishment, ISMF, Men & Boys Engagement, dignity/MHM kits) | 10455800 | [8 empty] | 0 | 0%
R2A4 | Strengthening community-based protection mechanisms (CBCPC, PALS, risk mapping, IPT/puppet, DRR training) | 11822800 | [8 empty] | 0 | 0%
R2A5 | Capacity-building for frontline staff/volunteers on CP-GBV integration | 295200 | [8 empty] | 0 | 0%
HR | Human Resources (all local staff salaries - Project Coordinator, Technical Coordinator, officers, M&E, admin, etc.) | 19514848 | [8 empty] | 0 | 0%
RunCosts | Running Costs (staff/support travel, office rent & utilities, communications) | 5494500 | [8 empty] | 0 | 0%
Equip | Equipment (laptops, furniture and fixtures) | 960500 | [8 empty] | 0 | 0%
Indirect | Indirect Costs (Local Partner ICR, max 2% of direct costs) | 1660963.59 | [8 empty] | 0 | 0%

## 13c. Budget - Yearly & Total
13c. Activity-wise Smart Budget Tracking - C. Yearly & Total Project Period
Year 1 = Jun 2026-May 2027 (Q1-Q4); Year 2 = Jun 2027-May 2028 (Q5-Q8). Total column = full 24-month project period. Auto-rolled up from the Quarterly tab (Sheet 13b).
Budget Line | Budget Line Title | Approved Budget (EUR) | Year 1 Spent (EUR) | Year 2 Spent (EUR) | Total Spent (EUR) | % Utilised (Total) | Remaining (EUR)
R1A1 | Identification, assessment and appropriate placement of out-of-school and dropout children, incl. disability screening (min. 3% target) | 279.7203 | 0 | 0 | 0 | 0% | 279.7203
R1A2 | Education Service Delivery Support: learning materials, teaching-volunteer incentives, CBLF minimum package, solar/fire safety, maintenance, assistive devices | 193693.007 | 0 | 0 | 0 | 0% | 193693.007
R1A3 | Gender-Appropriate Dignity Kits and MHM Support for adolescent girls | 17204.4755 | 0 | 0 | 0 | 0% | 17204.4755
R1A4 | Strengthening Technical/Operational Capacities of Staff, Teaching Volunteers and Consortium Partners | 8727.2727 | 0 | 0 | 0 | 0% | 8727.2727
R1A5 | Community Engagement (CESG), Caregiver Support and SEL Storybooks | 7658.4615 | 0 | 0 | 0 | 0% | 7658.4615
R2A1 | Child protection case management services (identification, assessment, planning, referral, closure) | 13727.2727 | 0 | 0 | 0 | 0% | 13727.2727
R2A2 | Establish and/or refurbish Multipurpose Centres + deliver MHPSS (shown as 0 in source - costs captured under R2A3 below) | 0 | 0 | 0 | 0 |  | 0
R2A3 | PSS and protection-focused group interventions via MPCACs (incl. establishment, ISMF, Men & Boys Engagement, dignity/MHM kits) | 73117.4825 | 0 | 0 | 0 | 0% | 73117.4825
R2A4 | Strengthening community-based protection mechanisms (CBCPC, PALS, risk mapping, IPT/puppet, DRR training) | 82676.9231 | 0 | 0 | 0 | 0% | 82676.9231
R2A5 | Capacity-building for frontline staff/volunteers on CP-GBV integration | 2064.3357 | 0 | 0 | 0 | 0% | 2064.3357
HR | Human Resources (all local staff salaries - Project Coordinator, Technical Coordinator, officers, M&E, admin, etc.) | 136467.4685 | 0 | 0 | 0 | 0% | 136467.4685
RunCosts | Running Costs (staff/support travel, office rent & utilities, communications) | 38423.0769 | 0 | 0 | 0 | 0% | 38423.0769
Equip | Equipment (laptops, furniture and fixtures) | 6716.7832 | 0 | 0 | 0 | 0% | 6716.7832
Indirect | Indirect Costs (Local Partner ICR, max 2% of direct costs) | 11615.13 | 0 | 0 | 0 | 0% | 11615.13
| TOTAL PROJECT PERIOD (Jun 2026 - May 2028) | 592371.4097 | 0 | 0 | 0 | 0% | 592371.4097
Cross-check: Approved Budget total should equal 592,371.41 EUR (84,709,111.59 BDT), matching the Logframe's approved FIVDB allocation exactly.

## 14. Activity List (for sharing)
14. Activity List - FIVDB Implementation Activities (Simplified, for Team Sharing)
A clean, non-technical extract of the Activity Tracker (Sheet 8), for circulating to field teams, partners or new staff who need the activity list without the tracking formulas/columns. Planned Start/End Quarter is derived from the Activity Tracker's PLANNED columns (first and last 'X' marked quarter). Q1 = Jun-Aug 2026 ... Q8 = Mar-May 2028.
Result | Activity Code | Sub-activity Code | Activity Description | Location | Target | Unit | Responsible | Planned Start (Quarter) | Planned End (Quarter)
Result 1 | R1A1 | R1A1.1 | Conduct household survey through community volunteers to identify out-of-school and dropout children. | Camps 1W, 6, 21, 24 | All target households surveyed | survey | Education Officer | - | -
Result 1 | R1A1 | R1A1.2 | Conduct technical/disability assessment and screening of identified children (minimum 3% disability target), referring complex cases to Humanity & Inclusion (HI) under FIVDB's MoU. | Camps 1W, 6, 21, 24 | Minimum 3% of 1,224 children (~37) | children | Education Officer | - | -
Result 1 | R1A1 | R1A1.3 | Print placement/assessment and disability-screening tools. | Camps 1W, 6, 21, 24 | 1 lumpsum print run, 4 times | lumpsum | Education Officer | - | -
Result 1 | R1A2 | R1A2.1 | Provide monthly incentives to host-community teacher volunteers. | Camps 1W, 6, 21, 24 | 17 volunteers x 22 months | volunteers | Education Officer | - | -
Result 1 | R1A2 | R1A2.2 | Provide monthly incentives to refugee-community teacher volunteers. | Camps 1W, 6, 21, 24 | 51 volunteers x 22 months | volunteers | Education Officer | - | -
Result 1 | R1A2 | R1A2.3 | Distribute scholastic material kits (exercise books, ALP books, drawing books, pens, pencils, water bottle, erasers, sharpeners) to enrolled children, 2 shifts per CBLF. | Camps 1W, 6, 21, 24 | 1,224 children, 2-year supply | children | Education Officer | - | -
Result 1 | R1A2 | R1A2.4 | Distribute one school bag per enrolled child (one-time distribution). | Camps 1W, 6, 21, 24 | 1,224 children, one-time | children | Education Officer | - | -
Result 1 | R1A2 | R1A2.5 | Provide assistive devices and reasonable accommodation for children with disabilities (device cost only; assessment carried out by HI). | Camps 1W, 6, 21, 24 | ~37 children (3% of 1,224) | children | Education Officer | - | -
Result 1 | R1A2 | R1A2.6 | Provide the CBLF minimum package (floor mats, whiteboards, boxes, stationery, cleaning materials). | Camps 1W, 6, 21, 24 | 51 CBLFs, 2-year supply | facilities | Education Officer | - | -
Result 1 | R1A2 | R1A2.7 | Install solar panels, lighting and fire extinguishers at all CBLFs. | Camps 1W, 6, 21, 24 | 51 CBLFs, one-time | facilities | Education Officer | - | -
Result 1 | R1A2 | R1A2.8 | Cover ongoing CBLF maintenance costs. | Camps 1W, 6, 21, 24 | 51 CBLFs, half-yearly x4 | facilities | Education Officer | - | -
Result 1 | R1A2 | R1A2.9 | Produce and display IEC materials (safeguarding, child protection, PSHEA posters) at all CBLFs. | Camps 1W, 6, 21, 24 | 51 CBLFs, one-time | facilities | Education Officer | - | -
Result 1 | R1A2 | R1A2.10 | Provide teacher kits (diary, pens, water bottle, teacher's guide). | Camps 1W, 6, 21, 24 | 68 teachers, 2-year supply | teachers | Education Officer | - | -
Result 1 | R1A2 | R1A2.11 | Provide teacher kits (bag and umbrella), annual distribution. | Camps 1W, 6, 21, 24 | 68 teachers, annual | teachers | Education Officer | - | -
Result 1 | R1A3 | R1A3.1 | Distribute standard MHM kits (reusable pads, underwear, laundry soap) to adolescent girls. | Camps 1W, 6, 21, 24 | ~820 girls, 2-year supply | girls | Education Officer | - | -
Result 1 | R1A4 | R1A4.1 | Deliver the 5-day basic training for teaching volunteers (once every 2 years, TiCC-aligned, CBLF-based). | Camps 1W, 6, 21, 24 | 68 participants, 5 days | participants | Education Officer | - | -
Result 1 | R1A4 | R1A4.2 | Deliver the 6-day subject-based (ALP curriculum) training for teaching volunteers. | Camps 1W, 6, 21, 24 | 68 participants, 12 days total | participants | Education Officer | - | -
Result 1 | R1A4 | R1A4.3 | Deliver quarterly refresher training for project personnel and teaching volunteers within the CBLF. | Camps 1W, 6, 21, 24 | 68 participants, 7 days/year | participants | Education Officer | - | -
Result 1 | R1A4 | R1A4.4 | Deliver cascading training for teachers on PSS, gender, SRHR, CAAFAG and referral mechanisms. | Camps 1W, 6, 21, 24 | 68 participants, 4 days | participants | Education Officer | - | -
Result 1 | R1A4 | R1A4.5 | Deliver the 2-day cascade training on Protective Education Services for teaching volunteers. | Camps 1W, 6, 21, 24 | 68 participants, 2 days | participants | Education Officer | - | -
Result 1 | R1A4 | R1A4.6 | Deliver ToT on Gender-Responsive Pedagogy for Inclusive and Gender-Responsive Learning (staff). | Camps 1W, 6, 21, 24 | 15 participants, 2 days | participants | Education Officer | - | -
Result 1 | R1A4 | R1A4.7 | Cascade the Gender-Responsive Pedagogy training from staff ToT to all teaching volunteers. | Camps 1W, 6, 21, 24 | 68 participants, 1 day | participants | Education Officer | - | -
Result 1 | R1A4 | R1A4.8 | Deliver ToT on Empowerment: Decision-Making and Resilience for Rohingya Women and Adolescent Girls (staff). | Camps 1W, 6, 21, 24 | 12 participants, 1 day | participants | Education Officer | - | -
Result 1 | R1A4 | R1A4.9 | Cascade the Empowerment/Decision-Making/Resilience session from staff ToT to teaching volunteers. | Camps 1W, 6, 21, 24 | 68 participants, 1 day | participants | Education Officer | - | -
Result 1 | R1A4 | R1A4.10 | Hold quarterly Male Allyship and Community Leadership Circles for Gender Justice (camp-based, incl. SC). | Camps 1W, 6, 21, 24 | 200 male participants, quarterly | participants | Technical Coordinator–Protection | - | -
Result 1 | R1A4 | R1A4.11 | Deliver ToT on Gender Equality in Education for field staff, facilitators and consortium partners. | Camps 1W, 6, 21, 24 | 25 participants, 2 days | participants | Education Officer | - | -
Result 1 | R1A4 | R1A4.12 | Cascade the Gender Equality in Education training from ToT to field staff/facilitators. | Camps 1W, 6, 21, 24 | 68 participants, 4 days | participants | Education Officer | - | -
Result 1 | R1A4 | R1A4.13 | Facilitate Adolescent Girls' Safe Circles for Leadership and Protection (per centre, peer group). | Camps 1W, 6, 21, 24 | 22 participants, 1 day | participants | Education Officer | - | -
Result 1 | R1A4 | R1A4.14 | Hold monthly project progress/coordination meetings. | Camps 1W, 6, 21, 24 | 15 participants, 24 days/2yrs | participants | Project Manager | - | -
Result 1 | R1A5 | R1A5.1 | Provide SEL storybooks to CBLFs to ensure a joyful learning environment. | Camps 1W, 6, 21, 24 | 67 copies, one-time | copies | Education Officer | - | -
Result 1 | R1A5 | R1A5.2 | Hold bi-monthly CESG meetings (7-8 members per CESG, 1 CESG per 2 CBLFs). | Camps 1W, 6, 21, 24 | 204 persons, 12 sessions/2yrs | persons | Education Officer | - | -
Result 1 | R1A5 | R1A5.3 | Hold bi-monthly parent/caregiver engagement meetings (1 parent per enrolled child). | Camps 1W, 6, 21, 24 | 1,224 persons, 12 sessions/2yrs | persons | Education Officer | - | -
Result 2 | R2A1 | R2A1.1 | Identify and enhance the capacity of alternative-care family members (foster and kinship) for unaccompanied/separated children (UASC). | Camps 1W, 6, 21, 24 | 12 participants, 3-day training | participants | Technical Coordinator–Protection | - | -
Result 2 | R2A1 | R2A1.2 | Provide case-management need-based and emergency support (NFIs) to children/families in active cases. | Camps 1W, 6, 21, 24 | 320 children, needs-based | children | Technical Coordinator–Protection | - | -
Result 2 | R2A1 | R2A1.3 | Maintain functioning Case Management Offices (1 per camp). | Camps 1W, 6, 21, 24 | 4 camps, one-time set-up + running | camps | Technical Coordinator–Protection | - | -
Result 2 | R2A1 | R2A1.4 | Deliver case management services per the CPMS 7-step process (non-budgetary - covered by CM Officer/volunteer time). | Camps 1W, 6, 21, 24 | 320 children caseload | children | Case Management Officer | - | -
Result 2 | R2A1 | R2A1.5 | Train para-social workers, volunteers and facilitators on referral pathways. | Camps 1W, 6, 21, 24 | 20 participants, 1 day | participants | Technical Coordinator–Protection | - | -
Result 2 | R2A1 | R2A1.6 | Provide monthly incentives to case-management volunteers (2 per camp, all refugees) for identification and referral. | Camps 1W, 6, 21, 24 | 8 volunteers x 11 months | volunteers | Technical Coordinator–Protection | - | -
Result 2 | R2A1 | R2A1.7 | Provide support-material kits (case-worker kits) for case-management service providers. | Camps 1W, 6, 21, 24 | 10 participants, lumpsum | participants | Technical Coordinator–Protection | - | -
Result 2 | R2A3 | R2A3.1 | Construct new MPCACs and refurbish existing MPCACs, including running costs. | Camps 1W, 6, 21, 24 | 4 new + 2 refurbished + 6 running | facilities | Technical Coordinator–Protection | - | -
Result 2 | R2A3 | R2A3.2 | Roll out 'I Support My Friend' (ISMF) at community level, including inception meeting and adolescent training. | Camps 1W, 6, 21, 24 | 100 participants, inception + 3-day training | participants | Technical Coordinator–Protection | - | -
Result 2 | R2A3 | R2A3.3 | Deploy MPCAC facilitators (refugee volunteers, host-community volunteers, security guards) to run PSS/awareness sessions. | Camps 1W, 6, 21, 24 | 18 persons (6+6+6) x 11 months | persons | Technical Coordinator–Protection | - | -
Result 2 | R2A3 | R2A3.4 | Orient and engage proactive Men and Boys in GBV prevention and response (bi-weekly sessions). | Camps 1W, 6, 21, 24 | 20 persons/camp x 4 camps, 88 sessions | persons | Technical Coordinator–Protection | - | -
Result 2 | R2A3 | R2A3.5 | Deliver community-led activities on CP and GBV issues (day/event observation). | Camps 1W, 6, 21, 24 | 4 events, 3 times | events | Technical Coordinator–Protection | - | -
Result 2 | R2A3 | R2A3.6 | Provide Dignity Kits and Menstrual and Hygiene Management (MHM) kit support to adolescent girls (CP side). | Camps 1W, 6, 21, 24 | 1,814 persons | persons | Technical Coordinator–Protection | - | -
Result 2 | R2A4 | R2A4.1 | Deliver DRR & Climate Resilience training for community leaders and volunteers. | Camps 1W, 6, 21, 24 | 240 persons, 2 days | persons | Technical Coordinator–Protection | - | -
Result 2 | R2A4 | R2A4.2 | Deliver PALS sessions for parents and adolescents (10-14 sessions per group). | Camps 1W, 6, 21, 24 | 4,320 adolescents + 4,320 caregivers | individuals | Technical Coordinator–Protection | - | -
Result 2 | R2A4 | R2A4.3 | Form/reform CBCPCs and hold monthly/bi-monthly meetings (2 CBCPCs per camp, 17 members each). | Camps 1W, 6, 21, 24 | 136 members, monthly x10 | members | Technical Coordinator–Protection | - | -
Result 2 | R2A4 | R2A4.4 | Deliver 2-day CBCPC member training, twice yearly (2 CBCPCs/camp x 17 members x 4 camps). | Camps 1W, 6, 21, 24 | 136 members, 2 days x2/year | members | Technical Coordinator–Protection | - | -
Result 2 | R2A4 | R2A4.5 | Conduct child-protection risk mapping and develop community-led prevention/response/referral plans. | Camps 1W, 6, 21, 24 | 8 mapping exercises | mapping | Technical Coordinator–Protection | - | -
Result 2 | R2A4 | R2A4.6 | Deliver Art for Awareness - Interactive Popular Theatre (IPT) and puppet shows for CP & GBV behaviour change. | Camps 1W, 6, 21, 24 | 4 events | events | Technical Coordinator–Protection | - | -
Result 2 | R2A5 | R2A5.1 | Deliver capacity-enhancing training for other-sector staff (health, education, nutrition, WASH) on CP integration and case-referral systems. | Camps 1W, 6, 21, 24 | 25 participants, 1 day | participants | Technical Coordinator–Protection | - | -
Result 2 | R2A5 | R2A5.2 | Hold quarterly coordination meetings with camp service providers (CiC and relevant stakeholders). | Camps 1W, 6, 21, 24 | 4 camps, quarterly x2 | camps | Project Manager | - | -
Result 2 | R2A5 | R2A5.3 | Enhance the capacity of implementing partners on CP and operations. | Camps 1W, 6, 21, 24 | 20 participants, 1 day | participants | Technical Coordinator–Protection | - | -
Result 2 | R2A5 | R2A5.4 | Conduct quarterly joint field-monitoring visits with government officials (CiC office and other actors). | Camps 1W, 6, 21, 24 | 4 camps, quarterly x4 | camps | Project Manager | - | -
Result 2 | R2A5 | R2A5.5 | Hold a project inception workshop with relevant stakeholders at camp level. | Camps 1W, 6, 21, 24 | 4 camps, one-time | camps | Project Manager | - | -
Preparatory | INC | INC-1 | Recruit and onboard FIVDB Education and Child Protection staff (Education Officer, Education Assistant, Technical Coordinator–Protection, case workers, facilitators). | Camps 1W, 6, 21, 24 | Full staffing complement in place | staff | Project Manager | - | -
Preparatory | INC | INC-2 | Coordinate FD7 government approval process with SC/PIB for FIVDB's operational camps. | Camps 1W, 6, 21, 24 | FD7 approval secured | approval | Project Manager | - | -
Preparatory | INC | INC-3 | Participate in project kick-off meeting and partnership review meetings (CP, Education) with PIB and SC. | Cox's Bazar (consortium level) | Kick-off + quarterly partnership review | meetings | Project Manager | - | -
Preparatory | INC | INC-4 | Adopt/contextualise SOPs (case management, referral pathway, safeguarding, MEAL tools) jointly with PIB. | Camps 1W, 6, 21, 24 | SOPs signed off | SOPs | Technical Coordinator–Protection | - | -
Preparatory | INC | INC-5 | Conduct joint site verification and mapping of CBLF/GoLF and MPCAC locations with PIB. | Camps 1W, 6, 21, 24 | 51 education sites + MPCAC sites mapped | sites | Education Officer | - | -
Preparatory | INC | INC-6 | Support data collection for the baseline / KAP survey in FIVDB's camps. | Camps 1W, 6, 21, 24 | Baseline data collected for FIVDB camps | survey | MEAL Officer | - | -
Preparatory | INC | INC-7 | Support preparation and submission of FD-6 documentation (distinct from the FD7 camp-access approval in INC-2). | Cox's Bazar / national level | FD-6 submitted and cleared | submission | Project Manager | - | -
Preparatory | INC | INC-8 | Sign the FIVDB-PIB partnership/sub-agreement setting out roles, budget and reporting lines. | Cox's Bazar (consortium level) | Signed partnership agreement | agreement | Project Manager | - | -
Preparatory | INC | INC-9 | Conduct staff orientation and induction (project kick-off) for newly recruited FIVDB staff. | Camps 1W, 6, 21, 24 | All newly recruited staff oriented | staff | Project Manager | - | -
Preparatory | INC | INC-10 | Participate in the project inception meeting with government stakeholders at union, upazila, district and national level. | Cox's Bazar + national level | Inception meeting(s) held | meetings | Project Manager | - | -
Preparatory | INC | INC-11 | Participate in the SC-led consortium MEAL Plan workshop (2 days). | Cox's Bazar (consortium level) | FIVDB MEAL staff attend | workshop | MEAL Officer | - | -
Preparatory | INC | INC-12 | Participate in SC-led training on Accountability and Safeguarding for all FIVDB staff and volunteers. | Camps 1W, 6, 21, 24 | All FIVDB staff/volunteers trained | individuals | Project Manager | - | -
General | GEN | GEN-1 | Attend regular coordination meetings with implementing partners (PIB, SC, JCF, BTS, PHD) and other stakeholders. | Cox's Bazar (consortium level) | Regular attendance throughout | meetings | Project Manager | - | -
General | GEN | GEN-2 | Conduct a safeguarding and GBV risk assessment of any prospective site before it is selected/established as a CBLF, GoLF, MPCAC or other facility (venue safety, lighting, privacy, access routes, presence of known risks). | Camps 1W, 6, 21, 24 | All new sites screened before establishment | sites | Technical Coordinator–Protection | - | -
General | GEN | GEN-3 | Conduct a safeguarding risk screening before any group activity, training, distribution or community event (adult-to-child ratios, presence of trusted adults, venue safety, transport/pick-up arrangements). | Camps 1W, 6, 21, 24 | Screening completed before every group event | events | Technical Coordinator–Protection | - | -
General | GEN | GEN-4 | Ensure gender mainstreaming and EU Gender-Age Marker compliance across all FIVDB activities (gender-responsive design review of facilities and sessions, sex/age-disaggregated monitoring, gender-balanced staffing and participation). | Camps 1W, 6, 21, 24 | All activities reviewed for gender/age responsiveness | review | MEAL Officer | - | -
Closeout | CLOSE | CLOSE-1 | Contribute to the national and local level lesson-learned workshop. | Cox's Bazar + national level | FIVDB participation and case examples shared | workshop | Project Manager | - | -
Closeout | CLOSE | CLOSE-2 | Support the SC-led external final evaluation (data access, KIIs/FGDs, verification of final indicator values). | Camps 1W, 6, 21, 24 | Full cooperation with evaluators | evaluation | MEAL Officer | - | -
Closeout | CLOSE | CLOSE-3 | Contribute FIVDB content (photos, case/success stories, quotes) to the consortium's video documentary and other visibility/media and printing products. | Camps 1W, 6, 21, 24 | FIVDB content supplied on request | products | MEAL Officer | - | -